AMBO UNIVERSITY

COLLEGE OF BUSINESS AND ECONOMICS

DEPARTMENT OF ACCOUNTING AND FINANCE

FACTORS AFFECTING REAL ESTATE CONSTRUCTION PROJECTS' SUCCESS IN ADDIS ABABA CITY

A Thesis summited to the Department of Accounting and Finance for partial Fulfillment of Masters of Business Administration in Finance (MBA) in Finance

BY: ABEBE CHALA MAKO         ID. No.: MEB/0076/10

ADVISOR: KOTA MADHUSUDHANA RAO (Dr)

December, 2023

AMBO

AMBO UNIVERSITY

COLLEGE OF BUSINESS AND ECONOMICS, DEPARTMENT OF ACCOUNTIG AND FINANCE

## APPROVAL SHEET

Submitted By;

Abebe Chala Mako                             __________________         __________________

Approved BY;                                               Signature                                    Date

Advisor

Dr KOTA MADHUSUDHANA RAO_________________           _________________

Name                                                               Signature                                Date

Head of Department

Tadele Assefa                                          _________________            _________________

Name                                                               Signature                             Date

College Institute Dean

________________                                __________________          –––––––––––––––––

Name                                                               Signature                                Date

Directors School of Graduate

_____________________                       _________________             ––––––––––––––––

Name                                                               Signature                             Date

AMBO UNIVERSITY

COLLEGE OF BUSINESS AND ECONOMICS, DEPARTMENT OF ACCOUNTIG AND FINANCE

## CERTIFICATION SHEET

A thesis research advisor, I hereby certify that I have read and evaluated this thesis prepared under my guidance by Abebe Chala Mako entitled" Factors affect real estate construction Success projects in Addis Ababa ”.I recommends that it be submitted as fulfilling the thesis requirement.

–––––––––––––––––––––––––––––––––               –––––––––––––

Name of Major Advisor                   Signature                              Date

–––––––––––––––––––             ––––––––––––––               –––––––––––––

Name of Co- Advisor                        Signature                              Date

As mentioned of the Board of Examiners of the M. SC/MA. Thesis open defense examined. We certified that we have read and evaluated the thesis prepared by––––––––––––––– and examined the candidate. We recommend that the thesis be accepted as fulfilling the thesis requirements for the degree of Master of Science/Art in –––––––––––––––––––––––

––––––––––––––––––                 –––––––––––––––––               –––––––––––––––

Chairperson	Signature	Date

––––––––––––––––––                 –––––––––––––––––               –––––––––––––––

Internal Examiner	Signature	Date

––––––––––––––––––                 –––––––––––––––––               –––––––––––––––

External Examiner	Signature	Date

## DECLARATION

I, the undersigned, declare that this thesis entitled “Factors affect real estate construction projects success in Addis Ababa” is my original work, prepared under the guidance of the research advisor. All sources of materials used for the thesis have been duly acknowledged. I further confirm that the thesis has not been submitted either in part or in full to any other higher learning institution for the purpose of earning any degree.

Name of Candidate:  Abebe Chala Mako    Signature: ________________

Ambo University Date: Dec, 2023

## DEDICATION

I need this work to be dedicated to my Eldest Sister W/ro. Ayelu Chala Mako, who passed away without seeing what they were dreaming for my life.

Abebe Chala Mako

## ACKNOWLEDGEMENTS

First and for most, my heartily thanks go to Almighty God, for his kindly provision of knowledge,

Wisdom, inspiration and diligence required for the successful completion of this research and for

bringing my dreams into reality.

I am deeply indebted to my advisor Kota Madhusudhana Rao (PhD) whom during this period has not only kept me on track, but provided invaluable advice and support.

I am thankful to my wife W/ro Asmera Ketema for all her unfailing support during this research

Study. Many thanks to Dr Lemma Fita and Ato Adisu Getahun for them advise me during this research study.

Kind gratitude and sincere acknowledgment to all HARC Finance staffs especially Ato Takele Ergete, Ato Tilahun Tibebu,W/ro Senait Shibiru, Ato Chala Akesa, Ato Alemayehu Teshome,W/ro Bire Kifle and W/ro Gadise Tesgera who were supported me during this

research study.

Thank you

Abebe Chala

Contents

APPROVAL SHEET	ii

CERTIFICATION SHEET	iii

DECLARATION	iv

DEDICATION	v

ACKNOWLEDGEMENTS	vi

List of Table	x

Abstract	xi

CHAPTER ONE	1

INTRODUCTION	1

1.1. Back Ground of the study	1

1.2. Statement of the problem	2

1.3. Research Questions	3

1.4. Objectives of the study	3

1.4.1. General Objective	3

1.4.2. Specific Objectives	4

1.5. Scope and Limitation of the Study	6

1.5.1. Scope of the study	6

1.6. Significance of the Study	6

1.7. Organization of the Study/Structure of the Study	7

CHAPTER TWO	8

LITERATURE REVIEW	8

2.1. Introduction	8

2.2. Conceptual Literature	8

2.2.1. Project and Project Management	8

2.2.2. Project Management	10

2.2.3. Success in Projects	11

2.2.4. Project Success and Project Management Success	12

2.2.5. Project Management in Construction Projects	14

2.2.6. Real Estate and Real Estate development in Ethiopia	14

2.3. Theoretical Literature	15

2.3.1 Project Success Factors	15

2.3.2. Success Factors for Construction Projects	16

2.3.3. Project Success Criteria	18

2.4. Empirical Review	22

CHAPTER THREE	26

RESEARCH METHODOLOGY	26

3. INTRODUCTION	26

3.1. Research Design and Approach	26

3.2. Study Area and Period	26

3.3. Types and Sources of Data	26

3.4. Sample Design	27

3.4.1. Population	27

3.4.2. Target population	27

3.5. Data Collection Methods	27

3.6. Data Analysis Techniques	28

3.7. Empirical Models Specification	29

CHAPTER FOUR	30

DATA ANALYSES AND INTERPRETATION	30

4.1 General Information about Respondents	30

4.2. General Profile of Sampled Respondents	32

4.3. Critical Success Factors Ranking	32

4.4. Critical Success Factors	33

4.1.4 Project Success (Success Criteria)	40

4.2. Correlation Analysis	40

4.3 Model Estimation	43

CHAPTER FIVE	47

CONCLUSION AND RECOMMENDATIONS	47

5.1. Conclusions	47

Recommendation	49

References	51

Appendix A	55

Appendix B	61

## List of Table

Table 4.1. Demographic profile of respondents

Table 4.2. Critical success factors rank

Table 4.3. Organizational Planning

Table 4.4. Project managers’ goal commitment

Table 4.5. Project team’s motivation and goal orientation

Table 4.6. Project’s scope and work definition

Table 4.7. Project manager’s capabilities and experience

Table 4.8. Safety precautions and applied procedures

Table 4.9. Control systems

Table 4.10. Summary of critical success factors

Table 4.11. Project Success

Table 4.12. Relation measurement scale between variables

Table 4.13. Correlations analysis

Table 4.14. Results of logistic regression estimates of determinates of project management success

## Abstract

This research project entitled with Factors affecting the real estate construction project: The case of Addis Ababa City identify and describes the main factors affecting the real estate construction in Addis Ababa city. The study identified existing operations of the real estate companies in the market and with a focus on currently existing situations in most aspect of the market; major problems are addressed. The study has met its objectives through providing answers for the basic questions of how successful real estate development construction projects’ management are, what are the major  success factors for real estate development construction projects management; and what is the impact of success factors in real estate construction projects’ management. The study area is not adequately studied from Ethiopian real estate development companies’ perspective or not available which makes this study is valuable to fill the gap in the study area. The study is conducted on real estate developers in Addis Ababa. Both primary and secondary data were collected for the accomplishment of the study. All  the project managers who have completed at least one real estate development construction projects were incorporated in the study making the study to implement censes method. The primary data are collected through self-administered questionnaires. The study uses Ashley&Jaselskis’s (2011) seven critical success factors of construction projects as independent variables where project success is measured in terms of time, cost and quality that are used as dependent variables. Correlation technique was used to indicate the relationship between the independent and dependent variables and a Ordinary least square (OLS) has used to identify the impact of the success factors over successful project completion.

Key words: Project Management, Project Management Success, Success Criteria, Time, Cost, Motivation and Commitment, Control Systems and Scope

# CHAPTER ONE

# INTRODUCTION

## 1.1. Back Ground of the study

Construction industry plays a vital role in any developing country. This is mainly because developing countries are considerably dependent on the growth and development of their physical infrastructures and because the linkage of the construction industry to both economic and social sectors is very significant. A wide range of buildings and construction facilities are required by our modern society, including residential and commercial property, manufacturing facilities, schools, hospitals, complex transport infrastructure, and so on. Thus, the construction industry is a major sector of the economy of the country.

The construction industry is the largest and most complex fragmented industry involves owners (government, industry, private parties, and investors), designers and construction monitors (engineers and architects), constructors, field managers, supervisors and craftsmen. Furthermore, the product is usually "custom made," with almost every project a separate and unique entity, conceived, financed, designed, constructed, and operated separately. Construction sector is playing greater role in the development of Ethiopian economy. It is creating job opportunities to the wide unskilled workforce (due to its labor intensive nature), creating market opportunities for suppliers, facilitating the growth of other sectors and generating income for the government (Ethiopian Economic Association, 2008).

Several real estate companies in Ethiopia are mobilizing considerable amount of resources conducting number of projects in the development of residential buildings. As construction projects are known to be notorious to be completed in schedule and budget, most of the real estates in Ethiopia are observed to fail to complete and deliver the residential buildings according to plan. This calls for the critical factors that might contribute for the success or failure of real estate construction projects to be identified and focused on. A combination of factors determines the success or failure of a project and influencing these factors at the right time makes success more probable (Savolainen, 2015).

Therefore, education and research allow for the development of new and promising technologies for all concerned parties, thus creating significant savings in time and money to firms who take advantage of these developments is vital. Since it is a rather new phenomenon, construction research is constantly changing and the best actions to take are still being debated (Abudayyeh et al., 2009).Research and development is the main driving force toward the technology advancement of modern industry (Warszawski, 2012). Discussion with professionals along with reading of past studies and researches showed that construction related researches are not involved in the construction industry, because of many factors, some of these include the lack of communication between the construction professionals between the industry and institutes, the weakness of the construction industry to be involved in research and development work.

## 1.2. Statement of the problem

There are about 1580 registered real estates in Ethiopia, where 1441 are pre- implementation, 81 are in implementation, and 58 are in operational stage (AAIA, 2017). In Addis Ababa, around 125 real estates and from those there are only few which are in operating stage. Having all these real estates and observing that they are not active seems to indicate that there are a lot of issues that should be seriously considered. One main thing is that all the real estates are not working towards alleviating housing problems but working for business or commercial purposes. The drawback seen in the country as a whole is that there is no ratio et in the allocation of area for residential, commercial and industrial developments.

Constraints in the capacity and performance of local contractors and consultants, poor quality and productivity, ineffective utilization of appropriate construction technologies, and lack of proper application of building regulations and standards are also challenges of the nation’s construction and real estate sector (Minister of Urban Development and Housing Construction Report, 2017). The real estate sector shares the responsibility of addressing the increasing demand for residential houses in the nation’s major cities. Moreover, it is the nation’s precious resources that are being wasted whenever construction projects are turned out to be a failure. This calls for improvements to always be made on current practices to assure proper utilization of resources and successful conversion of resources in to outputs. To increase the likelihood of real estate construction projects, it worth studying the major success factors in the real estate construction projects and to what extent the success factors are impacting project success. Though it has been arguable between scholars of how to measure project success, most agree the requirement of critical success factors for successful project completion.

Project success factors are the elements of a project which, when influenced, increase the likelihood of success; these are the independent variables that make success more likely (Turner, 2010).These success factors need to be identified and focused on from the initialization stage of a project so that they could influence the project as much as expected. Rockart (2009) mentioned that to ensure future success, a company and its industry should identify its critical success factors.

The study conducted by Ashley &Jaselskis’s (2011) produced one of the famous findings in the study area identifying seven critical success factors particularly for construction projects. Besides Ashley &Jaselskis’s critical success factors, different studies conducted by Nguyen et al. (2004), Sanvido et al. (2010), Chua et al. (1999), Gudienė, Banaitis, Banaitienė,and Lopes (2013) and Cooper et al. (2001) are also available. However, no single study is available which is conducted on investigating the role of critical success factors on project success from Ethiopian companies’ perspective.

## 1.3. Research Questions

The study is conducted in search of answers for the following basic research questions:

- How successful real estate development construction projects’ are managed?

- What are the major critical success factors for real estate construction projects management?

- What is the impact of critical success factors in real estate construction projects’ management success?

## 1.4. Objectives of the study

## 1.4.1. General Objective

The general objective of the study is to determine factors affecting real estate construction projects.

## 1.4.2. Specific Objectives

The specific objectives are listed below.

- To investigate the factors affecting the development of real estate construction projects   management.

- To assess the real estate construction operations in Addis Ababa city.

- To describe the progress and trend of real estate development in Addis Ababa.

H1: Organizational planning effort has a significant positive impact on project management success in real estate construction projects.

Organizational planning (planning of designs and constructions) has been found to have a significant impact on the probability of project management success though the impact is negative and opposite to what is hypothesized and expected. The estimated odds ratio indicated the probability of project management success declines as organizational planning efforts are increased. When the agreement level of organizational planning increase by 1 unit, the odds ratio of timely project completion increase by 0.19. It is known that when the odds ratio is lesser than 1, it implies that the probability of an event occurring, in this particular case timely project completion, decrease. This rejects the null hypothesis as the impact organizational planning have towards project success is negative.

H2: Project manager goal commitment has a significant positive impact on project management success in real estate construction projects.

Though project manager’s goal commitment does not significantly impact successful project completion in terms of time and allocated budget, it has an unexpected negative impact on project completion meeting planned quality level. The model estimation indicated an odds ratio increment by 0.28 when respondents’ levels of agreement about project manager goal commitment increase by 1 unit. Once again here is an odds ratio values lesser than 1 indicating a decrement on the probability of successful project completion in terms of planned quality level.

H3: Project team motivation and goal orientation has a significant positive impact on project management success in real estate construction projects.

Earlier in the analysis, respondents’ response indicated that project team members lack the motivation and goal oriented-ness. Yet, this success factor found to possess a significant positive impact on project completion meeting the planned quality level. The model test indicate a 1 unit increase in the level of agreement by respondents’ on project team members goal commitment and goal orientation leads to a 4.9 increase on the odds ratio of successful project completion in terms of quality.  The result leads in to a conclusion that the more project team members are motivated and goal oriented, the more will be the probability of the construction project meets planned quality requirements. This makes the null hypothesis acceptable which state project success is significantly and positively impacted by the project team members’ motivation and goal orientation.

H4: Project scope and work definition has a significant positive impact on project management success in real estate construction projects.

As the models tasted, the success factor project scope and work definition couldn’t found to have any kind of significant impact in any of the dependent variables. This implies that a change in the respondents’ agreement level in the project scope and work definition, any of the dependent variables (time, cost and quality) do not significantly impacted. These disprove the null hypothesis which states project scope and work definition positively and significantly impact project management success.

H5: Project managers’ capability and experience has a significant positive impact on project management success in real estate construction projects.

When asked to rank the critical success factors according to their potential in successful project completion, most of the respondents ranked project managers’ capability and experience as presented in table 4.2. While testing the models, a result that goes along with that finding have found. The odds ratio of the relationship between project managers’ competency and experience and successful project completion in terms of time is 4.3. Meaning, a 1 unit increase in the agreement level of respondents response increase the odds ratio of timely project completion by 4.3.This indicates the strong positive impact project managers’ competency and experience have over timely project completion that is project management success.  The fifth hypothesis is proven to be correct as it claims project managers’ competency and experience has a significant positive impact on project success which actually has.

H6: Safety precautions and applied procedures have a significant positive impact on project management success in real estate construction projects.

The student researcher started the investigation hypothesizing safety precautions and applied procedures of the real-estate developing companies have a significant positive impact on the success of project management success. As expected, the variable found to have a significant impact on the probability of the dependent variable occurring. When the level of agreement about the existence of proper safety precautions and applied procedures, the odds ratio of successful project completion in terms of cost increase by 2.7.  Since the increment in the odds ratio is higher than 1, the impact of safety precautions and applied procedures over project success in terms of cost is positive. This supports the null hypothesis the student researcher stared the investigation with.

H7: The availability of proper control systems has a significant positive impact on project management success in real estate construction projects.

Though it has ranked by respondents as the sixth important success criteria for project success, the presence of proper controlling systems found to have a significant positive impact over all the three dimensions of project success. For every 1 unit increment in the agreement level of the presence of proper control systems in the real estate developers, odds ratio of timely project completion increase by 3.3 and it increase by 2.98 and 19.28 respectively for successful project completion in terms of cost and quality. This makes control system the only variable that has a significant positive impact on all measures of project management success. The finding proves the null hypothesis which states the control system has a significant positive impact on project success.

## 1.5. Scope and Limitation of the Study

### 1.5.1. Scope of the study

This research deals with success in private real estate purchase contracts by focusing on residential real estate development firms working in Addis Ababa, Ethiopia. Real estate agents and developers who sell houses or apartments after construction is completed are not included in the study.

### 1.6. Significance of the Study

This project paper entitled as factors affecting the real estate construction project success is expected to provide important information to stake holders in the market including the investors or the real estate developers, the government agencies & regulatory bodies, the real estate construction or the real estate brokers, customers in the real estate construction; in different perspectives. For readers depending on the research objectives the outcomes of this research had believed to mainly benefit the construction industry and any other interested stakeholders.  Results from this study would help prioritize future research areas. Findings of the study would confirm whether the well-liked research topics are in fact most important to the construction industry and try to understand the needs of the industry, and increase the relevance of future research. It is important to have relevant information on project risks for real estate developers. Therefore, this study would a stepping stone by giving a broader insight on success and their impact on project objectives, mainly cost and schedule. It is believed this could help the companies move towards a better risk management practice.

## 1.7. Organization of the Study/Structure of the Study

This research had organized under five chapters

Chapter one deals with background of the study, research motivations, statement of the problem, research questions, objectives, significance, scope and limitations of the study and organization of the research.

Chapter two comprises literature review, and comprises the various related works mainly focusing and analyzing issues associated with construction related researches and needs of the industry.

Chapter three deals with the research methodology, research approach, research design, sampling techniques, data source and collection methods and data analysis .

Chapter Four covers results and discussion and last chapter covers the main conclusions and recommendations of the research

## CHAPTER TWO

## LITERATURE REVIEW

## 2.1. Introduction

The up to date definitions focus on the fact that a real estate refers to the land and fixtures together, as distinguished from real property, referring to ownership rights of the land itself. A contemporary definition of real estate is provided by investors: Real estate is a term that encompasses land along with anything permanently affixed to the land, such as buildings, specifically property that is stationary or fixed in location. Real estate includes entities such as residential homes, raw land, and a variety of forms of income property, including warehouses, office and apartment buildings, and condominiums.

Research in common phrasing refers to a search for knowledge. One can also define research as a scientific and systematic search for pertinent information on a specific topic. In fact, research is an art of scientific investigation. Some people consider research as a movement, a movement from the known to the unknown. It is actually a journey of discovery. We all possess the vital instinct of curiosity for, when the unknown confronts us, we wonder and our inquisitiveness makes us search and attain full and fuller understanding of the unknown. This inquisitiveness is the mother of all knowledge and the method, which man employs for obtaining the knowledge of whatever the unknown, can be termed as research (Kothari, 2004). Concise Oxford Dictionary (2001) provides a more extensive definition of research as ‘the systematic investigation into and study of materials and sources, in order to establish facts and reach new conclusions’. The emphasis lies on determining facts in order to reach new conclusions, that is, new knowledge. The issue of ‘facts’ is not as clear, philosophically speaking, as is commonly assumed (Richard and Anita, 2008).

## 2.2. Conceptual Literature

## 2.2.1. Project and Project Management

Real estate is often defined as a triangle of space, money and time. in this sense a particular usage is attributed to a defined space which generates an estimated cash flow over a specific period of time. Based on this understanding of real estate, the definition of development postulated by Graaskamp (2013) the creation and management of space time units in termed as real estate development is applicable. Development is an idea that comes to realization when consumer-tenants or owner occupants-acquire and use the bricks and mortar (space) put in place by the development team. Land, Labor, Capital, Management, and entrepreneurship are needed to transform an idea into reality. Value is created by providing usable space over time with associated services. Effective project management strategies & the construction industry is commercial domain of building and construction has attained significant prominence in the recent time. As such, this sector deals with huge amount of money and thus, stake in this line of business is much higher. Any construction project invariably comes with certain constraints. These constraints include an estimated costing and a fixed deadline. Stakeholder of a project has to ensure these predetermined factors do not get skipped at any cost. Along with these estimations, one has also to ensure superior quality of construction work to a project. However, at the implementation level it seems most challenging to maintain this cost estimation and the deadline.

Project is defined as ‘a one-time, complex and unique set of activities carried out in a project organization with time and budget constraints and they have a predefined project result to be implemented’(Gorog, 2013). The Project Management Institute (2010) defines a project as a temporary, definitive beginning and definitive end, endeavor undertaken to create a unique product or service. Projects can be considered as the achievement of a specific objective and involve the utilization of resources on a series of activities or tasks. A project is a group of tasks, performed in a definable time period, in order to meet a specific set of objectives. Projects are expressed with characters such as likelihood of being a one-time program, having a life cycle with a specific start and end date, budget and resources. Probably the simplest definition is found in the Project Management Body of Knowledge (PMBOK) guide of the Project Management Institute (PMI).

Projects are complex, one time processes- A project arises for a specific purpose or to meet a stated goal. They are complex because they typically require the co-ordinate inputs of numerous members of the organization, project members may be from different departments or other organizational unit or from one functional area. On the other hand, some projects such as new product introductions, work best with representatives from many functions, including marketing, engineering, production and design. Because a project is intended to fulfill a stated goal, it is temporary. It exists only until its goal has been met, and at that point, it is dissolved.

Projects are limited by budget, schedule and resources. Project work requires that members work with limited financial and human resources for a specified time period. They do not run indefinitely. Once the assignment is completed, the project team disbands. Until those points, all its activities are constrained by limitations on budget and personnel availability. Projects are “resource constrained” activities.

Projects are developed to resolve a clear goal or set goals. There is no such thing as a project team with an on-going, nonspecific purpose. Its goals, or deliverables, define the nature of the project and that is its team. Projects are designed to yield a tangible result, either as a new product or service. Whether the goal is to build a new bridge, implement a new account receivable system or win a presidential election, the goal must be specific and the project organized to achieve a stated aim.

Projects are customer focused: Whether the project is responding to the needs of an internal organizational unit (e.g. accounting) or intended to exploit a market opportunity external to the organization the underlying purpose of any project is to satisfy customer needs. In the past, this goal was sometimes overlooked. Projects were considered successful if they attained technical, budgetary or scheduling goals. More and more, however, companies have realized that the primary goal of a project is customer satisfaction. If that goal is neglected, a firm runs the risk of “doing the wrong things well” pursuing projects that may be done efficiently but ignore customer needs or fail commercially.

## 2.2.2. Project Management

In order to distinguish between the project and project management it is necessary to develop distinct definitions for the two terms. A project can be considered to be the achievement of a specific objective, which involves a series of activities and tasks which consume resources. It has to be completed within a set specification, having definite start and end dates. In contrast, project management can be defined as the process of controlling the achievement of the project objectives. Utilizing the existing organizational structures and resources, it seeks to manage the project by applying a collection of tools and techniques, without adversely disturbing the routine operation of the company (See, for example, Kerzner, 2003). The function of project management includes defining the requirement of work, establishing the extent of work, allocating the resources required, planning the execution of the work, monitoring the progress of the work and adjusting deviations from the plan. Initially these two definitions may appear to overlap. Both are heavily orientated to the achievement of the project. The important distinction lies in the emphasis of both definitions. The project is concerned with defining and selecting a task which will be of overall benefit to the company. The role of project manager has developed in accordance with the understanding of concept of project success (Görög 2002; 2013). Earlier, when projects were defined as unique tasks, project managers were supposed to focus on the process of the project, thus managing the implementation process considering the project results, and the time and cost constraints. As the understanding of the concept of a project widened, the role of the project manager also advanced. The management of stakeholders and the delivery of the beneficial change became part of his/her role. These days the most important roles are as follows: planning the projects, implementing the plan, managing stakeholders and delivering the beneficial change (see e.g. Fekete– Dobreff 2003; Project Management Association 2006. Thus project management can be considered as an application of knowledge, skills, tools, and techniques to project activities to meet the project requirements (Project Management Association 2006).

## 2.2.3. Success in Projects

Success is an interesting word and a word that is so general and wide in nature that it is difficult to define and obtain mutual agreement when asked from different individual. Judgev and Muller (2012) in their article mentioned that in order to define what success means in the project context is like gaining consensus from a group of people on the definition of “good art.” There is wide divergence of opinions in this field; the only agreement seems to be the disagreement on what constitutes ‘project successes.

Based on a current study conducted by Crawford, Pollack and England (2006)to uncover the journal emphases over the last 10 years in the field of project management, it is found that the study of project evaluation and improvement has gained increase significance. This implies that more studies have been directed to the area of project management and project success. Generally, the views on project success have evolved over the years from simple definitions that were limited to the implementation phase of the project life cycle to definitions that reflect an appreciation of success over the entire project and product life cycle (Judgev& Muller, 2007).De Wit (2002) and other writers distinguish between project success (measured against the overall objectives of the project) and project management success (measured against the widespread and traditional measures of performance against cost, time and quality).

## 2.2.4. Project Success and Project Management Success

Apparently determining whether a project is a success or a failure is far more complex. There can be ambiguity in determining and measuring the success or failure of a project. Delays in completion of projects are common but they could still be considered successful. De Wit (2002) was among the first to recognize that there is a difference between project success and project management success and that a distraction is needed between them. The importance of this is that successful project management would contribute to the achievement of a project but project management will not stop a project deliverable from failing to succeed. Baccarini (2011) also points out that project management literature often confusingly intertwine two separate dimensions of project success. Product success and project management success. Project management success focuses on fulfilling the cost, time and quality criteria. On the other hand, Project success deals with the effects of the project’s final deliverable, namely project goals, project purpose and satisfaction of stakeholders. There is also a scenario where a project that is perceived as successful by the project manager and team members might be perceived as a failure by the client or market.

Project success can mean different things to different people because of varying perceptions and point of view. This can lead to a disagreement about the success of a project (Liu & Walker, 2002). The perception of the overall project is likely to be different between users and stakeholders and thus also is the project success. Shenhar et al. (2002) suggest three reasons for this difference in perception. First of all this is due to the universalistic approach used in most project management studies that all projects are assumed to be similar, secondly the subjective nature of the success or weakly defined success measures and at last the limited number of managerial variables examined by previous research. According to Munns&Bjeirmi (2007) this difference in perception will continue to exist if a distinction between project success and project management success is not established.

Project management success is oriented towards planning and control in the context of the short-term life of the project development and delivery but project success tends to be long term in nature and stretches with the objective or product, the project delivers. The project management success focuses on the values of the Iron Triangle and also on the way in which a project is managed, that is the “quality of the management process”. This forms one part of project success defined to preparation and execution phases in the project life cycle. The other part of project success relates to the effects of the project’s deliverable or service and is referred to as “product success” (Baccarini, 2002). Therefore a project can be viewed as being successful despite the Iron Triangle criteria not being met. Munns&Bjerimi (2007) agree on this and illustrate this distinction in their paper as follows.

The project management team is focused on the task of successfully reaching the end of project implementation phase, at which point the project team will terminate its involvement whereas the client is interested in all the phases. The scope of the project management success spans phases Conception to Implementation where the scope of the project success spans all the phases (Munns&Bjerimi 2007). Distinction between project management success and project success is not just a debate about terminology. Determining how success is to be defined for a project is a necessary precursor to the establishment of appropriate methods for managing the project life cycle and for the selection of suitable measurement techniques, Bryde (2005).Finally, defining success is also a key step in understanding the important “success factors”, that is, the inputs to the project management system that have an influence on the outcome (Cooke-Davies, 2002). He also defines project management success and project success as follows.

Project management success, being measured against the traditional gauges of

Performance (i.e., time, cost and quality/performance).

Project success, being measured against the overall objectives of the project.

According to PMBOK the project life cycle is made up of three main phases; Initial/Implementation, Intermediate/Execution and Final/Handover. The literature mainly focused on the implementation or execution phases where the attention will on the Iron Triangle (Lim & Mohamed, 2004). This will be understandable as the implementation phase was typically the longest and consumed the most resources (PMI, 2000).

## 2.2.5. Project Management in Construction Projects

According to PMI (2004) – A guide to the Project Management Body of Knowledge (PMBOK Guide), the definition of a project is: A temporary endeavor undertaken to create a unique product, service or result. Though there are process based activities in the construction industry, for instance regarding manufacturing of building materials, from a contractor or a property developer perspective most of the activities in the construction industry are project based. Also when considering different initiatives to industrialize the construction process the recent years it is fair to say that a major part of the money spent in the construction sector is invested in project activities.

Considering this, it is crucial for the participants in the construction industry to be experts in management, monitoring and control of projects, thus find the formula for successful projects. Major parts of a recipe for successful projects ought to be generic for all kind of projects, but it is reasonable to believe that some other features are more specific to the construction industry, to certain types of projects, to the project size and to other characteristics of a project. Jaafari (2001), argue complexity is one distinctive characteristic of many projects to manage to enable successful projects. The complexity in construction projects is mentioned by Tah and Carr (2000), and Chan and Scott and Chan (2004). Complexity in terms of turbulent environment in large scale engineering projects is emphasized by Floricel and Miller (2007).

## 2.2.6. Real Estate and Real Estate development in Ethiopia

Modern definitions focus on the fact that a real estate refers to the land and fixtures to gather, as distinguished from real property, referring to ownership rights of the land itself. A contemporary definition of real estate is provided by investors: Real estate is a term that encompasses land along with anything permanently affixed to the land, such as buildings, specifically property that is stationary or fixed in location.Thomsett (2013), defined real estate as land and all permanent improvements on it, was including building. According to Geissler (2008) the term is artificially delineated space referenced to a fixed point on the surface of the earth with a fourth dimension of time. It is built to house an economic activity that is subject to cultural preferences and restricted by the public infrastructure. Real estate includes entities such as residential homes, raw land, and a variety of forms of income property, including warehouses, office and apartment buildings, and condominiums. Considering the similarity, all the authors define real estate as land that is identifiable and tangible. They further included all fixtures, improvements and buildings that are permanent to the land are to be considered as real estate.

## 2.3. Theoretical Literature

## 2.3.1 Project Success Factors

Rubin &Selling (2004) first introduce the concept of project success factors in 1976.Rockart (2007) first uses the terminology critical success factors (CSFs) and defines it as those few key factors absolutely necessary to reach goals. McCabe (2001) highlights CSFs are vital for managers to improve their organization in the sense that it would indicate the progress is being made in particular areas. Success factors can be perceived as main variables that contribute to projects’ success (Dvir, 2003), as levers that can be operated by project managers to increase chances of obtaining the desired outcomes (Westerveld, 2003).

A combination of factors determine the success or failure of a project and influencing these factors at the right time makes success more probable (Savolainen, 2012).In earlier project management literatures, the main focus was on identifying generic factors that contribute to projects’ success. Within the last years, authors emphasized on the existence of different success factors depending on project type. The struggle to identify the critical success factors is an ongoing topic, approached by many researchers especially due to the pressure of implementing successful projects in a dynamic global market and ever changing business world (Crisan, Borza, 2014), where continuous innovation is a must in order to achieve competitive advantage (Salanta, Popa, 2014).

According to this study, approaches of success factors evolved from focusing on the operation level of a project in1970s to embracing a stakeholder focused approached after 2000s (Davis, 2014). As a result of the numerous studies that approached the topic of project success, several lists of success factors exist. Pinto and Slevin’s paper from 2005 represents a reference point by establishing a list of ten success factors, recognized by other authors as accurate (Turner, Müller, 2010): project mission, top management support, schedule and plans, client consultation, personnel, technical tasks, client acceptance, monitoring and feedback, communication, troubleshooting(Pinto, Slevin, 2005). Davis (2014) adopted in her paper a set of nine themes in order to describe success factors of projects: cooperation and communication, timing, identifying/ agreeing objectives, stakeholder.

## 2.3.2. Success Factors for Construction Projects

A building project is completed through a combination of many events and interactions, planned or unplanned, over the life of a facility, with changing participants and processes in a constantly changing environment. Certain factors are more critical to a project’s success than others. These factors are called critical project success factors. The term Critical Success Factors in the context of the management of projects was first used by Rockart in 2010 and is defined as those factors predicting success on projects. Success is defined by Ashley et, al. (2011) as "results much better than expected or normally observed in terms of cost, schedule, quality, safety and participant satisfaction”.

The Factors affect real estate construction projects has attracted the interest of many researchers and many studies have been conducted, with the aim of providing contract parties with valuable insight into how to consistently achieve superior results for their projects. Although construction projects are by their nature repetitive activities, each one has its own characteristics and circumstances. The following section investigates studies that identify critical success factors leading to successful completion of projects on time, within a planned budget, in the safest manner, and with the highest quality. These studies differ in the way they approach the problem and in the way the researchers evaluate success factors. Sanvido et al (2008) defined the success of construction projects as the degree to which project goals and expectations are met.

These goals and expectations may include technical, financial, educational, social, and professional aspects. Sanvido et al (2008) determined the existence of a set of critical project success factors that play an important role in the planning, design, and construction of successful building projects. Parfitt and Sanvido (2008) used those success factors to develop a checklist that could be used by building professionals to predict the success of a project. An example of this checklist is:

Facility team:

- Have adequate steps been taken to assemble and build a facility team with the common goals and chemistry appropriate for this project?

- Is a sense of respect for the role and services of each team member evident?

- Is there an open and honest communication flow?

- Do all team members share a compatible philosophy with the owner of this project?

Chua et al (2003) identified critical success for construction projects based on the accumulated knowledge and judgment of experts in the industry. Sixty-seven success related factors were considered and grouped under four main project aspects: project characteristic, contractual arrangements, project participants, and interactive process. Cooper et al (2001) reviewed literature identifying success factors on generic projects and construction projects. The research identified several success factors for the construction process such as clarity/ definition of project objective, scope of project, project manager, project team commitment, capability, cooperation, planning, control, appropriate size of work package, communication and information management, top management support, environment, and health and safety. Ashley et al. (2011) offer insight into factors that influence construction project effectiveness through interviews with construction project personnel and a literature review of relevant studies. Researchers started with a list of approximately 2000 success factors from previous studies and construction management personnel interviews, which they reduced to 46 success factors grouped into 5 major categories, as follows:

i. Management, organization, and communication

ii. Scope and planning

iii. Controls

iv. Environmental, economic, political, and social

v. Technical

Ashley (2011) made the success factors for each to objectively be rated by several construction project personnel to identify which of these factors had the most significant influence on construction project success. Each factor was subjectively rated using a range from no influence at all to major influence. From these ratings the top 15 factors were grouped by their respective categories. From this list, 11 factors were chosen for further analysis. These are planning effort, project manager goal commitment, project team motivation and goal orientation, scope and work definition, project manager capability and experience, safety, control systems, design interface management, risk identification and management, technical uncertainty, and legal political environment. After extending the study on eight construction companies, the researcher could find the first seven of the eleven success factor are the most critical for construction projects’ success. A final analysis of the correlation between particular factors and their influence on the success of a construction project was conducted. Results showed that differences in construction and design planning efforts best explained the delineation between average and outstanding projects. Interpretation of the results further showed that the following factors are most significant in determining project success:

1. Construction and design planning effort

2. Scope and work definition

3. Project manager goal commitment

4. Project team motivation goal orientation

5. Project manager capabilities and experience

6. Safety

7. Control systems

Most of the critical success factors identified are human-related factors. This is supported by Nguyen et al (2004) on the study on project success factors in large construction projects in Vietnam. Among 20 success factors researched, 5 critical success factors were identified.

These were:

1. Competent project manager

2. Adequate funding until project completion

3. Multidisciplinary/competent project team

4. Commitment to project

5. Availability of resources.

## 2.3.3. Project Success Criteria

Success criteria are defined by Muller and Turner (2007) as variables that measure project success. Relevant success criteria have to be identified and then, success factors should be determined in order to increase the chances of project success (Müller, Turner, 2007). Many different approaches of measuring project success can be used. One of the most traditional ones is the iron triangle approach. It affirms that, three main aspects that must be managed together characterize projects: scope, cost and time. PMI (2013. p. 105) defines the scope as “the work performed to deliver a product, service, or result with the specified features and functions”. Approaches cost management as: “the cost of resources needed to complete project activities.

The effect of project decisions on the subsequent recurring cost of using, maintaining, and supporting the product, service, or result of the project” PMI (2013. p. 195), and finally time management as “the processes required to manage the timely completion of the project” PMI (2013, 141). After projects are planned, while they are being developed through time, these three concepts may be monitored. They can show the manager and the project’s team the level of adherence of the project to its iron triangle. This traditional approach is mentioned by Carvalho&Rabechini (2011), and PMI (2013). Kerzner (2006) also mentioned it, but with an addition: client’s expectation attendance. Kerzner highlight his addition mentioning that it makes sense to any kind of client, being it internal or external. Lim & Mohammad (2000) disperse success criteria into micro viewpoint completion (e.g. time, cost, quality, performance and safety) and macro viewpoint completion (e.g. time, satisfaction, utility, and operation).

In the same vein, Chan & Chan (2004) and Crawford & Pollack (2004) group construction project success criteria into objective measures (e.g. time, cost, safety and environment) and subjective measures (e.g. quality, functionality and satisfaction of different project participants). Furthermore, Blindenbach-Driessen (2006) suggests a model that consists of project success (e.g. adherence to quality target, schedule, budget, and captured knowledge) and market success (e.g. profitability, revenue, market share, reputation competitive advantage and customer satisfaction). These researches ponder quantitative measures and qualitative measures. Since standard framework has yet to be documented, two groups of protagonists consequently exist. The first group has been prone to qualitative measurement (Munns&Bjeirmi, 2007) because of the admiration to crisp value concept. Contrarily, the other group fancies quantitative measure.

The debate seems no end simply because researches into success criteria tends to make assumption at first place, ceteris paribus, where the outcome only affected by criteria perceived to be prominent. Given the widely accepted ambiguous, assessing success criteria based on project stages has emerged. Assessing project success is made on the altar of delivery stage and post-delivery stage (Atkinson, 2000). The delivery stage is adherence to cost, time, quality, and efficiency. Meanwhile, there are benefits to stakeholders, criteria from project manager, top management, resultant system, impact on customer and business success found in post-delivery stage. In the same vein, the project lifecycle of international development project are divided into five stages namely conceptualizing, planning, implementing, closing, and overall project success (Do &Tun, 2008). The authors further assign different success criteria to the project lifecycle stages. Chan, Scott & Lam (2004) further divide the success criteria into objective and subjective measure under project lifecycles namely pre-construction stage, construction stage, and post construction stage respectively. Similar to this avenue, Shenhar&Renier, (2002) focus on success category namely internal project objectives, benefit to customer, direct contribution and future opportunity which resemble pre-completion, short term, medium term and long term respectively. The authors are pioneer in etymologizing project success criteria.

The basic assumption behind the scene is success varies with time. The research seems to be the robust as it takes into consideration the project success and project management success components as well. Additionally, Shenhar, Dvir, Levy &Maltz (2003) claim that project success represents strategic management concept as all efforts must be in accordance with the strategic long-term goals of the organization. However, concerns are raised over the project classification across industry. Given the character of success criteria is inherently multidimensional, Shenhar et al. (2002) suggest four dimensions of project success criteria namely project efficiency, impact on customer, business success, and preparing for the future. At the meantime, Sadeh, Dvir&Shenhar (2000) divide success dimension into meeting design goals, benefits to the end user, benefits to the developing organization, and benefit to the defense and national infrastructure. In addition, Diallo&Thuillier (2004) posit three empirical macro dimensions namely management success, project itself and profile of international development project.

These researches, however, tend to create simplicity out of the knowledge itself. This is the prevailing assumption concerning the validation process of exhaustive data. Moreover, the practically impact remains a doubt. It seems paradoxical, but that is the imperfection of the knowledge unless a robust validation method comes in sight. Lastly, prevailing trend is noted in studying the project success criteria based on individually stakeholder’s perspective. As the project success could be assessed by different stakeholders namely clients, managers, contractors, workers, and end-user, the relevant criteria, therefore, must represent different views (Stuckenbruck, 2008). Bryde& Robinson (2005) show that client puts more emphasis on the need of other stakeholders whilst contractor puts more emphasis on project cost and duration. Being the main person in any project, the perspective of client has drawn more attention compared to other stakeholders. For example, Frodell (2008) depicts an empirical result that shows success measures like keeping project on time, within budget, maintenance costs and project goals as well as ensuring profitability are important criteria.

At the meantime, Ellatar (2009) suggests a trilogy perspective framework on construction project. As suggested, client’s perspective (e.g. time, cost, functionality, end result, quality, aesthetic value, profitability, marketability, less aggravation), designer’s perspective (e.g. satisfied client, quality, cost and profit, professional related issues like staff fulfillment, marketable product, less construction problem, no liability, socially accepted, client pays and well defined scope of work) and contractor’s perspective (e.g. time, cost, quality, free from claims, clearly defined expectation from all parties, client satisfaction, as well as less surprises during project) are prominent to increase the likelihood of project success.

Generally, the perspective research has several limitations: first, it concerns about individually stakeholder’s viewpoint and overlooks the interrelationship among stakeholders. Second, no universal accepted methods for measuring subjective measures and it only exacerbates the problem by putting objective and subjective measures together. This topic has described by for instance Chan and Chan (2004), and they state that it is essential to define what project success means, or it will not be feasible to discuss performance measurement. Further, they conclude that both qualitative and quantitative KPIs are desirable. A set of methods on how to measure the performance is presented by Salminen (2005), and that the criteria cost, schedule deviation, quality and safety form a coherent description of construction project success. Often failure in one aspect indicates failure in more of the aspects, though this dependency is not necessary. Construction industry is a case in point given the trilogy will culminate in profit related concerns.

However, questions and concerns are raised about the insufficiency in this trilogy per se as success criteria. Baccarini, (2011) suggests product success, which consists of owner’s strategy, user satisfaction, profitability, and market share together with project management success, which resembles the time, cost, quality, project management process and stakeholders’ satisfaction as components that form project success concept. Likewise the seven critical success factors, Ashley et al. (2011) also suggested six criteria by which success of construction projects should be measured against. The criteria were comparatively rated for average and outstanding projects, revealing that the most important criteria for gauging the success of a construction project were:

1. Budget

2. Schedule

3. Client satisfaction

4. Functionality

5. Project manager / team satisfaction

6. Contractor satisfaction

Furthermore, the three researchers (Ashley, Nguyen &Sanvido) held similar viewpoints; for example, all agreed that the financial reality of doing business and achieving an appropriate schedule was a means of measuring the success of a project. On the other hand, there were some unique criteria. For example, the designer was looking for a project that would increase the level of professional satisfaction among their employees.

## 2.4. Empirical Review

Different researchers in different countries investigated project success factors and success criteria from different industries perspectives. In this sub section, the methodology used and findings identified on studies conducted on project success, success factors and success criteria are reviewed. Alan Murphy and Ann Ledwith (2007) investigated which critical success factors contribute for project success on high technology small and micro enterprises.

The authors selected six critical factors what they have considered to have potentially highly influential critical success factors and conducted a survey on 200 high technology SMEs. Clear goals/objectives, senior management support, resource allocation, planning, monitoring and control, Client consultation and risk management are the selected critical success factors. Their finding indicates that the existence of a project manager and the use of project planning significantly contribute to project success. Control for projects resides primarily with owner managers and achieving quality standards is a significant success criterion. Additionally, having clear goals/objectives and top management support are identified as the most important success factors in the firms surveyed. Lonna, Emil and Razvan (2012) on their quest investigated the main factors influencing project success through conducting a quantitative research method.

They adopted Pinto and Slevin’s critical success factors and tried to identify the top five project success influencing factors. The authors confirmed all the critical factors are important for project success yet they argue the top five influencing factors are clearly defined goal and directions, competent project team members, clearly defined roles and responsibilities, communication and consultation with stakeholders and compliance with the planned budget, time frame and performance criteria. Alias, Zawawi, Yusof, and Aris (2014) have conducted a study to identify the relationship between critical success factors of project and project performance.

The authors building their theoretical framework on five critical success factors as variables and investigated their influence on project performance using cost, time, quality and client satisfaction as performance measures. Project management action, project procedures, human factors, external issues and project related factors are the success criteria used as variables in the study. At the completion of the study, the authors proved there is a positive relationship between project performance and all the five critical success factors. Chan WaiKuen (2007) developed conceptual framework and tested it in Malaysia manufacturing sector. Chan’s focus was identifying success measures of projects and contributing factors for manufacturing related projects. Chan adopted Pinto’s critical success factors and the traditional time, cost and quality measure of project success in his study and investigated the relationship existed between the two.

Based on his finding, Chan argue that all the critical success factors identified by Pinto and Slevin to be influential factors for project success in Malaysia manufacturing industry. The studies conducted by Ashley et al. (2011), Nguyen et al (2004), Sanvido et al (2007), Chua et al (2003), Gudienė, Banaitis, Banaitienė, and Lopes (2013) and Cooper et al (2001) are one step closer to the study conducted by the student researcher from the above summarized studies. All this studies are conducted on critical success factors for construction projects. Ashley (2011) started his investigating with 2000 success factors identified by prior researchers. By the interviews he conducted with construction management personals, he narrowed down the success factors to 46. With further investigation, the construction project management personnel rated 15 of the success factors are identified to have greater influence on project success compared to the others. Continuing his investigation, Ashley ultimately found that seven of the factors are critical for construction projects success.

The critical success factors identified by Ashley are construction and design planning effort, scope and work definition, project manager goal commitment, project manager capabilities and experience, safety, and control systems. Nguyen et al (2004) studied project success factors in large construction projects in Vietnam. Nguyen started his investigation with 20 success factors and identified five of critical success factors by the completion of the study. Among the 20 success factors he started his study with, competent project manager, adequate funding until project completion, multidisciplinary/competent project team, commitment to project, and availability of resources are found to be the critical ones. Nguyen’s study also grouped the success factors into one of four components which are comfort, competence, commitment and communication. His findings found to be supportive to that of Ashley’s study. Sanvido et al (2003) identified the success criteria list for each of the contract parties: owner, designer, and contractor. Some of the owner success criteria included being on schedule, being on budget, and return on investment. Examples of the designer success criteria were client satisfaction, quality architectural product, well-defined scope, and social acceptability.

Finally, contractors’ criteria for measuring success included meeting the schedule, profit, being under budget (savings obtained for owner and/or contractor), safety, and client satisfaction. Chua et al (2003) identified critical success for construction projects based on the accumulated knowledge and judgment of 20 experts in the industry. Sixty-seven success related factors were considered and grouped under four main project aspects: project characteristic, contractual arrangements, project participants, and interactive process. The results of the study revealed that experts agree that there are different sets of construction success factors for different objectives. They determined that the probability of project success can be increased if the inherent characteristics of the project are thoroughly understood, appropriate contractual arrangements are adopted, a competent management team is assigned, and a sound monitoring and control system is established. Gudienė, Banaitis, Banaitienė, and Lopes (2013) used multiple criteria approach taking in to consideration seven groups of factors from different dimensions.

A conceptual model that includes the grouped critical success factors affecting project success was developed. According to the authors’ findings, the seven major groups of factors, namely external factors, institutional factors, projects related factors, project management/team members related factors, project manager related factors, client related factors and contractor related factors are proved to influence construction project success in Lithuania. However, as far as the venture of the researcher is concerned, no published study is available that devotes its attention on investigating what factors influence project success or how projects success is to be measured in Ethiopian or Ethiopian companies perspective.

Independent variables                                                                 Dependent variables

project manager goal commitment

Organizational Planning effort

Project team motivation and goal orientation

Real estate project success

- Cost

- Time

- Quality

Project Scope and work Definition

project manager technical capability and experience

Safety Precautions and Applied Procedures

Control Systems

Figure 2.1: conceptual framework of the study

Adopted from: Ashley &Jaselskis’s (2011) Determinants of

Project management success for construction projects.

# CHAPTER THREE

# RESEARCH METHODOLOGY

## 3. INTRODUCTION

In this part of the study the different methods, instruments, and techniques those are employed in the accomplishment of this study are explained. This includes a detail description and justification of the methodological choices made to conduct this study, presents the research design, sampling design and strategy, data collection methods including how they are analyzed, interpreted, and discussed.

## 3.1. Research Design and Approach

The study intends to assess the impacts of project success factors over project success. Cause and effect (causal) relationship between variables would be assessed throughout the study. This makes it appropriate for the study to implement explanatory research design. Depending on the type of data that are used in the research, two general research approaches are identified, qualitative or quantitative. In this study both types of data those can and cannot be quantified are used. The quantifiable data would be gathered by the closed ended questions of the questionnaire which would be designed to keep the respondents in scope. There would be also open ended questions, providing unquantifiable data, which would be designed to provide respondents with the freedom of expressing what they believe important for the study. This leads for the study to use a mixed research approach which both qualitative and quantitative research methods are applied.

## 3.2. Study Area and Period

The study is conducted on real estate development companies located in Addis Ababa city focusing on investigating how construction projects are managed, how successful projects are and how the success level is influenced by the project management success factors.

## 3.3. Types and Sources of Data

For the completion of this study, both primary and secondary types of data would be used. The primary data for this research would be acquired from sample respondent project managers who would be selected from the real estate companies, secondary data is collected from books, articles, web sites, and reports.

## 3.4. Sample Design

In this part, the target population and sample size of the study are discussed including the procedures and techniques used to identify them.

## 3.4.1. Population

Currently, a total of one hundred (125) real estate companies are operating in Ethiopia. However, as the study is conducted on the real estate developers located in Addis Ababa city, it focuses only on 91 of the total 125. Project managers of 91 real estate developers are considered to be the population of the study.

## 3.4.2. Target population

A list of all sampling units those are eligible and available for selections at the stage of sampling process would be identified and sampling frames would be prepared. From the total 91 real estate companies operating in Addis Ababa city, 45 are decided not to be incorporated in the sample frame as they are yet to complete a single real-estate development project. According to the recommendation of Hosmer and Lemeshow (2000) and Long (2003), the minimum sample size should not be less than 10 per independent variable in case of regression analysis and it should not be less than 100 in aggregate. The theoretical framework of the study, which is discussed in the preceding chapter, suggests 7 independent variables.

## 3.5. Data Collection Methods

In this study both primary and secondary data would be used. Secondary data is collected from books, articles, web sites, and reports. These data are expected to help in introducing the concept of project management and project success; clarifying the theoretical framework designed for the study; and to imply how much is known about the study area and the research gap existed. Questionnaires (both open and closed ended) are the tools implemented by the student researcher to collect all the necessary primary data. The questionnaire for this study would be developed based on Ashley &Jaselskis’s (2011) seven critical success factors and the ‘iron triangle’ project success measure. The items in the questionnaire would be validated and tested for reliability and used after it is assured to meet the requirements in both cases; Reliability and Validity Tests. Validity is the extent to which the items or questions incorporated in the questionnaire measures what it is supposed to measure and performs as it is designed to perform (Hair et al., 2003). The item in this study questionnaire would argued to be valid by the student researcher as they are designed according to Ashley’s (2011) seven critical success factors for construction projects. Reliability is consistency and reliability test measures whether or not the instrument consistently measure what it is intended to measure. According to George and Mallery (2003), a Cronbach’s alpha value higher than 0.7 is considered to be reliable. The reliability gets stronger as it goes higher than 0.7 and poorer as it gets lower than 0.7.

## 3.6. Data Analysis Techniques

As the study type is explanatory, the type of technique preferred for the data analysis is inferential statistics. The relationship between the dependent variable of project success and the independent variables of success factors would be measured with the application of Ordinary Least Square (OLS) regression tests. The type and extent of the relationship between the critical success factors in any one of the success criteria represents the relationship between success criteria and project management success. Statistical Package for Social Science (SPSS) is used to analyze the descriptive and inferential statistics of the study.

The procedure are summarized below

Study are........ Addis Ababa

Study design.....................    - Explanatory study from document & desk study

- Observational studies for quality assessment

Study Participants..............     - Real estate developers

- Financer

- Governments

- End users (Customers)

Method of data collection............     - Observation

-  Publication, research papers

-  Interview

Method of data analysis...........     - Desk study

- Identify the parameters and allocating weight the parameters

-  Evaluating based on the parameters

## 3.7. Empirical Models Specification

Once the relationship between a set of variables is hypothesized based on theories, the highly recommended approach to test the hypothesis is through econometric modeling and testing (creel, 2006). To achieve the proposed objectives similar fashion would be suggested in this study. Logistic regression analysis is used to estimate the potential determinates of the limited dependent variable that is “project success”. Based on the above theoretical framework, three econometric models are constructed. In the models, it is tried to statistically measure the impact of the independent variables on the probability of project success. The equations of the models use the “Project Success” which is explained by Time (T), Cost (C) and Quality (Q) as dependent variable. They also contain the vector of explanatory/independent variables.

The equations of the models are given as;

P(T) = 𝛼0+ 𝛼1OP + 𝛼2PMGC + 𝛼3PTMGO + 𝛼4PSWD + 𝛼5PTMTC +𝛼6SPAP + 𝛼7 CS +𝜀(1) P(C) = 𝜷𝟎+ 𝜷𝟏OP + 𝜷𝟐PMGC + 𝜷𝟑PTMGO + 𝜷𝟒PSWD + 𝜷𝟓PTMTC +𝜷𝟔SPAP + 𝜷𝟕+𝜀(2) P(Q) = 𝝁𝟎+ 𝝁𝟏OP + 𝝁𝟐PMGC + 𝝁𝟑PTMGO + 𝝁𝟒PSWD + 𝝁𝟓PTMTC +𝝁𝟔SPAP + 𝝁𝟕 CS (3) Where: OP is Organizational Planning; PMGC is Project Manager Goal Commitment; PTMGO is Project Team Motivation and Goal Orientation; PSWD is Project Scope and Work Definition; PMTC is Project Manager Technical Capabilities; SPAP is Safety Precautions and Applied Procedures; CS is Control Systems; 𝛼𝑖 is slope coefficient and ε is error term. To estimate the above model, Ordinary Least Square (OLS) is used, which enabled to predict a dependent variable, which assumes a limited value from a set of variables that may be continuous, discrete, and dichotomous or a mix of any of these (Kothari, 2004).

The Ordinary Least Square (OLS)is used to estimate the variance of dependent variable explained by the independent and to rank the relative importance of independent variables (Mender, 2002). The Ordinary Least Square OLS)applies maximum likelihood estimation to estimate the probability of certain event occurring, after transforming dependent variable in to a logit variable that is the natural log of the odd of dependent occurring or not. Since the model contains dependent variables which possibly assume a binary outcome of “0” or “1”, bivariate The Ordinary Least Square OLS) is used to estimate the marginal effect of all independent variables on project completion at the planned time, cost and quality (project success).

CHAPTER FOUR

## DATA ANALYSESAND INTERPRETATION

This chapter explains and present the results of findings based on the analysis done on the data collected. The result of the survey was discussed by triangulating the different source results: questionnaire results, interview and document review results .the discussion attempts to accomplish the objectives of the study and answer the research questions. A total of 91 questionnaires which dealt with real estate construction project managers who have at least completed one project. However 81questionnaires were collected and usable responses (95.04% response rate), interview and relevant documents have been also reviewed. The questionnaire contains variables which include the presence of the seven construction project success factors in the real estate sector and their impact on the success or failures of the construction are discussed thoroughly. All items in the questionnaire are arranged in a form of census survey method to capture the feelings of respondents in scale ranging from 1 to 5.All the data has been analyzed in SPSS so that the accuracy of the information is maintained.

In addition to this a self-administered close ended questionnaire is included to support the researcher to discuss the results more clearly and an interview is conducted among management members. The content of the interviews were manipulated in a way that it would prove or disprove the feeling expressed by the participants who responded the questionnaire .All the interview question were structured so that it match the contents of the items enlisted in the questionnaire .

## 4.1 General Information about Respondents

The information of respondents generated to address the stated research objectives is solicited from respondents with diverse demographic characteristics. The first part of the questionnaire consists of the demographic information of the participants. This part of the questionnaire requested a limited amount of information related to personal and professional characteristics of respondents. Accordingly, the demographic variables about the respondents were summarized and described in different figures and tables. These variables include: sex, educational qualification, work experience and job position.

Table 4.1. Demographic profile of respondents

| Variables | Frequency | Percent |
| --- | --- | --- |
| Sex |  |  |
| Female | 29 | 35.80% |
| Male | 52 | 64.20% |
| Total | 81 | 100% |
| Educational qualification |  |  |
| MA/MSC | 7 | 8.64% |
| BA/BSC | 66 | 81.48% |
| College Diploma | 5 | 6.17% |
| Others | 3 | 3.70% |
| Total | 81 | 100% |
| Work experience |  |  |
| Less than 5 Years | 15 | 18.52% |
| 5-10 | 35 | 43.21% |
| 10-15 | 19 | 23.46% |
| Above 15 Years | 12 | 14.81% |
| Total | 81 | 100% |
| Job position |  |  |
| Top Management | 13 | 16.05% |
| Middle Management | 32 | 39.51% |
| Project manager | 19 | 23.46% |
| Others | 17 | 20.99% |
| Totals | 81 | 100% |

Source survey data

Educational accomplishment was also one of the respondents profile incorporated in the study which 7(8.64%) of the respondent managers are found to be MA/MSC holders and 66 (81.48%) of the respondent project managers are found to be first degree holders. The rest 5 (6.17%) respondents are diploma holders, and also 3 (3.70%) are found to be the others. In terms of respondents’ experience, most (50 or 61.73%) have served as project manager between the years Less than 10 years. 19 (23.46%) of the respondents have a project management experience between 10 to 20 years while only 12 (14.81%) of the respondents are experienced project management for more than fifteen years.

## 4.2. General Profile of Sampled Respondents

Table 4.2.General Profile of Sampled Respondents

| Company Name | Est. Year | Type of Real Estate Development | Head office location (Sub city) | Site(s) |
| --- | --- | --- | --- | --- |
| Akakas Real estate PLC | 2006 | Residential Properties | Kirkos | Around Ayat |
| Ayat S.c | 1997 | Residential Properties | Ayat area | Ayat |
| CCD PLC | 2003 | Residential Properties | Bole | Legetafo |
| Enyi Real estate PLC | 2005 | Residential Properties | Arada | Jimma Rode & Bole bulbula |
| Gift Real estate | 2004 | Residential Properties | Kirkos | Yeka |
| Kara Kore | 2002 | Residential Properties | Bole | Kara Kore slopes in the Ayer Tena Distric |
| Sunshine | 2001 | Residential Properties | Kirkos | CMC, Gerji, Legetafo, & Bole-beshale |
| Zenebe Ferew | 2005 | Residential Properties | Nifas-Silk | Kara kore |
| Tsehaye Real estate PLC | 2011 | Residential Properties | Yeka | CMC |

## 4.3. Critical Success Factors Ranking

The question would presented for the respondents to indicate and prioritize which factors they consider to be important for successful completion of real estate construction projects among the seven potential success factors. The result indicated that all the presented factors are success factors for real estate development construction projects where some are even critical.

Table 4.2. Critical success factors rank

| No | Item | % |  | Count | Rank |  |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Project manager’s capabilities and experience | 30.86% |  | 25 | 1 |  |
| 2 | organizational planning (Construction and design planning effort) | 22.22% |  | 18 | 2 |  |
| 3 | project’s scope and work definition | 13.05% |  | 13 | 3 |  |
| 4 | Project manager goal commitment | 12.35% |  | 10 | 4 |  |
| 5 | Project team’s motivation and goal orientation | 8.64% |  | 7 | 5 |  |
| 6 | control systems | 6.17% |  | 5 | 6 |  |
| 7 | Safety precautions and applied procedures | 3.70% |  | 3 | 7 |  |
| Total |  |  | 100% | 81 |  |  |

Source survey data

## 4.4. Critical Success Factors

a questions which are believed to evaluate the presence of critical success factors in the real estate development construction projects were presented. The data collected for all the seven variables are analyzed separately at first and finally analyzed jointly to implicate which factors are presented and which are not in the selected real estate companies.

1. Organizational Planning

Table 4.3. Organizational Planning

|  | Items | Median |  | Std. Deviation |
| --- | --- | --- | --- | --- |
| OP 1 | Adequate consideration and attention is given in designing buildings | 3 |  | 1.147 |
| OP 2 | Project schedule and construction completion time are well planned | 4 |  | 1.214 |
| OP 3 | There is a proper estimation of the cost that will be needed to complete the construction | 3 |  | 1.113 |
| OP 4 | Constructions are thoroughly planned in advance before they are started | 4 |  | 1.015 |
| OP 5 | Resources needed to carry out construction projects are well recognized in advance |  | 4 | 1.124 |
| AVOP | Organizational Planning |  | 3.60 | .71524 |

Source: Respondents

The response indicated an average median value of 3.60 indicating majority of the respondents' agreement on the presence of proper planning of construction and design. Though the average median value of the variables is greater than 3.00 indicating the respondents’ agreement, the table also indicates a median value of 3.00 on the fifth item. This implies even though majority of the project managers are convinced with the proper implementation of construction planning activities in general terms, they agree that project schedules and completion times are not being

estimated properly.

2. Project managers’ goal commitment

Five items were presented for the respondent project managers to assess if they are fully committed for the projects’ goals. Their response indicates an average median value of 3.2 as presented in the table below indicating their commitment for the project goals they ate managing. They haven’t provide this response without reservation though as they believe they haven't felt sure whether or not they are doing enough in initiating project team members towards the attainment project goals, the goals set for projects are attainable and they are doing enough to defend projects from external influences.

Table 4.4. Project managers’ goal commitment

|  | Items | Median |  | Std. Deviation |
| --- | --- | --- | --- | --- |
| PMGC | Project managers are devoted to meet goal of the project they have assigned on. | 3 |  | 1.102 |
| PMGC | The goals set for projects are perceived to be attainable by project managers | 3 |  | 1.138 |
| PMGC | Project managers initiate their team members for successfully completing the project | 3 |  | 1.004 |
| PMGC | Project managers resist interferences and influences that might challenge project goal achievement | 4 |  | 1.383 |
| PMGC | Project managers often evaluate if the project is on the right path to meet its intended goal |  | 4 | 1.004 |
| PMGC | Project managers’ goal commitment |  | 3.20 | .80121 |

Source: Respondents

3. Project team’s motivation and goal orientation

Motivation and goal oriented-ness of project team members is proven to be one of the critical

factors for construction projects success. Hence, project managers have been asked regarding

their team members’ motivation and goal orientation. Their response is presented in the table

below.

Table 4.5. Project team’s motivation and goal orientation

|  | Items | Median |  | Std. Deviation |
| --- | --- | --- | --- | --- |
| PTMGO 1 | Project team members are motivated enough to turn the project they are assigned on in to a success | 1 |  | 1.123 |
| PTMGO 2 | The effort of project team members is directed on activities that contribute for the project success. | 4 |  | 1.031 |
| PTMGO 3 | Ideas of how to improve project performance are forwarded by project team members | 3 |  | 1.157 |
| PTMGO 4 | Project team members accept any assignment as long as it would help for project goal attainment | 1 |  | 1.275 |
| PTMGO 5 | Attaining the project goal is the priority for of the project team members |  | 3 | 1.001 |
| AVPTMGO | Project team’s motivation and goal Orientation |  | 2.40 | .59558 |

Source: Respondents

The data indicates an average median value of 2.4 which is below 3 designating most of the respondents doesn’t agree project team members are not adequately motivated and lack project goal oriented-ness. Specifically, most of the respondent project managers argue that team members lack the motivation to turn the project in to a success, their prior objective is not the successful completion of the project and are not willing assignments that are convenient to them yet have greater importance to the project success.

4. Project’s Scope and Work Definition

Another dimension of construction project management the study has tried to assess is scope and work definition of projects. Respondents were asked regarding their agreement level on the presence of proper defining of project work and scope. The result is presented in the table below.

Table 4.6. Project’s scope and work definition

|  | Items | Median | Std. Deviation |
| --- | --- | --- | --- |
| PSWD 1 | What projects are and aren’t about is well clarified | 3 | 1.421 |
| PSWD 2 | Works to be done in construction projects are listed and defined properly | 4 | 1.724 |
| PSWD 3 | Responsibilities of project participant parties are well illustrated | 3 | .927 |
| PSWD 4 | What major activities need to be done and to what end result does they lead is clearly defined. | 4 | 1.650 |
| PSWD 5 | Criteria to measure whether a project is successful or not is placed in advance | 4 | 1.004 |
| AVPSWD | Project’s scope and work definition | 3.60 | .82721 |

Source: Respondents

The analyzed response of the project managers indicates the existence of proper scope and work defining practice in the real estate development construction projects. This is indicated by the average median value of 3.6. Most of the respondents agreed up on all of the items presented in under the variable.

5. Project Manager’s Capabilities and Experience

Also another critical success factor for construction projects is the capability and experience project managers possess. This is also assured in this study where the respondents were given the chance to rank the critical success factors and most rated project manager’s capability and experience as indicated in table 4.2. Here, the respondents were asked if this critical success factor, which they rated as the most critical of all, is existed in the real estate construction projects. The results are presented in the below.

Table 4.7. Project manager’s capabilities and experience

|  | Items | Median | Std. Deviation |
| --- | --- | --- | --- |
| PMCE 1 | Project managers are rich in technical capabilities that are needed to manage the project. | 4 | 1.341 |
| PMCE 2 | Project managers are rich in managerial capabilities that are needed to manage the project | 3 | 1.015 |
| PMCE 3 | Alternative direction that leads to project goal achievement is provided by project managers when the first plan fails. | 3 | .891 |
| PMCE 4 | Project managers strongly bargain for the interest of the project not to be affected | 2 | 1.207 |
| PMCE5 | Project managers are assigned on projects only when they are believed to possess the required capabilities and experience. | 3 | 1.116 |
| AVPMCE | Project manager’s capabilities and experience | 3.00 | .78614 |

Source: Respondents

From the five items presented under the variable, most of the respondents neither agree nor disagree on four of them which is indicated by the median values of 3.0. Most of the project managers agreed that though project managers are rich in technical capabilities yet are not confident in their response in their managerial capability that is needed to successfully manage projects. This is indicated by the median values of 4.0 for technical capability and 3.0 for managerial capabilities. The data in the table also indicates the project managers’ neutrality in providing their response about project managers’ bargain to protect the project’s interest, producing alternative directions for the successful project completion and assignment as project managers based on their fitness and qualification which all are indicated by median values of 3.0.In general, the average median value of 2.80 for all the five items under the variable indicates that project managers doesn’t fulfill the required capability and experience to proper project management practices.

6. Safety Precautions and Applied Procedures

Table 4.8. Safety precautions and applied procedures

|  | Items | Median | Std. Deviation |
| --- | --- | --- | --- |
| SPAP 1 | The real estate pays greater attention for the safety of personnel and machineries throughout its operation. | 3 | .958 |
| SPAP 2 | Trainings on how to keep personnel and machineries from harm is facilitated by the real estate | 2 | 1.351 |
| SPAP 3 | Accidents that could have been prevented if safety procedures are implemented are not observed in the real estate’s projects. | 3 | .882 |
| SPAP 3 | The real estate has a well-designed safety standard | 2 | 1.174 |
| SPAP 4 | The real estate monitors the implementation of its safety standards. | 2 | .785 |
| AVSPAP | Safety precautions and applied procedures | 2.60 | .78543 |

Source: Respondents

Building construction works in nature require physical activity and the operation of several heavy machineries. Safety of equipment’s and workers is always in danger and needs to be protected. What are appropriate construction companies such as real estate developers is to develop or adopt standard safety procedures. Five items those are believed to assess the applied safety procedures of the real estates were presented to the respondents on which they expressed their level of agreement. The analyzed response indicated the existence of poor safety precaution and applied procedures in most of the real estate developers. This is indicated by the below average (2.0 for there of the items) and average (3.0 for two of the items) out of five items under the variable which left the average variable median value at 2.6.

7. Control Systems

Close follow-up and controlling of planned activities is proven to increase the likelihood of successful completion in construction projects. Taking this in to consideration, control systems of construction projects is one dimension of project management that the study intended to assess. Whether or not proper controlling systems are applied in the real estate developers under investigation is tried to be assessed by three items provided to respondents to express their level of agreement on. The results are presented in the table below.

Table 4.9. Control systems

|  | Items | Median | Std. Deviation |
| --- | --- | --- | --- |
| CS 1 | Control systems to assure projects’ timely completion are implemented | 3 | 1.085 |
| CS 2 | Control systems that assure projects ‘completion within the cost limit are implemented | 3 | 1.416 |
| CS 3 | Control systems that assure projects ‘completion based on the intended quality level are implemented | 4 | 1.050 |
| AVCS | Control Systems | 3.33 | .89752 |

Source: Respondents

The respondents’ response indicates neutrality regarding the presence of controlling system for timely and in budget completion of projects. This is indicated in the table with a median value of 3.00. This provides an average variable median of 3.33 indicating proper control systems are in practice in the real estate developing companies.

Summary of Critical Success Factors

From the discussions above, the presence of the critical success factors in the under investigation real estate developing companies have been investigated in detail. This leads up to the understanding that some are existed while some are not. In the table below, the respondents 'responses are summarized and presented to identify the critical success factors which are and are not being applied in the real estate developing companies.

Table 4.10. Summary of critical success factors

|  | Items | Median | Std. Deviation |
| --- | --- | --- | --- |
| OP | Organizational planning | 3.60 | .71524 |
| PMGC | Project manager goal commitment | 3.20 | .80121 |
| PTMGO | Project team’s motivation and goal Orientation | 2.40 | .59558 |
| PSWD | Project’s scope and work definition | 3.60 | .82721 |
| PMCE | Project manager’s capabilities and Experience | 3.00 | .78614 |
| SPAP | Safety precautions and applied Procedures | 2.60 | .78543 |
| CS | control systems | 3.33 | .89752 |

Source: Respondents

## 4.1.4. Project Success (Success Criteria)

Next to assessing the presence of critical success factors in the real estate development of Addis Ababa, the study evaluated the success level of project management. The project management success in the real estate construction projects is investigated from three different dimensions of the ‘Iron Triangle’ of project management. Respondents were asked whether or not they have completed the most recent project they have managed within the given time, cost and quality targets. Their response is presented in the table below.

Table 4.11. Project Success

|  | Project Success |  | No | Yes | Total |
| --- | --- | --- | --- | --- | --- |
| PSC1 | I have completed the most recent project | Frequency | 57 | 24 | 81 |
|  | I managed on the scheduled time. | Percent | 65% | 35% | 100% |
| PSC2 | I have completed the most recent project | Frequency | 51 | 30 | 81 |
|  | I managed on the budget allotted. | Percent | 71.4% | 28.6% | 100% |
| PSC3 | I have completed the most recent project | Frequency | 49 | 32 | 81 |
|  | I managed meeting the quality standard assigned. | Percent | 57.1% | 42.9% | 100% |

According to the data, only 24 (35%) of the respondents have completed the most recent project they have managed on the scheduled time where the other 57 (65%) are failed to do so. In terms of budget, only 30 (28.6%) of the respondents were able to complete the last project they have managed with the allocated budget while the other 51 (71.4%) needed additional financial resources to complete the projects. Lastly, project managers were asked if the maintained the planned quality level in the most recent project they have managed and which 49(57.1%) of them have failed to do so. This leads in to a conclusion that real estate development construction projects in Addis Ababa city mostly fail to be delivered in the planned time, budget and quality standards. This indicates that project management is not successful in each of the three measurements.

## 4.2. Correlation Analysis

Studying the level of interdependence between independent variables is another aspect of project management that the student researcher has tried to assess. Pearson’s correlation was used to evaluate the type and strength of relation existed between the independent variables. Pearson’s correlation is the most widely used method of measuring the degree of relationship between variables. The interdependency is measured according to the scale recommended by Hair et al (2009) and presented in the table below.

Table 4.12. Relation measurement scale between variables

|  | No relation | Week relation | Moderate relation | Strong relation | Very strong relation |
| --- | --- | --- | --- | --- | --- |
| Pearson Correlation | 0.00-0.20 | 0.21-0.40 | 0.41-0.60 | 0.61-0.80 | 1.80-1.00 |

Sources: Hair et al (2009)

Table 4.13. Correlations analysis

|  |  | PS1 (TIME) | PS2 (COST) | PS3 (QUALITY) |
| --- | --- | --- | --- | --- |
| AVOP | Pearson Correlation | -.112 | .103 | .246* |
|  | Sig. (2-tailed) | .255 | .298 | .011 |
|  | N | 81 | 81 | 81 |
| AVPMGC | Pearson Correlation | .082 | .128 | .269** |
|  | Sig. (2-tailed) | .403 | .194 | .006 |
|  | N | 81 | 81 | 81 |
| AVPTMGO | Pearson Correlation | .095 | .153 | .304** |
|  | Sig. (2-tailed) | .337 | .118 | .002 |
|  | N | 81 | 81 | 81 |
| AVPSWD | Pearson Correlation | .152 | .055 | .280** |
|  | Sig. (2-tailed) | .121 | .575 | .004 |
|  | N | 81 | 81 | 81 |
| AVPMCE | Pearson Correlation | .241* | .132 | .398** |
|  | Sig. (2-tailed) | .013 | .180 | .000 |
|  | N | 81 | 81 | 81 |
| AVSPAP | Pearson Correlation | .139 | .274** | .265** |
|  | Sig. (2-tailed) | .157 | .005 | .006 |
|  | N | 81 | 81 | 81 |
| AVCS | Pearson Correlation | .346** | .376** | .724** |
|  | Sig. (2-tailed) | .000 | .000 | .000 |
|  | N | 81 | 81 | 81 |

*. Correlation is significant at the 0.05 level (2-tailed).

**. Correlation is significant at the 0.01 level (2-tailed).

The correlation results between independent and dependent variables found to be significant at 1 and 5 percent. The results indicate the existence of positive but weak relationships between all the variables with the exception of one relationship. In the relationship existed between control systems and project completion in the planned quality standards indicates a strong positive relationship with a Pearson’s correlation value of 0.72.   Weak yet positive relationship is existed between the first dependent variable, that is timely project completion, and the independent variables project managers competency and experience (0.24) and control systems (0.35). On the other hand, the same type of relationship is existed between the second dependent variable, that is project completion in the allotted budget, and the critical success factors safety precautions and applied procedures (0.27) and control systems (0.376). Finally, the same type of relationship is existed between the third dependent variable (meeting the quality standards) and the critical success factors, organizational planning (0.25), project managers goal commitment (0.27), project team motivation and goal orientation (0.30), project scope and work definition (0.28), project managers competency and experience (0.40), safety precautions and applied procedures (0.27), and control systems (0.72).Where positive relationship is existed between dependent and independent variables, an improvement in the independent variable is observed, the dependent variable reacts in the same manner. In other words, increasing the independent variables those have positive relationship with the dependent variable, the dependent variables will also indicate improvement which increase the likelihood of project management success. The reverse is also true where if a significant negative relationship between dependent and independent variables exist, and increase in the independent variable exists, the dependent variable indicated a decrement.  Luckily, the only negative relationship indicated in the correlation matrix is the one existed between the independent variable organizational planning and the dependent variable timely project completion which is not found to be. Meaning, the change to be happen in any direction on the variable organizational planning is not significant enough to impact timely project completion whatsoever.

## 4.3 Model Estimation

In order to analyze the impact of the critical success factors on project success, a binary logistic regression model was estimated through maximum likelihood estimation method. In the model, the three project success criteria (Iron Triangle) are considered as dependent variable while Ashley’s (2011) seven critical success factors for construction projects are used as explanatory variables. Successful project completion in all the three criteria was codded as ‘1’ where failure was coded ‘0’. The set of independent variables that are included in the model are organizational planning (OP), project manager goal commitment (PMGC), project team motivation and goal orientation (PTMGO), project scope and work definition (PSWD), project manager capabilities and experience (PMCE), safety precautions and applied procedures (SPAP) and control systems (CS).The variables were presented in statistical equations as follows

P(T) = 𝛼0+ 𝛼1OP + 𝛼2PMGC + 𝛼3PTMGO + 𝛼4PSWD + 𝛼5PTMTC +𝛼6SPAP + 𝛼7 CS + 𝜀 … (1)

P(C) = 𝜷𝟎+ 𝜷𝟏OP + 𝜷𝟐PMGC + 𝜷𝟑PTMGO + 𝜷𝟒PSWD + 𝜷𝟓PTMTC +𝜷𝟔SPAP + 𝜷𝟕 CS + 𝜀 … (2)

P(Q) = 𝝁𝟎+ 𝝁𝟏OP + 𝝁𝟐PMGC + 𝝁𝟑PTMGO + 𝝁𝟒PSWD + 𝝁𝟓PTMTC +𝝁𝟔SPAP + 𝝁𝟕 CS + 𝜀 … (3)

Ordinary least square (OLS) regression is used to estimate the model. Both methods can be used to determine which predictor variables are statistically significant. However, in OLS regression, the independent variable is continuous and in logistic regression, it is binary and coded as 0 and 1.Thus, Ordinary least square is used in this study to find out the critical success factors that have a potential impact on real estate development construction projects and to accept and reject the study’s hypothesis. Critical success factors those have significant impacts on project success at (0.01) 1%, (0.05) 5% and (0.10) 10% have proved the associated null hypotheses where the rest failed to do so indicating the existence of no significant impact on project success (dependent variable).

In the model estimation, beta/slope coefficients (β) and odd ratios (OR) for each variable are reported. The beta (β) coefficient indicates the expected change in the natural logs of odds ratio of dependent variable or project success because of one unit change in explanatory variable with all of the other variables in the model held constant. A relatively unambiguous term odds ratio is the ratio of two odds. The odd of an event happening by itself is defined as the probability that the event occurs divided by the probability that the event does not occur. Odds ratio is the transformed log or an exponential of beta coefficients. If a beta coefficient is positive, its transformed log value (odds ratio) will be greater than one, meaning that project success is more likely to occur. If a coefficient is negative, its transformed log value will be less than one, and the odds of the event occurring or the probability of project success decreases. A coefficient of zero (0) has a transformed log value of 1.0, meaning that this coefficient does not change the odds of the event or project success by one way or the other.

The likelihood ratio (LR) chi-square test is used to test the over significance of the model. The test has a null hypothesis of no difference between the model with only a constant and the model with independent variables. The null hypothesis of the test is that there is no difference between the model with only a constant and the model with independent variables. Chi-square for the tested models is equal to 18.01 (0. 0119) for the first model, 24.89 (0.0008) for the second and 33.89 (0.00) forte third model. That means the null hypothesis of no difference between the model with only a constant and the model with independent variables is rejected in all three models. Thus, there exist a significant relationship between the independent and the dependent variables.

The model goodness of fit is also evaluated through Pseudo R-square with a predicted value of 0.22 for the first, 0.19 for the second and 0.53 for the third models that may explain how much the variation in dependent variable is explained by explanatory variables. However, this measures of goodness of fit is not as reliable as R-squared that is found in OLS as of many authors (Hosmer and Lemeshow, 2010).The diagnostic tests discussed so far indicates that it is pertinent to interpret the model in order to draw an inference from the tested models. Thus, the estimated result of the three models along  with diagnostic test result are presented in the table below followed by hypothesis testing and discussions on factors that are found to be significant in the models.

Table 4.14. Results of logistic regression estimates of determinates of project management  success

|  | Model 1 Dependent variable: PSC 1 (Time) |  |  | Model 2 Dependent Variable: PSC2 (Cost) |  |  | Model 3 Dependent variable:PCS 3 (Quality) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Variables | Coeff. | Sig | Odds Ratio | Coeff. | Sig. | Odds Ratio | Coeff. | Sig. | Odds Ratio |
| AVOP | -1.653*** (0.543) | .002 | 0.191*** (0.104) | 0.246 (0.532 | .635 | 1.278 (0.680) | -0.12 (-0.456 | .873 | 0.887 (0.404) |
| AVPMGC | -0.462 (0.590) | .47 | 0.630 (0.372 | -0.0631 (0.577) | .920 | 0.939 (0.542) | - 1.301** (-0.602) | .102 | 0.272** (0.164) |
| AVPTMGO | 0.150 (0.591 | .80 | 1.162 (0.687) | 0.482 (0.520) | .366 | 1.619 (0.842 | 1.596*** (-0.473) | .116 | 4.933*** (2.335) |
| AVPSWD | -0.0467 (0.471) | .92 | 0.954 (0.450 | -0.603 (0.467) | .175 | (0.842) 0.547 | -0.587 (-0.505) | .424 | 0.556 (0.281) |
| AVPMCE | 1.448*** (0.560) | .017 | 4.254*** (2.383) | -0.651 (0.610) | .289 | 0.522 (0.318) | 0.941 (-0.585) | .249 | 2.563 (1.499) |
| AVSPAP | -0.634 (0.403) | .15 | 0.530 (0.214) | 0.977** (0.442) | .044 | 2.656** (1.173) | -0.231 (-0.352) | .718 | 0.794 (0.279) |
| AVCS | 1.186*** (0.451) | .002 | 3.274*** (1.478) | 1.094*** (0.305) | .002 | 2.985*** (0.911) | 2.959*** | .000 | 19.28*** (11.38 |
| Constant | -0.383 (1.793) | .82 | 0.682 (1.223) | 0.00621* (0.0165) | .013 | -5.082* (2.664) | 9.900*** (-2.876) | .001 | 5.0205*** (0.000144) |
| Observations | 81 |  | 81 | 81 |  | 81 | 81 |  | 81 |
| Wald chi2(7) | 18.01 |  |  | 24.89 |  |  | 33.89 |  |  |
| Prob> chi2 | 0.0119 |  |  | 0.0008 |  |  | 0.0000 |  |  |
| Pseudo R2 | 0.2166 |  |  | 0.1869 |  |  | 0.5255 |  |  |

Robust standard errors in parentheses

*** p<0.01, ** p<0.05, * p<0.1

## CHAPTER FIVE

## CONCLUSION AND RECOMMENDATIONS

This chapter tried to summarize the outcomes of the study or findings and to provide possible solutions or recommendations in order to solve the problems. The first section of this chapter is dedicated to the conclusion part and based on these summarized findings recommendations are given last.

## 5.1. Conclusions

The construction industry is a major component, a key contributor and major player in the economic development of any given economy. It provides numerous employment opportunities to the skilled, semi-skilled and unskilled segments of society's labor force, offers market for construction materials hence uplifting living standards to many people and provides the infrastructural platform for further economic development. Due to numerous advantages derived from the industry to the economy, it is critical and imperative to facilitate its effectiveness in performance and delivery.

Real estate companies have no involvements in the real estate space market; all provide residential properties in the Asset market. Most have an exclusive focus on the supply of luxurious if not very expensive housing in which this segment is very thin for which majority of the suppliers relied on. Almost all middle income levels do not fit to this segment and that is why it remained a market for the Diaspora. And this excessive reliance on those groups may seriously affect its prospect. However, there is acute Shortage of residential building especially for low-income households that account for over 80 percent of the city’s population. And this demand is not yet the target of the companies because of different reasons.

The market is at its grass root level and not yet reached maturity. It is not competitive and efficient market. The advantages of operating economies of scale that may be achieved by developers in such markets are least probable to be transferred from the builders to buyers, because of this. The absence of competition (& efficiency), and lack of contemporary real estate market, may hinder transparency and access to “real” time market information. As a result, the bargaining power of the buyers become weak and price setting powerfully rest on the seller’s hand, which also affects the affordability of those buyers. Real estate sector in Addis Ababa was on upturn in the recent periods. The main growth thrust is due to favorable demographics, and increased demand from the Ethiopian Diaspora, in which prices were raised highly. However, the local demand side is not enhanced by increasing purchasing power. The existing inadequate supply of mortgage is also affected by the increase in costs of houses. Minimum own requirements are now raised up to 50%. The mortgage facility is also affected by both the real estate companies’ support (to facilitate the collateralization process), and the buyers’ capacity and transparency with the bank. The sales pattern in the real estate market mainly has an installment basis; payments are made at different phases while the houses have been built for the buyers. Sales from inventory are not common in the market (by sample companies).

Planning of construction and design works (organizational planning) are found to exist in the real estate yet the practice still lacks properly planning project schedules and construction completion time. The success factor also found to have a significant negative impact on project management success against what is theoretically right and expected. This indicates though organizational planning is practiced in the real estates, it is not being done correctly in a way that contributes for the success of project management. However project managers believe they are fully committed for the attainment of goals of the projects, their effort in this dimension is hurting the success of project management than it is benefiting. Project managers also failed to motivate and initiate subordinate team members towards successful completion of projects. Regardless of its significant positive impact over project management success, real estate developers have failed to motivate project team members and to make them and their effort goal oriented. Irrespective of the qualities project team members have in providing idea on how to increase the likelihood of project success, they lack the motivation and the willingness to take assignments that have greater importance for the project management success.

The successful completion of the project is also found not to be the prior intention of the team members. Once again, real estate developers have missed a critical success factor that is proven to have a significant positive impact on project management success. Notwithstanding of being considered the most prior critical success factor for construction project management success and proven to have a positive impact, project manager’s competency and experience is found not to be adequate in the real estate development construction projects. Project managers are rich in technical capabilities though they lack the needed managerial capability. It is also true that project managers are assigned in the position without possessing the required capabilities and they fail to produce alternative directions when the project struggles to succeed. The one and only success factor that has a positive significant impact on project success and existed in the real estate development construction projects is control systems. Proper controlling systems monitoring the successful completion of projects in terms of time, cost and quality are implemented in the real estate development construction projects. Luckily, this is also the one and only success factor that positively impact all the three measures of project success which are time, cost and quality. In general, only one of the critical success factors that possess a significant positive impact is found to exist in the real estate construction projects though there are three others which the real estate development construction projects have missed. Also among the critical success factors that are existed in the projects, some are found to have a negative impact in project management success against what is theoretically right.

## Recommendation

From the foregoing results the study recommends that; the foreign exchange policy ought to be determined by the forces of demand and supply, thus the status quo remains as such to attract investment in the real estate segment. Secondly, the both national and county government ought to be discouraged from borrowing locally as such to increase the prospect of real estate growth. Thirdly, there is need to devise measures and mechanisms of improving the GDP so as to ensure there is a positive trend in the real estate sector. Finally, measures ought to be taken as such to control the level of inflation even if it increases the prospect of real estate growth. Future research should adopt the use of primary data to examine the determinants of real estate growth in Ethiopia. From this study it would be appropriate to retrieve first-hand information from those who are actively involved real estate development and also gather information from those who benefits from real estate investment in Ethiopia. Most importantly, much should be done on the demand side to enable households buying housing.

Mechanisms to enhance or increase the borrowing capacity of buyers are mostly needed. The favorable demographic feature in Addis which increases the need (underlying demand) for housing is not supported by an ability to afford buying, under current trends. Policy needs to focus on increasing the supply of housing - particularly low-cost housing - and reducing the time taken to bring land and housing to market. The provision of low cost house by these developers may stimulate the demand of many, rather than the current excessive focus on the very expensive housing supply in the market. So it is advisable if these companies should think of supplying less complex homes that can be affordable by many. In addition, the government has a role in promoting real estate growth more so it ought to ensure that all are housed in good housing conditions. Through government planning, future studies ought to examine the role of government on real estate development and what it can do as such to trigger faster growth and development in the real estate sector

## References

Akarakiri (2006): Project Analysis, Selections and Evaluation, OAU Printing Press.

Ashley &Jaselskis (2011), Determinants of construction project success, Project, Management

Journal, Vol .18, (2), pp.69 – 79

Atkinson R (2000), „Project management: cost, time and quality, two best guesses and

phenomenon, it’s time to accept other success criteria‟, International Journal of Project

Management, Vol. 17, Issue 6, pp. 337-342.

Avots I (1969), Why does project management fail? .California management review,12,(10),pp.

77-82

Baccarini, D. (2011). The Logical Frame Work Method for Defining Project Success.Project

Management Journal 30 (4), 25-32.

Baker, BN; Murphy, DC & Fisher, D (1988), Factors Affecting Project Success: Project

Management Handbook, Van Nostrand Reinhold co., 2nd edition, New York.

Baker.B.N, Murphy, D. C. & Fisher, D. (1983). Factors affecting project success, Project

Management Handbook, (ed.) D.I Cleland & W.R King, VanNostraud Reinhold, NY,Pp669

BarnesN.M.L and Wearne S.H. (1993) .The future of major project management. International

Journal of Project Management, 11(3), pp. 135 -142

Beale,P.and Freeman M. (1991), Successful project execution: a model. Project Management

Journal, 4 (December), pp. 23-30

Bedelin H.M (1996), Successful major projects in a changing industry. Civil engineering, April,

pp. 55-63

Belassi, W. &Tukel, O.I. 1996. A new framework for determining critical success/failure factors

in projects. International Journal of Project. Management, 14(3), pp. 141- 151.

Bentley D. and Raftery G. (1992), Project management: key to success. Civil Engineering,

April,pp. 58-59

Bryde, D J (2005), „Methods for Managing Different Perspectives of Project Success‟,British

Journal of Management, Vol. 16, pp. 119-131.

Cash C. and Fox R. (1992), Elements of successful project management. Journal of System

Management, pp. 10-12

Chan, A. P. C., Scott, D., and Lam, E. W. M. (2004).Framework of success criteria for

Design/build projects. J. Manage. Eng., 18~3!,120–128.

Chan, A.P.C and Chan A.P.L (2004) Key performance indicators for measuring construction

Success. Benchmarking: An international Journal, 11(2), 203-221.

Chua D.K.H and Kog, Y.C. and Loh, P.K. (1999) Critical success factors for different

project objectives. Journal of construction engineering and management, May/June 1999. Chua D.K.H and Loh P.K. (1997), Neural networks for construction project success. Expert

Systems with Applications, Vol 13(4), pp.317-328

Clarke A. (1999), A practical use of key success factors to improve the effectiveness of project

Management, International Journal of Project Management, 17(3), pp. 139-145

Cleland, D. I. (1994): Project Management – Strategic Design and Implementation (2nd ed.)

New York: McGraw-Hill.

Cooper, T (2001), „The “real” success factors in projects‟. International Journal of

Project Management, Vol. 20, pp. 185–190.

Crawford, L. 2006. Profiling the competent project manager. In: Project Management

Research at the Turn of the Millennium: Proceedings of PMI Research Conference,

21-24 June 2000, Paris, France.Sylva,NC: Project Management Institute, pp.3-15.

Crawford, L. 2005. Senior management perceptions of project management competence.

International Journal of Project Management, 23(1), pp. 7-16.

De Wit, A. (2002): Measurement of project success. International Journal of Project

Management 6(3): 164-170.

Dvir, D, Raz, T &Shenhar A J (2003), „An empirical analysis of the relationship between

Project planning and project success‟, International Journal of Project Management, Vol.

21, pp. 89–95.

Ellatar, S.M.S.(2009).Towards Developing an Improved Methodology for Evaluating

Performance and Achieving Success in Construction Projects. Scientific Research

Vol 4. n. 6, June, pp. 549-554.

Fekete, I. – Dobreff, Cs. (2003): Távközlésiprojektmenedzsment [ICT project management].

Budapest: MűegyetemiKiadó.

Harvey, M. (1999).Project Management, the Nature and Context of Project Management,

Strategy and Project Management, Financial Time Prentice Hall

Hensey M. (1991), Essential success factors for strategic planning, .Journal of Management in

Engineering, 7(2), April,.pp .167-177

Hughes M.W. (1986), Why project fail: The effect of ignoring the obvious. IndEng

(1986),Vol.18,pp.14 -18

International Journal of Project Management, vol 24, pp 53-65.

International Project Management Association (2014): The PE Model. http://ipma.ch. Accessed:

10.11.2014.

Jaafari, Ali (2001) Management of risks, uncertainties and opportunities on projects: time for a

Fundamental shift. International Journal of Project Management, 19(2), 89-101.

Jha, K.N. –Iyer, K.C. (2007): Commitment, coordination, competence and the iron triangle.

International Journal of Project Management 25(5): 527–540.

Judgev, K. –Müller, R. (2007): A Retrospective Look at Our Evolving Understanding of Project

Success.Project Management Journal 36(4): 19-31.

Kerzner H. (2003). In Search of Executive in Project Management Successful practices in high

performance organization. New York: John Willey and Sons.

Kerzner, H. 2006. Project management: A system approach to planning, scheduling and

controlling. 9th edition. New Jersey: John Wiley & Sons Publications.

Kerzner, H. 2011. Gerenciamento de Projetos: Uma AbordagemSistêmica Para

Müller, R. – Turner, J. R. (2007): Matching the project manager’s leadership style to project

type. International Journal of Project Management 25(1): 21-32.

Munns, AK &Bjeirmi, BF (2007), „The role of project management in achieving project

success‟, International Journal of Project Management, Vol. 14, Issue 2, pp. 81-88.

Nguyen DL, Ogunlana SO, Quang T and Lam KC. (2004), large construction projects in

developing countries: a case study from Vietnam, International Journal of Project

Management, Elsevier, 22(7), pp. 553-561

Olander S. and Landin A., (2005), Evaluation of stakeholder influence in the implementation of

construction projects, in International Journal Of Project Management, vol23,pp321-328.

Olsen, R. P. (1971): Can project management be defined? Project Management Quarterly 2(1):

12-14.

Pinto, J. and Mantel S.J. (1990), The cause of project failure, in IEEE Transaction On

Engineering Management, vol.37, no.4, pp269-276, IEEE.

Pinto, JK &Slevin, DP (1987), Critical Factors in Successful Project Implementation‟,

IEEE Transactions on Engineering Management, New York, Vol. EM34, p. 22-28.

Pinto, JK &Slevin, DP (2005), Project Success: Definitions and Measurement Techniques‟,

Project Management Journal, Sylva, Vol. 19, Issue 1.

Planejamento, Programação e Controle; São Paulo: Blucher.

Shenhar, AJ; Levi, O &Dvir, D (June 2002), „Mapping the dimensions of project success‟,

Project Management Journal, Sylva, Vol. 28 Issue 2, pp. 5-14.

Turner J.R & Muller R. (2010). The Project Managers Leadership Style as a Success Factor on

Projects: A Literature Review. Project Management Journal, 36(1), 49-50.

Turner, JR (1999), Handbook of Project-based Management: Improving the Process for

Achieving Strategic Objectives (2nd ed.), McGraw-Hill, London.

Verma V.K (1995). Organizing Projects for Success, Project Management Institutes, and

Newton Square, PA

Westerfeld, E. (2003): The Project Excellence Model®: linking success criteria and critical

success factors. International Journal of Project Management 21(6): 411-418.

Yeo K.T., (2002), Critical failure factors in information systems projects, in International

Construction Project”. Journal Review: Journal of construction engineering.

## Appendix A

AMBO UNIVERSITY

SCHOOL OF GRADUATE STUDIES

Questionnaire for data collection

Dear respondents

I am undertaking a research survey on construction project focusing “Factors affecting the real estate construction project: The case of Addis Ababa City”The research is an individual research project as part of my study for MBA Degree at AmboUniversity.

The main purpose of the research questionnaire is to collect information regarding the current condition of factors affect real estate Development construction Projects in Addis Ababa. As a key staff you are invited to participate in this survey. The information you provide in response to the items in the questionnaire will be used as part of the data needed for the study.

All the information you provide will kept in strict confidentiality and it will be used only for academic research .please answer each question carefully .there is no right or wrong answer. If you are unsure of an answer, please respond with your best estimate. I value your participation and thank you for the commitment of time, energy and effort. If you have any further question, I can be reach at the address below.

Sincerely

Abebe Chala Mako

Email jiinenuscaalaa@gmail.com

Cell phone No. - +2519-12-97-85-29

- +2519-19-45-56-46

1. GENERAL INSTRUCTIONS

- There is no need of writing your name

- In all cases were answers options are available please tick (If there is anything that you would like to add?

_________________________________________________________________________

_________________________________________________________________________

_______________________________________________________.) in the appropriate box.

Part I. Back ground information about the respondents please use (√) in the relevant box for your response

a. Gender Female Male

b. Educational back ground

1. PHD

2. MA/MSC

3. BA/BSC

4. College Diploma

c. Work Experience

1. Less than 5 years

2. 5-10 years

3. 10-15 years

4. Above 15 year

d. Job Title

1. Top Management

(Manager)

2. Middle management

(Team leader)

3. Project management

4. Others (………………)

Please write your title.......................................................................

2. PROJECT SUCESS

Instruction: Rank the items presented in the table from 1st to 7th based on their importance for project success. You may leave item/s unranked that you believe have no importance for successful project completion.

| No | Item | Rank |
| --- | --- | --- |
| 1 | Project manager goal commitment |  |
| 2 | Clarity of the project’s scope and work definition |  |
| 3 | Project team’s motivation and goal orientation |  |
| 4 | Use of proper control systems |  |
| 5 | Safety precautions and applied procedures |  |
| 6 | Proper organizational planning(Construction and design planning effort) |  |
| 7 | Project manager’s capabilities and experience |  |

No. Items Rank

13. PROJECT SUCCESS FACTORS

Instruction: Read the statements in the table and show to what extent you agree with them

by marking (√) sign. The numbers represent: 1 strongly disagree, 2 disagree, 3 neutral, 4

agree, and 5 strongly agree.

Project Success Factors

| No | Item | 1 SD | 2 D | 3 N | 4 A | 5 SA |
| --- | --- | --- | --- | --- | --- | --- |
| Organizational planning |  |  |  |  |  |  |
| 1 | Adequate consideration and attention is given in designing buildings. |  |  |  |  |  |
| 2 | Constructions are thoroughly planned in advance before they are started. |  |  |  |  |  |
| 3 | Resources needed to carry out construction projects are well recognized in advance. |  |  |  |  |  |
| 4 | There is a proper estimation of the cost that will be needed to complete the construction |  |  |  |  |  |
| 5 | Project schedule and construction completion time are well planned. |  |  |  |  |  |

| No | Item | 1 SD | 2 D | 3 N | 4 A | 5 SA |
| --- | --- | --- | --- | --- | --- | --- |
| Project manager goal commitment |  |  |  |  |  |  |
| 6 | Project managers are devoted to meet goal of the project they have assigned on. |  |  |  |  |  |
| 7 | Project managers are devoted to meet goal of the project they have assigned on. |  |  |  |  |  |
| 8 | The goals set for projects are perceived to be attainable by project managers |  |  |  |  |  |
| 9 | Project managers often evaluate if the project is on the right path to meet its intended goal. |  |  |  |  |  |
| 10 | Project managers resist interferences andinfluences that might challenge project goal achievement. |  |  |  |  |  |
| Project team’s motivation and goal orientation |  | 1 SD | 2 D | 3 N | 4 A | 5 SA |
| 11 | Project team members are motivated enough to turn the project they are assigned on in to a success. |  |  |  |  |  |
| 12 | Ideas of how to improve project performance are forwarded by project team members. |  |  |  |  |  |
| 13 | The effort of project team members is directed on activities that contribute for the project success. |  |  |  |  |  |
| 14 | Attaining the project goal is the priority for of the project team members. |  |  |  |  |  |
| 15 | Project team members accept any assignment as long as it would help for project goal attainment |  |  |  |  |  |
| Clarity of the project’s scope and work definition |  | 1 SD | 2 D | 3 N | 4 A | 5 SA |
| 16 | What projects are and aren’t about is well clarified. |  |  |  |  |  |
| 17 | Works to be done in construction projects are listed and defined properly. |  |  |  |  |  |
| 18 | Responsibilities of project participant parties are well illustrated |  |  |  |  |  |
| 19 | What major activities need to be done and to what end result does they lead is clearly defined. |  |  |  |  |  |
| 20 | Criteria to measure whether a project is successful or not is placed in advance. |  |  |  |  |  |

| No | Item | 1 SD |  | 2 D |  | 3 N | 4 A | 5 SA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project manager’s capabilities and experience |  |  |  |  |  |  |  |  |
| 21 | Project managers are rich in technical capabilities that are needed to manage the project. |  |  |  |  |  |  |  |
| 22 | Project managers are rich in managerial capabilities that are needed to manage the project. |  |  |  |  |  |  |  |
| 23 | Alternative direction that leads to project goal achievement is provided by project managers when the first plan fails. |  |  |  |  |  |  |  |
| 24 | Project managers strongly bargain for the interest of the project not to be affected. |  |  |  |  |  |  |  |
| 25 | Project managers are assigned on projects only when they are believed to possess the required capabilities and experience. |  |  |  |  |  |  |  |
| Safety precautions and applied procedures |  |  | 1 SD |  | 2 D | 3 N | 4 A | 5 SA |
| 26 | The real estate pays greater attention for the safety of personnel and machineries throughout its operation. |  |  |  |  |  |  |  |
| 27 | Trainings on how to keep personnel and machineries from harm is facilitated by the real estate. |  |  |  |  |  |  |  |
| 28 | Accidents that could have been prevented if safety procedures are implemented are not observed in the real estate’s projects. |  |  |  |  |  |  |  |
| 29 | The real estate has a well-designed safety Standard |  |  |  |  |  |  |  |
| 30 | The real estate monitors the implementation of its safety standards |  |  |  |  |  |  |  |
| Use of control systems |  |  | 1 SD |  | 2 D | 3 N | 4 A | 5 SA |
| 31 | Control systems to assure projects’ timely completion are implemented |  |  |  |  |  |  |  |
| 32 | Control systems that assure projects’ completion Within the cost limit are implemented. |  |  |  |  |  |  |  |
| 33 | Control systems that assure projects’ completion based on the intended quality level are implemented. |  |  |  |  |  |  |  |

4. PROJECT SUCCESS CRITERIA

Instruction: Read the statements in the table and show if the last project you have completed meet the three success criteria by marking (√) sign. The numbers represent: 1 Yes and 2 No.

Project Success (Time, Cost, Quality)

| No | Item | Yes 1 | No 2 |
| --- | --- | --- | --- |
| 1 | I have completed the most recent project I managed on the scheduled time. |  |  |
| 2 | have completed the most recent project I managed on the budget allotted. |  |  |
| 3 | I have completed the most recent project I managed meeting the quality standard assigned. |  |  |

- If there is anything that you would like to add?

_________________________________________________________________________

_________________________________________________________________________

_______________________________________________________.

## Appendix B

Model Testing

Time (PS1)

Model Summary

| Step | -2 Log likelihood | Cox & Snell R Square | Nagelkerke R Square |
| --- | --- | --- | --- |
| 1 | 106.750a | .245 | .337 |

a. Estimation terminated at iteration number 5 because                                                            parameter estimates changed by less than .001.

Variables in the Equation

| Variables | B | S.E. | Wald | df | Sig. | Exp(B) |
| --- | --- | --- | --- | --- | --- | --- |
| AVOP AVPMGC AVPTMGO Step 1 AVPSWD AVPMC AVSPAP AVCS Constant | -1.653 -.462 .150 -.047 1.448 -.634 1.186 -.383 | .536 .635 .592 .440 .607 .439 .382 1.713 | 9.516 .530 .064 .011 5.691 2.087 9.620 .050 | 1 1 1 1 1 1 1 1 | .002 .467 .800 .915 .017 .149 .002 .823 | .191 .630 1.162 .954 4.254 .530 3.274 .682 |

A.Variable entered on step 1: AVOP, AVPMGC, AVPTMGO, AVPSWD, AVPMCE, AVSPAP,

AVCS.

Cost (PS2)

Model Summary

| Step | -2 Log likelihood | Cox & Snell R Square | Nagelkerke R Square |
| --- | --- | --- | --- |
| 1 | 102.157a | .200 | .287 |

a. Estimation terminated at iteration number 5 because                                                                        parameter estimates changed by less than .001.

Variables in the Equation

| Variables | B | S.E. | Wald | df | Sig. | Exp(B) |
| --- | --- | --- | --- | --- | --- | --- |
| AVOP AVPMGC AVPTMGO Step 1a AVPSWD AVPMC AVSPAP AVCS Constant | .246 -.063 .482 -.603 -.651 .977 1.094 -5.082 | .517 .632 .533 .445 .614 .486 .346 2.045 | .226 .010 .818 1.838 1.123 4.048 10.013 6.177 | 1 1 1 1 1 1 1 1 | .635 .920 .366 .175 .289 .044 .002 .013 | 1.278 1.278 1.619 .547 .522 2.656 2.985 .006 |

a. Variable(s) entered on step 1: AVOP, AVPMGC, AVPTMGO, AVPSWD, AVPMCE, AVSPAP, AVCS.

Quality (PS3)

Model Summary

| Step | -2 Log likelihood | Cox & Snell R Square | Nagelkerke R Square |
| --- | --- | --- | --- |
| 1 | 68.049a | .512 | .688 |

a. Estimation terminated at iteration number 7 because parameter estimates changed by less than 001.

Variables in the Equation

| Variables | B | S.E. | Wald | df | Sig. | Exp(B) |
| --- | --- | --- | --- | --- | --- | --- |
| AVOP AVPMGC AVPTMGO Step 1a AVPSWD AVPMC AVSPAP AVCS Constant | -.120 1.301 1.596 - .587 .941 -.231 2.959 -9.900 | .747 .795 1.014 .735 .817 .641 .724 2.969 | .026 2.678 2.476 .638 1.327 .130 16.703 11.118 | 1 1 1 1 1 1 1 1 | .873 .102 .116 .424 .249 .718 .000 .001 | .887 .272 4.933 .556 2.563 .794 19.276 .000 |