AMBO UNIVERSITY

COLLEGE OF BUSINESS AND ECONOMICS

DEPARTEMENT ACCOUNTING AND FINANCE

Factor Affecting Projects Cost Overrun on Real Estate Construction Projects: The Case of Addis Ababa City.

A master’s thesis submitted to department of Accounting and Finance, College of business and Economics, Ambo University for the partial fulfillment of masters of business administration in Finance.

By: Abdisa Angasa

Advisor: Ayana Gemechu(Assistant Professor)

October, 2022

Ambo, Ethiopia

DECLARATION

I, Mr. Abdisa Angasa, hereby declared and affirmed that the research thesis entitled “Factor Affecting Projects Cost Overrun on Real Estate Construction Projects: the Case of Addis Ababa City” was my own work conducted under the supervision of Ayana Gemechu(Assistant Professor). I followed all the ethical principles of research work, data collection, data analysis and completion of the research thesis. All research matters that was included in the thesis given recognition through citation. I adequately cited and referenced all the original sources. I also declared that I have adhered to all principles of academic honesty and integrity and I have not misrepresented, fabricated, or falsified any idea /data/fact/ source in my research thesis submission. I further declared that the research thesis did not been submitted to any other institution anywhere for the award of any academic degree, diploma or certificate.

I understood that any violation of the above would be cause for disciplinary action by the University and can evoke penal action from the sources which had not properly cited, or from whom proper permission had not taken when needed.

Name of the researcher: Abdisa Angasa Boru

Signature:_________________

Date of submission:_______________

# CERTIFICATION SHEET

This is to certify that the thesis entitles “Factor Affecting Projects Cost Overrun on Real Estate Construction Projects: the Case of Addis Ababa City”, submitted in partial fulfillments of the requirements for the award of master of business administration in finance and is work carried out by Mr. Abdisa Angasa, under my guidance and supervision.

________________________ Signiture_______________ Date ___________________

Advisor Name

As mentioned 	of the of examiners of the MA. Thesis open defense examined, we certified that we have read and evaluated the thesis prepared by Abdisa Angasa and examined the candidate. We recommend that the thesis be accepted as fulfilling the thesis requirements fot the Degree of MBA in finance.

________________________ Signiture_______________ Date ___________________

Chairperson

________________________ Signiture_______________ Date ___________________

Internal Examiner

________________________ Signiture_______________ Date ___________________

External Examiner

________________________ Signiture_______________ Date ___________________

# APPROVAL SHEET

The thesis entitles “Factor Affecting Projects Cost Overrun on Real Estate Construction Projects: the Case of Addis Ababa City” is prepared by Abdisa Angasa in partial fulfillments of the requirements for the Award of Master of Business Administration in Finance, with the regulation of the university the accepted standards with respect to originality.

Submitted by

_______________________             ___________________                       _______________

PG Candidate                                     Signature                                             Date

Approved by:

- Advisor

Ayana Gemechu (Assistant Professor)       _____________                       ___________

Signature                                 Date

- College/Institute Dean:

_______________________             _______________                       _______________

Name                                                       Signature                                 Date

- Head of Department:

_______________________             _______________                       _______________

Name                                                       Signature                                 Date

- Director, School of Graduate studies:

_______________________             _______________                       _______________

Name                                                       Signature                                 Date

ACKNOWLEDGEM

The completion of this thesis would have not been realized without the help of Almighty God and others; I would like to take this opportunity to thank everyone who helped me with this thesis. With deep gratitude, I also acknowledge and appreciate the kind support, guidance, constructive supervision, insightful comments and suggestions of my academic advisor Ayana Gemechu(Assistant professor) from the core of my heart. His constant encouragement throughout the period of this study have been greatest inducement for me and directly contributed to the accomplishment of the task.

Sincere thank to the Real Estate Construction Projects management and participants for their precise time and frank response to the questionnaires and interviews with out which this paper would come to life.

Finally my special gratitude goes to my lovely teachers of Ambo University and I would like to thanks all of my staff members and also all of Ambo University workers for their moral support. God bless all of you.

TABLE CONTENTS

Declaration……………………………………………………………………………....................I

Certificate……………………………………………………………………………………..…..II

Approval Sheet…….……………………………………………………………………..………III

Acknowledgment………………………………………………………...………………………IV

Table Content ……………………………………..…………………………………….................V

List of tables………………………………………………………………….……………...........X

List  Of Figures. ……………………………………….…………………………..………….....XI

Acronyms And Abbreviations……………..………………………………………………….…XII

Abstract………………………………………………………………………………………...XIII

CHAPTER ONE

INTRODUCTION………………………………………………………………….……………1

1. Background of the study…………………………………………………………………….1

1.1 Statement of the problem……………………………………………………………….….3

1.2 Research questions………………………………………………………………………....6

1.3 Objectives of the study……………………………………………………………………..6

1.3.1 General objective……………………………………………………………………….6

1.3.2 Specific objective………………………………………………………….………...….6

1.4 Significance of the study………………………………………………...………….…..…7

1.5 Scope of the study………………………………………………………………...……..…7

1.6 Limitations of the Study…………………………………………………………………....7

1.7 Organization of the paper ………………………………………………………………....8

CHAPTER TWO

REVIEW OF RELATED LITERATURE……….……………………………………………9

2. ITRODUCTION OF THE STUDY…………………………………………………………………………………………………………..9

2. Theoretical Review…………………………………………………………..…………....9

2.1cost overrun in construction industry………………………………………….……….10

2.1.1 Concepts Of Real Estate Development…………………………………………...10

2.1.2 Construction Management In Real Estate	11

2.1.3 Factors leading to cost overrun in construction project	12

2.1.3.1 Factors related to contractor	12

2.1.3.2 Economic factor	14

2.1.3.3. Consultant related factors	15

2.1.3.4  Owner related factors	15

2.1.3.5.Timeliness of payment and financial factors	16

2.1.4 Cost overrun	17

2.1.4.1. Cost overrun in Ethiopia	20

2.2 Empirical review………………………………………………………………………......…22

2.3 Research gap………………………………………………………………………….….......23

2.4 Conceptual framework………………………………..…………………………..…………23

CHAPTER THREE

RESEARCH METHODOLOGY………………………………………………………..…….25

3. Introduction……………………………………………………………………………….…..25

3.1 Description of study area………………………………...…………………………….....25

3.2 Background of the organization…………………………………………………………..25

3.3 Research design………………………………………………………………………..…26

3.4 Research approach……………………………………………...………………………...26

3.5 Data sources and type………………………………………………………………..…...26

3.6 Target population …………………………………………………………..………….27

3.7 Sample size……………………………………………………………………….……27

3.8 Sampling Techniques………………………………………………………………….28

3.9 Data collection Techniques…………………………………………………………....29

3.10 Method of Data analysis………………………………………………………...…...30

3.10.1 Descriptive analysis…………………………………………………………....….30

3.10.2 Model specification ………………………………………………………………30

3.10.2.1 Logistic Regression Analysis…………………………………………………...31

3.10.2.2 Basic assumption of binary logistic regression model………………….….…...32

3.10.2.3 Estimation of parameters……………………………………………..………....33

3.10.2.4 Variable selection and Model assessment……………………………………....34

3.10.2.4.1 Variable selection…………………………………………………………..34

3.10.2.4.2 Assessing goodness of fit……………………………………………..……34

3.10.2.4.3 The Hosmer-Lemeshow Test………………………………………………..34

3.10.2.4.4 The Likelihood Ratio Test……………………………………………….…..35

3.10.2.4.5 The Wald Test……………………………………………………………….35

3.11 Ethical consideration…………………………………………………………………..36

CHAPTER FOUR

DATA PRESENTATION AND ANALYSIS ………….………………………..………...…37

4.1 Introduction…………………………………………………………………..……37

4.1.1 Response Rate………………………………………………………………....37

4.2 General Information about the respondents………………………………………...38

## 4.3 Discussion on Factor Affecting Projects Cost Overrun……………………………41

## 4.3.1 Rank the project’s cost overrun……………………………………….......…41

4.3.2 Causes of project cost overrun using descriptive analysis………………....42

## 4.3.2.1 Factors related to contractor…………………………………..…......43

4.3.2.2   Economic Factors…………………………………………………..….46

### 4.3.2.3 Consultant-related factors………………………………………...…....48

4.3.2.4 Owner-related factors…………………………………………………..50

4.3.2.5 Timeliness of Payment and Financial Factors………………………….52

## 4.4 Inferential Analysis………………………………………………………..….........54

### 4.4.1 Logistic Regression Model Analysis……………………………………….....55

4.4.1.1 Classification…………………………………………………………....55

4.4.1.2 Omnibus Tests of Model Coefficients………………………………….56

4.4.1.3 Model Summary……………………………………………..…………56

4.4.1.4 Hosmer and lem test………………………………..…………………...57

4.4.1.5 Variables in the Equation…………………………………………...…..58

4.5 Presentation and Analysis of the Interview Data………………………………….59

4.5.1 The way of cost of the project determined……………………………….59

4.5.2 Projects resources distribution…………………………………………….60

4.5.3 Factors for project cost overrun…………………………………………...60

4.5.4 Projects cost incurred due to schedule delay……………………………....60

4.5.5 The relationship between size of the project and rate of cost overrun……..60

CHAPTER FIVE

# SUMMARY, CONCLUSION AND RECOMMENDATIONS……………………………...61

## 5.1 Summary of Major Findings…………………………………………….……….61

5.2 Conclusions……………………………………………………………….……...62

## 5.3 Recommendations…………………………………………………………….…..63

REFERENCE………………………………………………………….........................................64                                                      APPENDEXIES ……………………………………………………………………………..…71

List of table

Table 3.1 Population and sample size……………...………...………………..……………….28

Table 4.1 Rate of Respondent…………………………………………………………………....38

Table 4.2 Demographic characteristics of the respondents…………………………………......38

Table 4.3 Ranking the factor affecting the determinants of projects cost overrun……….…….41

Table 4.4 Causes of project cost overrun………………………………………………………..42

Table 4.5 Factors related to contractor……………………………………………………...……..44

Table 4.6 Economic Factors…………………………………………………………………..…47

### Table 4.7 Consultant-related factors……………………………………………………………..49

Table 4.8 Owner-related factors…………………………………………………………………51

Table 4.9 Timeliness of Payment and Financial Factors………………………………………...53

Table 4.10 Case Processing Summary………………………………………………………...…55

Table 4.11 Encoding…………………………………………………………………………......55

Table 4.12 Classification table………………………………………………………………...…55

Table 4.13 Omnibus Tests of Model Coefficients…………………………………………….....56

Table 4.14 Model Summary…………………………………………………………………..…56

Table 4.15 Hosmer and Lemeshow test………………………………………………………….57

Table 4.16 Variables in the Equation…………………………………………………………….58

List of Figures

Figure 2.1 Conceptual framework of the study…………………………….……………………24

Figure 4.1 cost estimation techniques used…………………………………………….………...40

ACRONYMS AND ABBREVATION

AC                                              Actual Cost

GDP                                            Gross Domestic Products

PC                                                Planned Cost

PDF                                             Probability Density Function

SPSS                                           Statistical Package for Social Studies

TQM                                           Total Quality Management

# Abstract

The purpose of the study was to identify Factor Affecting Projects Cost Overrun on Real Estate Construction Projects the Case of Addis Ababa City. Specifically the study aimed at testing the relationship between the independent variables (owner related factor, economic factor, consultant related factor, factor related to contractures and Timeliness and financial factors) and the dependent variable (Projects Cost Overrun). This research was used both descriptive and explanatory research design because it enables the study to clearly investigate the characteristics and nature of the study undertaken and the cause and effect relationship with explanatory and dependent variables of the study. The target populations of the study are all contractors, consultants, clients of the Real estate construction projects in Addis Ababa making a universe of 557 to which 182 were sampled. The selections of respondents were made using stratified sampling technique. The data obtained were analyzed using quantitative and qualitative analysis techniques. Both descriptive and inferential statistics were used to see the factor affecting of projects cost overrun and following that logistic regression analysis were done. The result indicates that financial factor, owner-related factor and factor related to contractor had the greatest influence on the project cost overrun under study as the influence was significant at 5% level of significance. Based on the findings, it recommended that  real estate project owners use strong auditing procedures and mechanisms of controlling financial diversion, they also give more emphasis on decision making and adequate budget management to make sure that the financial resource are used for the intended purposes, team work must required with the owner of project and others  parts to exchange every additional cost and change of plans, the way of resource utilization and management  which also likely to costs minimization and set proper feedback channels.

Keywords: project cost overrun, real estate construction project, economic factor, contractor related factor, financial, owner and consultant related factors.

CHAPTER ONE

INTRODUCTION

1. Background of the Study

The construction industry is truly the engine of national economy through which the total of physical development is achieved. The construction industry is a vital element of the economy and has a significant effect on the efficiency and productivity of other industry sectors. One cannot think of widespread investment in manufacturing, agriculture, or service sectors unless the construction results of infrastructure facilities are in place. In some of the developing countries, the growth rate of construction activity outstrips that of population and of GDP (Chitkara, 2004).

In addition, construction industry is an important industry that plays a vital role in the socio-economic growth of a country. Economically, it contributes in significant improvement in the overall GDP of a country. It also improves the quality of life by providing the necessary infrastructure such as roads, hospitals, schools and other basic and enhanced facilities. Hence, it is fundamentally crucial to make construction projects completed successfully within time, budget and expected quality. However, being a complex, fragmented and schedule driven industry it always facing chronic problems such as low quality and productivity, cost overrun, time overrun, construction waste and others. Of these, cost overrun is a severe problem (Cantarelli, 2009, Olawale and Sun, 2010) because it affects the overall development of any country.

Infrastructure is the backbone of economic development for any country (Prasad et al, 2019). Many governments have invested huge amounts of capital in infrastructure projects and programs in order to contribute to socio-economic development of their country (Andric et al, 2019). In fact, the construction sector plays a central in the economy of any country, providing essential structures such as private and public infrastructure and housing (Kirchberger, 2018).

Cost is the fundamental component for any construction project. However, cost overrun is observed as one of the most frequently occurring issues in construction projects worldwide and need to be more studied to alleviate this issue in the future (Memon, A. et al., 2010).

Cost overrun is a global phenomenon in the construction industry where very rarely projects are finished within the budgeted cost. In a global study on construction project performance, cost overrun was identified the major problem where 9 of 10 projects faced the overrun in the range of 50 to 100%. The problem of cost overrun in the construction industry is a global phenomenon (Ameh et al. 2010).

Many factors are responsible for these cost overruns such as underestimation of costs to make the projects more viable, addition of scope during later stages of project planning and even during construction, changed conditions, etc. One of the most important contributing factors to the magnitude of cost overrun in large transportation projects are project delays. Furthermore, the length of project development phase from planning to construction seems to be a major factor in the extent of cost overrun.  Cost is the fundamental component for any construction project. However, cost overrun is observed as one of the most frequently occurring issues in construction projects worldwide and need to be more studied to alleviate this issue in the future (Memon, A. et al., 2010).

In addition, in construction project is an indication of project failure so, the key to success is to realize and understand the challenges early in the planning process, to develop strategies to address them and to establish accurate and achievable expectations. Moreover, it provides the decision makers with early warning devices to reduce the cost overrun problems. So, understanding these factors allows for appropriate actions to mitigate factor impacts. Project participants can take action to curtail or control the effects of these identified cost escalation factors throughout the life of the project. Indeed, cost overrun occurs due to many factors that differ from one country to another. (Memon, A. et al., 2010)

Cost is undoubtedly the most important concern in any business endeavor, not at least in the construction industry (Bari et al, 2012). The demand for more construction of all types, coupled with a tight monetary supply has provided the construction industry with a big challenge to cut costs (Ikechukwu & Akiohnbare, 2017), hence the need for well – informed cost estimation. Estimating, as noted by Tyler (2004); is an art, not science because there is no estimate that fits all work. In fact, many past researchers perceived that qualitative factors including project complexity, project team requirement, contract requirements and market requirement (Elinwa & Buba, 1993; Akintoye, 2000; Chan & Park, 2005) have a higher impact on the total project compared to quantitative factors such as gross external floor area, median floor height and construction duration (Stoy & Schalcher, 2007; Stoy et al, 2008). Poor cost performance has become a major concern for both contractors and clients (Xiao & Proverbs, 2002; Memon et al, 2010). Realizing and understanding cost – determinants will enrich the cost estimator’s competence, hence, adequately delivering a more sustainable and reliable cost modeling and estimating technique (Elhag et al, 2005).

In addition, in construction project is an indication of project failure so, the key to success is to realize and understand the challenges early in the planning process, to develop strategies to address them and to establish accurate and achievable expectations. Moreover, it provides the decision makers with early warning devices to reduce the cost overrun problems.

Cost is the fundamental component for any construction project. However, cost overrun is observed as one of the most frequently occurring issues in construction projects worldwide and need to be more studied to alleviate this issue in the future (Memon, A. et al., 2010).

1.1 Statement of the problem

The inability to complete projects on time and within budget continues to be a chronic problem. Thus, cost overrun occurs when the final cost of the project exceeds the original estimates.  A cost overrun is the increase in the amount of money required to construct a project over and above the original budgeted amount. Cost overruns on construction projects are a universal phenomenon.  The trend of cost overruns is common worldwide and that it is more severe in developing countries, like Ethiopia (Azhar and Farouqi, 2008). There are a number of researches about factors affecting project’s cost overrun in construction projects in several countries (developed and developing countries), as follow

Cost control is considered as one of the key success indicator of any construction project among three iron triangle; cost, time and quality (Azhar et al.; Elhag et al. 2005; Enshassi et al. 2009; Hammad et al. 2008; Umar Isma’il et al. 2013). The causes of cost overruns in construction projects are varied, some are not only difficult to predict but also difficult to manage. However, the major cause of cost overrun in many projects is ineffective construction management and poorly established cost control systems (Endut May 2008). This factor depends on individual organizations understanding of project management “Projects that are not managed effectively experience many cost overruns” (Chileshe and Berko 2010).

Roachanakanan (2005) examined project cost controls in the United States and Thailand, as well as the causes and solutions for cost overruns in the two countries also are examined. Flyvbjerg et al. (2004) presented results from the statistically significant study of the causes of cost escalation in infrastructure projects of different nations. According to Frimpong et al. (2003) major  cost overruns occur during the project implementation phase; therefore, in their studies factors such as, monthly payment difficulties, poor contractor management, material procurement, poor technical performances and escalation of material prices were examined in construction of groundwater projects in developing countries. Other studies (Datta 2002; Mansfield et al. 1994; NAP 2003; Schexnayder et al. 2003) identified cost escalation to be a result of problems such as delay in land acquisition, unexpected problems in supply of raw materials, illegal encroachment on land even during project implementation, or due to internal problems in government organizations.

Azhar et al. (2008) found the top ten cause of cost overrun in Pakistan are; fluctuation in prices of raw materials, unstable cost of manufactured materials, high cost of machineries, lowest bidding procurement procedures, poor project (site) management/ poor cost control, delays between design and procurement phases, incorrect/ inappropriate methods of cost estimation, additional work, improper planning, and unsupportive government policies.

Dissanayaka and Kumaraswamy (1999) found procurement related factors as major cause cost overrun in Hong Kong building projects. Kaming et al. (2010) identified factors, which cause cost overrun in Indonesia, which include material cost and inaccurate material estimating. Endut May (2008) identified the five highest factors which cause cost overrun in Malaysia; changes in building codes was a most critical factor.

Ramabodu and Verster (2010) identified that changes in the scope of work on the site are critical factors, which cause cost overruns in South Africa construction. Although, cost overrun can be caused by several reasons a comprehensive analysis of factors associated with the construction cost overrun in post-contract context need to be performed (Doloi 2013).

Ekab, (2009) mentioned that poor review of drawings and Changes in design is the most influencing factor in cost overrun of construction projects in Iraq then, poor contracts management and fluctuation in material prices.

Gajewska, and Ropel, (2011) stated that the delay in diction making, miscalculation, and not finding the right contractor are the most influencing factors of delay the construction projects which leading to cost overrun occurrence in Sweden. In addition, Memon et al, (2011), Toh et al, (2012) and Abd-Karim et al, (2013) mentioned that client requirements on quality, poor design and delays in design, unrealistic contract duration and requirements imposed lack of experience, late delivery of materials and equipment, relationship between management and labor, fluctuation of prices of materials, cash flow and financial difficulties faced by contractors and shortages of materials are the most influencing factors in cost overrun in Malaysia. In Malaysia, a study investigated large projects and found that cash flow and financial difficulties faced by contractors, contractor's poor site management and supervision, inadequate contractor experience, shortage of site workers, incorrect planning and scheduling by contractor were most severe factors while changes in scope of project and frequent design changes are least affecting factors on construction cost (Memon AH et al., 2010).

Based on the above previous study the seeds of present study are attempted to find major influencing factors or bottlenecks that affect the occurrences of cost overrun in construction project. It is believed that the challenges for cost overrun was indicated socio political factor due to political interference and instability, economic factor due to economic instability, exchange rate fluctuation, fluctuation in raw material price, managerial factors due to delays in decision making process, poor project management leadership style and owners interference, construction techniques and design factor due to frequent design change, design error and mistakes, incomplete design at the time of tender, deficient design and delays in design process and risk management strategy and time lines of payment and financial factor due to delay in progress payment by clients, poor financial control on site was identified as causes of cost overrun in public construction project. To facilitate the present study, the researcher examined the factors that lead to cost overrun in public construction project.

The researcher intention here was to investigate the Factor Affecting Projects Cost Overrun on Real Estate Construction Projects. To the knowledge of this researcher Most of the empirical studies was focused on public sectors (which controlled by concerned government bodies), this implies that construction material are provided by the government at certain fixed unit rate which makes it completely different from the private run projects and although, there is no recent research has been done on Factor Affecting Projects Cost Overrun on Real Estate Construction Projects in Addis Ababa City. Therefore this research would clearly discuss about the cause of project cost overrun, their aggregate effects on different sectors, and resolution methods in construction projects.

As a result the researcher believes that dealing with the Factor Affecting Projects Cost Overrun on Real Estate Construction Projects, would worth discussing issue and this paper was mainly focused on Factor Affecting Projects Cost Overrun on Real Estate Construction Projects in Addis Ababa City.   The study attempted to fill the gaps stated in the aforementioned paragraphs. It looks in to the details of projects cost overrun, problems encountered and suggestions in improving the problems and challenges faced by the contractors.

1.2. Research Questions

A research question is a question that a study or research project aims to answer. This question often addresses an issue or a problem, which, through analysis and interpretation of data, is answered in the study’s conclusion.

1. What are the economic factors affecting cost overrun on real estate construction projects in       Addis Ababa city?

2. What is the financial factor that cases cost overrun on real estate construction projects in Addis Ababa city?

3. How are the contractor and consultant related factors affecting cost overrun on real estate   construction projects in Addis Ababa city?

1.3 Objectives of the study

1.3.1 General Objective

The general Objective of the study was identifying factors affect projects cost overrun on Real Estate construction projects in Addis Ababa City.

1.3.2 Specific Objectives

The specific objectives are directly related to the general objectives, detailing the processes necessary for their realization. In this way, the specific objectives serve as a guide for how the work will be approached. The specific objectives should present in detail the goals of the project. This is how the object studied is related to its particularities and the steps to be followed to meet the general objective are identified. The specific objectives of the research are as follow:

1. To determine economic factors affecting cost overrun on real estate construction projects in       Addis Ababa city.

2. To identify the financial factor that cases cost overrun on real estate construction projects in Addis Ababa city.

3. To examine contractor and consultant related factors affecting cost overrun on real estate   construction projects in Addis Ababa city.

1.4. Significance of the study

The study intended to the factors affecting project cost overrun in the real estate construction projects. The result of the study was the guideline to the parties or concerned bodies that involve in the sectors, so that it was help to suggest several factors that will avoid the cost overrun in construction projects. The factor can be study for the organizations that involve in construction to reduce the risk of cost overrun in construction project and to study the effect of the cost overrun in construction projects. The finding of the study was help as an input for policy makers to make clear and timely discussions on the construction sectors. The study was also important to the researcher as it add theoretical and practical knowledge on how to conduct research. The study was significant to scholars and researchers in other higher learning institutions who require basis for further research in this area.

1.5. Scope of the study.

The scope of this study is limited to Factor Affecting Projects Cost Overrun on Real Estate Construction Projects: the Case of Addis Ababa City. These studies were concentrated on only among the real estate Constriction project plc in Addis Ababa city, particularly on mostly large real estate projects in Addis Ababa.

The researcher believes that there were many problems that need research or investigation in real estate construction areas. However, the studies were particularly interests to evaluate the Factor Affecting Projects Cost Overrun on Real Estate Construction Projects: the Case of Addis Ababa City. It is concerns in areas of Factor Affecting Projects Cost Overrun on Real Estate Construction Projects: the Case of Addis Ababa City but does not include the public construction. Hence, the studies were confines to the real estate constructions, which are geographically limited in the Addis Ababa city.

1.6 Limitations of the Study

The purpose of this study was limited to investigate the Factors affecting projects cost overrun on Real Estate only that located in Addis Ababa city and currently top five projects. The study faced the following limitations: although the study employed different data quality control measures to get accurate information, the majorities of respondents hesitate and failed to give accurate information. Another problem faced the researcher during the gathering data was unavailability of the respondents heads in their office and project area during the survey day time and some respondents delayed to respond the question paper on the requested time. Generality of the independent variables that affects projects cost overrun on Real Estate  and the limitation of similar literature because there was no similar study in the area on the topic were the other problems that restricted the researcher during the study.

1.7. Organization of the paper

The study was organized in to five chapters where the first chapter gives an explanation on background of the study, statement of the problem, general and specific objectives of the study, Research question, significance of the study, scope study, and limitation of the study and Organization of the paper. The second Chapter explains review of related literatures and Theoretical review, Conceptual review and Empirical findings by different authors. The third chapter was  present the background of the organization, research design, research approach, data source and type, target population, sample size, sample techniques, data collection techniques, method of data analysis, ethical consideration. Whereas, the fourth chapter was presents findings of the study and discussion; and finally, the fifth chapter presents the conclusion of study findings and recommendation for concluded problematic areas

CHAPTER TWO

REVIEW OF RELATED LITERATURE

2. Introduction

Under this section, Concepts, theories, dimensions regarding construction project cost overrun and its effects on the projects or cost overrun carried out by various researchers are discussed. This chapter was discussing the areas by categorizing on theoretical and empirical review sections to make clear about the areas which the study focuses.

2. Theoretical Review

2.1 Cost Overrun in Construction Industry

Cost is the common factor of any construction project. However, cost overrun is one of the most occurring risks construction projects and the most severe in developing countries, where these overruns sometimes exceed 100% of the estimated budget (Memon, A et al., 2010). Construction cost which is out of control adds investment pressure, increases construction cost, affect investment decision making. Hence, it is important to identify the factors that contribute to cost overrun to avoid and reduce the problems (Ali, A. & Kamaruzzaman, 2010). This part of the thesis focuses on theoretical approaches to examine the approaches and techniques as tools towards private construction plc. Additionally, related studies, a review of books, thesis, standards and relevant guidelines are reviewed.

A project is a sequence of unique, complex, and connected activities that have one goal or purpose and that must be completed by a specific time, within budget, and according to specification. Project management is an organized commonsense approach that utilizes the appropriate client involvement in order to meet sponsor needs and deliver expected incremental business value. Projects arise out of unmet needs. Those needs might be to find a solution to a critical business problem that has evaded any prior attempts at finding a solution.  Construction project is a mission, undertaken to create a unique facility, product or service within the specified scope, quality, time, and cost (Chiittkara, 2004).

In practice, however, some construction projects encounter cost overrun, delay on completion time or poor Workmanship upon completion. Cost overrun, poor quality workmanship and delay of construction projects require an in-depth investigation to improve the outputs of the construction industry. Cost overrun is common in infrastructure and building construction projects. Researches on construction projects in some developing countries indicate that by the time a project is completed, the actual cost exceeds the original contract price by about 30 % Alla- Momanii (1996].

### 2.1.1 Concepts of Real estate development

### The term real estate can be defined as, the private ownership of a limited parcel of land, which includes the right of the air above it and the ground below it, and any buildings or structures attached to the ground (Miles, 2007). Real estate can exist in the form of business and/or residential properties, which can be sold or either by a relatives or directly by the individual who owns the property.

### Ownership of land is considered as a real property that has sale or transfer right granted by law. Yet, the principle of sale or transfer follows the land policy regulated by the government of a specific country.  Real estate also; “space delineated by man, relative to a fixed geography, intended to contain an activity for a specific period of time. To the three dimensions of space (length, width and height), then, real estate has a fourth dimension – time for possession and benefit. This is referred to as space-time characteristic.” Residential real estate refers to capital investments in the development of land and housing for purposes of occupancy by households. Real estate investments offer two forms of return; capital gain and rental income. Capital gain is realized from appreciation of the asset value, in this case, value of the land or housing units built on the land. Rental income is represented by cash inflows from the users of the real estate (Yang and Ye, 2010).

### According to Geissler (2008) the term is artificially delineated space referenced to a fixed point on the surface of the earth with a fourth dimension of time. It is built to house an economic activity that is subject to cultural preferences and restricted by the public infrastructure. Real estate includes entities such as residential homes, raw land, and a variety of forms of income property, including warehouses, office and apartment buildings, and condominiums.

### Considering the similarity, all the authors define real estate as land that is identifiable and tangible. They further included all fixtures, improvements and buildings that are permanent to the land are to be considered as real estate.

### 2.1.2 Construction management in Real estate

### Real estate is often defined as a triangle of space, money and time. In this sense a particular usage is attributed to a defined space which generates an estimated cash flow over a specific period of time. Based on this understanding of real estate, the definition of development postulated by Graaskamp (1992, p. 620) “(...) the creation and management of space time units is termed as real estate development” is applicable. This definition primarily makes reference to the economic benefit derived from the space produced by the developer.

### The definition of the Urban Land Institute, as formulated by Miles / Berens / Weiss (2000, p. 4), also refers to the management and entrepreneurial aspect of real estate development: “Development is an idea that comes to realization when consumers – tenants or owner occupants - acquire and use the bricks and mortar (space) put in place by the development team. Land, labor, capital, management, and entrepreneurship are needed to transform an idea into reality. Value is created by providing usable space over time with associated services.”

### Efficient project management strategies & the construction industry is commercial domain of building and construction has attained significant prominence in the recent times. As such, this sector deals with huge amount of money and thus, stakes in this line of business is much higher. Any construction project invariably comes with certain constraints. These constraints include an estimated costing and a fixed deadline. Stakeholders of a project have to ensure these predetermined factors do not get skipped at any cost. Along with these estimations, one has also to ensure superior quality of construction work to a project. However, at the implementation level it seems most challenging to maintain this cost estimation and the deadline. As such, scores of unforeseen adversities crop up revolving any construction job almost every now and then. This string of adversities either withholds the work or delays the work progress. One has to resolve all these challenges as early as possible in order to complete a project successfully. In this situation, the aspect of project management has become crucial for obvious reasons. The concept, as such, deals with organizing and managing resources with an efficient approach. As such, the resources include both labor and materials, which are essential in the building and construction sector. Thus, in other words, the aspect of management in construction industry ensures timely and successful completion of a project perfectly in the way it was expected Weiss EL, et al. (2000).

### Professionals involved in the domain of construction management require resolving the unforeseen issues in one hand, while on the other they require identifying the potential adversities beforehand. To put it in simpler words, the aspect of project management in construction is undoubtedly challenging. Professionals involved in this vocation require knowing all the relevant dimensions of a construction project. Moreover, they require keeping themselves promptly updated about all minute developments occurring in a project. This information helps them to take better decisions to resolve unforeseen challenges and adversities. The fraternity of project management services shoulders a host of relevant responsibilities. Starting right from finding ideal site for project owners to successful completion of the construction project, the fraternity leaves no stone unturned, to shoulder their responsibilities Weiss EL, et al. (2000)

2.1.3 Factors Leading to Cost Overrun in Construction Projects

There are many factors causing of project cost deviation in other words, causes of variations between estimated cost or planned cost (PC) and actual cost (AC) of project which will be explained in details later. Hence, the researcher reviewed a lot of studies concern with the causing factors of cost overrun in private construction projects. Many studies show that 90% of construction projects have underestimated costs and this percentage increases in the developing countries because of the lack of experience in the project management process. So, there are many factors can cause cost overrun that are different from one project to another and from one place to another. Cost overrun will be identified, its reasons will be clarified, and many of previous studies will be analyzed (Ammar, M. et al,. 2009).

A cost overrun, also known as cost increase or budget overrun, involves unexpected costs incurred in excess of budgeted amounts due to an underestimation of the actual cost during budgeting. Cost overrun should be distinguished from cost escalation, which is used to express an anticipated growth in a budgeted cost due to factors such as inflation.

2.1.3.1 Factors related to contractor

Among all the construction parties, a contractor has the major responsibility to carry out most of the project activities. Similarly, if the project is not finished on time and within the allocated budget then the contractors is blamed. In reality, the contracting business is a challenging and demanding profession that contains many complex activities, and, to avoid project cost overrun, the main contractor often holds full responsibility for the work of sub-contractors as well as his own. Basically, how the contractor deals with particular situations depends on the nature of the work and the type of contract (Shi & Arditi, 2001).

The capability of the contractor to finish the project according to the planned schedule and given budget mainly depends on two things: availability of resources (incorporating money, manpower, materials, and equipment and machinery) and managerial competence. There are two types of sources from which the contractor hires manpower: sub-contract and direct hire. If the sub-contractor causes delay to the construction project then both the owner and the main contractor have the responsibility to look for a solution to the problem. Therefore, it is essential for the contractor to constantly supervise the work performance of sub-contractors in order to maintain a balance between construction activities (Abdul-kadir & Price, 1995).

Materials

Materials are one of the imperative components of any construction project and also the major expenditure for the owner. From the contractor’s perspective, on-site management of materials is just one side of the picture. In reality, material procurement planning is vital for the contractor at the initial planning stages of the construction project (Abdulrahman & Alidrisyi, 1994).

The failure to produce a proper procurement plan, or poor material handling by the contractor, may result in delays and many other problems such as the theft or deterioration of materials. According to Odeh & Bataineh (2002), the timely flow of materials is a vital responsibility of the contractor because in case of unavailability of materials additional expenditures will increase the cost of the construction project.

Koushki et al (2005) highlight another key aspect regarding material prices. According to them, an increase in material prices may sometimes hinder the owner’s decision to acquire more materials, especially in the case of large building projects where rises in prices make a real difference. The decision to wait for a fall in material prices is crucial, because it may lead to increase in final cost of the construction project.

Equipment

Construction equipment and machinery are used to perform repetitive tasks and operations. According to the function, the equipment used in the construction sector can be classified into two fundamental categories: operators and haulers (Abdulaziz & Michael, 1998). Operating equipment includes cranes and graders which can be left within the boundaries of the construction site, whereas haulers are dump, trucks, and other transportation equipment which is usually used to shift the materials to and from the construction site (Odeh & Bataineh, 2002). The equipment can either be hired or purchased by the contractors, depending on the frequency of their intended usage (Kwakye, 1997).

Some of the basic responsibilities of the contractor regarding the acquisition of equipment are selection of suitable equipment type, on-time delivery, proper maintenance, and prevention from damage. The project may face slowdowns in the construction processes if the contractor fails to fulfill his responsibilities regarding equipment. AbdMajid & McCaffer (1998) opine that the selection of equipment by the contractor is very important for making an effective project plan, because a shortage or unavailability of equipment may badly disrupt the project schedule and final cost.

2.1.3.2 Economic Factors

Chism and Armstrong (2010) confirm the fact that the political environment affects the construction of a project. Fortune and White (2014) in their review of sets of critical success factors in sixty-three publications listed political stability as one of the twenty-seven critical success factors. Wideman (1986) assert that changes in government actions are a major external risk factor militating against the success of projects. Economic environmental considerations refer to the level of general economic activity and resources available to carry out construction.

Memo, Rahman and Azis (2012) investigated the variation and claims in construction projects in Dubai and Abu Dhabi in the United Arab Emirates using 124 claims related to can be little more specific the range of the projects or typical project. He concluded that 1) a reasonable time should be allowed for the design team in order to reduce clear and complete contract documents with no or minimum errors and discrepancies; 2) efficient quality control techniques and mechanisms need to be established to minimize errors, mismatches, and discrepancies in the contact documents; 3) special contracting provisions and practices need to add in contract document and a strategy needs to introduce to deal with tighter scheduling requirements.

Alaghbari (2014) found several causes of delay in Saudi construction projects and they are drawing preparation, approval of design, payment delay, changes in design, slow cash flow, design errors, labour shortage.

### 2.1.3.3. Consultant-related factors

### The client may consult with other professionals who can assist him in organizing the entire construction project. These professionals are called consultants. The main duties and responsibilities of a consultant may be to design the infrastructure of the project, which includes architectural, mechanical, structural, and electrical designs. Some other responsibilities may include the preparation of project related documents such as bills, drawings, specifications, and tender documents (Long et al, 2004). Furthermore, in some cases, consultants also conduct project planning, cost control and estimation, and quality control.

### In normal circumstances, consultant-related delays occur during preparation of drawings, during the adoption of design drawings, while taking design approvals from contractors and client, and when performing inspection procedures. There are many possible reasons behind these types of cost overrun; prominent factors include inexperienced consultancy staff, poor qualifications, inadequate communication and coordination skills, and improper planning (Gunlana & Krit, 1996). Odeh & Battaineh (2002) believe that during the construction processes, the enquiries and inspections of the consultant may slow down the progress of the work. In response, the contractor may come up with solutions to the problems; however, these solutions may not satisfy the consultant, and could result in the work having to be redone. Effective control and command over production on the0 construction site is a major element that contributes to the success of implementing the project; conversely, hindrances in performing these activities can have severe impacts on a construction project.

### 2.1.3.4. Owner-related factors

### The owner or client is the key participant during the entire construction process. Kwakye (1998) mentioned that the owner’s duties and responsibilities are onerous, and that he or she needs other knowledgeable parties to manage or organize the construction project. In a few cases, owners have in-house project management teams that participate in the construction process, but most of the time, owners hire a project manager and external parties to handle the project (Odeh & Battaineh, 2002).

### One of the most crucial decisions that owners need to take at the beginning of the project is to determine the duration of the contract. Many owners prefer fast completion of work but thorough investigations should be conducted to decide the contract duration. Another major factor that delays the initialization of the project is the owner’s failure to hand over the site to the contractor. Therefore, the personal involvement and quick decision-making on various matters by the owner in the initial phases of the project may accelerate the project’s progress. Kimmons & Loweree (1989) observed that “the working relationship between an owner and a contractor is one of the most crucial determinants of project success and this relationship also develops trust between the two parties”. The owner must participate in the construction project horizontally and vertically, but without interrupting the contractor’s project plan. In addition, financial matters should also be taken into account, and the owner must ensure the on-time availability of funds; lack of financial stability may cause many problems, such as extensive delays due to labor strikes or material mismanagement (Chan & Kumaraswamy, 1997).

2.1.3.5 Timeliness of Payment and Financial Factors

A common issue in worldwide construction companies is to complete projects both on time and within the budget initially planned. The completion of projects in a timely manner is often a critical factor and measure of project success. In recent years, there has been an increasing interest in the use of projects as building blocks in the strategic management of organizations (Weiss & Potts, 2012). The success of any project is highly dependent on its completion time and cost from start to delivery of results. This has a direct bearing on management decisions such as budgets, targets and standards (Seddon, 2008).

Al-Tabtabai (2002) conducted a study on causes of delays in construction projects in Kuwait and found out that the major causes of delay were: Slow financial and payment procedures; Slow decision-making process; Limited authority among supervision staff; Risk allocation mainly on the contractor; and Lack of design drawings coordination. Memon, Rahman and Azis (2012) conducted a study on time and cost performance in construction projects in Malaysia and revealed that only 21% of public sector projects and 33% of private sector projects were completed within time.

### 2.1.4 Cost overrun

The problem of cost overrun, especially in the construction industry is a worldwide phenomenon and its ripples are normally a source of friction among clients, Consultants and contractors on the issue of project cost variation. Project cost overruns create a significant financial risk to clients. However, in spite of the risks involved, the history of the construction industry is full of projects that were completed with significant cost overruns (Garry, 2005).

Angelo and Reina, (2002), stated that cost overrun is a major problem in both develop and developing countries. Several studies of major projects show that cost overruns are common. The causes of cost overrun in construction projects are varied, some are not only hard to predict but also difficult to manage [Morris and Hough, 1991]. According to a study made in Turkey by Arditi, et al, (1985), the important sources for cost overruns were found to be inflationary pressures, increases in material prices and workmen's wages, difficulties in obtaining construction materials, construction delays, deficiencies in cost estimates prepared by public agencies and unexpected sub soil conditions were the most important sources for cost overruns.

Kaming, et al, (1997), studied the factors influencing construction time and cost overruns for high-rise projects in Indonesia, and pointed out that the major factors influencing cost overrun were material cost increase due to inflation, inaccurate material estimating and the degree of project complexity.

Fetene (2008) this research was done on cause and effects of cost overrun on public building construction in Ethiopia. This research was carried out to dig-out information on the factors that cause cost overrun during construction and their effects on public building construction projects in Ethiopia. Questionnaire survey together with desk study was used to collect data on cost overrun. A total of 42 questionnaires from clients, consultants and contractors were collected and a desk study of 70 completed public building construction projects in Ethiopia were investigated and analyzed using both descriptive and inferential statistics. From the results it was found that 67 out of 70 public building construction projects suffered cost overrun.

The rate of cost overrun ranges from a minimum of 0% to the maximum of 126% of the contract amount for individual projects. In this research it was found that the rate of cost overrun decreases with the increase in contract amount. Respondents identified 39 causes of cost overrun for Ethiopian case. The most important causes of cost overrun were found to be inflation or increase in the cost of construction materials, poor planning and coordination, change orders due to enhancement required by clients, excess quantity during construction. Spearman rank order correlation analysis was used to evaluate whether consensus of opinions exists between groups of respondents (client versus consultant, client versus contractor and consultant versus contractor). From the analysis of the results it was found that consensus of opinion exists between respondents on the factors that cause cost overrun and on their rate of occurrence. The most common effects of cost overrun identified by this research were delay, supplementary agreement, adversarial relations among stakeholders, and budget shortfall of project owners. It is hoped that these findings will guide efforts to improve the performance of the construction. This study was carried out to examine causes and effects of cost overrun on construction projects in Bahrain. Cost performance is one of the basic criteria for measuring construction project success. Despite its proven importance it is not uncommon to see a construction project failing to achieve its objectives within the specified cost. The paper attempts to identify the major causes of cost overrun in Bahrain construction sector, and to assess the effect of these causes on cost overrun. In total 45 factors were short-listed to be made part of questionnaire used in a survey conducted with representatives from local contracting, consulting, and client firms. Findings are presented in form of tables that classify cost overrun factors, and their ranking. The overall results showed that frequent design changes, mistakes during construction, and schedule delay were considered as the most important factors of cost overrun causes in Bahrain construction industry. The results obtained indicate that the top major causes of delay were; fluctuation of prices of construction materials, shortage of materials, inaccurate time estimation, and errors during construction. In addition the top major effects of delay were; Cost overrun, acceleration of losses, time overrun, negative social impacts and litigation. Also the top major risks associated with construction delay were; too much pressure on project stake holders, price inflation of materials and overall project, disputes amongst project participants, project  abandonment,  overall cost increase and decline in revenue. And finally the top major delay mitigating measures were; Information sharing, Total Quality Management (TQC), Quality cycles, Benchmarking, and Joint risk management Abusafiya (2017).

Mansfield, Ugwu, and Doran, (1994), found that cost overrun is attributed to problems in finance and payment arrangements, poor contract management, material shortages, changes in site conditions, design changes, mistakes and discrepancies in contract documents, mistakes during constructions, price fluctuations, inaccurate estimating, delays, additional work, shortening of contract periods, and fraudulent practices and kickbacks. Stewart, (1982), attributes cost overruns to several factors that are either not controllable or that to a varying degree are unmanageable. They include the accuracy of original cost estimate, degree of government regulation and control, construction completion delays, number of design changes, and labor related matters such as their availability, skills, and increases in fringe benefits.

According to Robert F. Cox,, (2007), project owners identified five reasons for project cost Overruns: these reasons were,, incomplete drawings,, poor pre-planning process,, escalating cost of materials,, lack of timely decisions and excessive change orders..According to User’s Guide,, (2005),, the following are the factors that change the cost of the Construction projects through time:: poor project management,, design changes,, unexpected Ground conditions,, inflation,, shortages of materials,, change in exchange rates, Inappropriate contractors,, funding problems and force majeure..In developing countries the lack of proper phasing of construction projects can contribute to the economy to become ‘overheated’.. This leads to shortage of construction materials as the demand will exceed the supply,, this in turn leads to a climb in the cost of construction Materials;; this inevitably gives rise to project cost overruns,, with consequential effects on Inflation and a decline on efficient activity in the construction industry [Mansfield,, Ugwuand Doran,, 1994].

According to Jahren, et al, (1990), on their research on predictors of cost overrun rates they found the following factors to influence the cost overrun rates; the size of the project, the difference between lowest bid and engineer’s cost estimate, the type of delivery method, the level of competition, quality of contract documents, and the nature of in personal relations on the project. Studies have shown that the size of a construction project influences the rate of cost Overrun. Large projects are generally more complex,, and in complex projects some items are fraught to be missed out or may be forgotten during planning and design stages hence the complexity may increase the rate of cost overrun. However, since takes are higher on larger projects, more care may be exercised from conception of the project until completion. Review of some literatures indicates support for both of the second flicking views. Randolph, ett all, (1987), found that cost overrun rates decreased as the contract amount increased, while Rowland, (1981), found that cost overrun rates increased with increase in the contract amount of construction projects.

The problem of cost overrun, especially in the construction industry, is a worldwide phenomenon, and its consequences are normally a source of argument among clients, consultants and contractors on the issue of project cost variation. Project cost overruns create a significant financial risk to clients. In the study made by Ahady, et al. (2017) stated that, In the past several decades, construction industries of many countries have faced the issue of cost overrun, though it is commonly acknowledged, the causes subject to more debate. The most important problem which led to the construction cost overrun in developing countries is fluctuations and increases in material price. Although all the factors are not similar to every project but most factors such as poor management, inaccurate material estimates and financial status of the contractor are common to the projects in the developing countries. More over on his research “A study of the causes of cost overrun in construction industry in Afghanistan”: also identified the frequency of experience of cost overruns in the construction projects in Afghanistan and the survey result indicated that 6 out of 10 projects fall into this category. According to Niaza, et al. (2016) Due to various factors, cost overrun is often more of a challenge in developing countries where budget problems are just one factor in often poor project performance.

### 2.1.4.1 Cost overrun in Ethiopia

Based on the construction type and scope, level of development, weather condition of the countries and other different factors the magnitude of cost overrun varies from one country to the other in extreme manner. As an example: Mehamid, et al. (2013) Stated that the average cost overrun in Palestine construction is between 10%- 30% of the project’s estimated cost. Different researchers have specified different percentage for the magnitude of cost overrun in Ethiopia based on the study area. Merid (2016) has studied to see the effect of Time and Cost Overruns on Ethiopian Construction Projects that are performed by Defense Construction Enterprise.

They found that cost overrun ranges from a minimum of 1% to the maximum of 47% of the contract amount. Turkey, (2011) confirmed that from the desk study: the average cost overrun was found to be 26.95% of the contract amount, the actual cost overrun ranging from -32.8% to 230.54%. The result of the questionnaire survey also strengthens this finding; it indicated that the perceived average cost overrun was found to be 34.18% of the contract amount found that in federal road construction projects.

Another study was conducted by Belachew (2017) to identify the causes of cost overrun in Federal Road Projects of Ethiopia. According to the research, the degree of cost 25 overrun among selected project lengthened from 4.16% to 83.2%. the average magnitude of cost overrun was nearly 21.52% based on the three major construction parties (client, consultant, and contractor) and the principal factors that affect project cost performance were investigated. Lack of training, benefit realization and production supports were the primary reason for cost overrun at the execution processes of the projects as per clients’ perception while lack of training, implementation process or bureaucrat and benefits realization were the primary reason for cost overrun at the execution processes as per contractors’ perception.

Abubeker (2015) confirmed cost overrun problems of Addis Ababa road projects by using Questionnaire survey and desk study: the researcher found that 100% of the road construction projects suffered both time and cost overrun. The rate of time overrun ranges from a minimum of 25% to the maximum of 264.38% of the contract amount and cost overrun ranges from a minimum of 4.11% to the maximum of135.06% of the contract amount. For this topic there is one good research in our country entitled: causes and effects of cost overrun on public building construction projects in Ethiopia, which is conducted by Fetene (2008), he explained that, from the results it was found that 67 out of 70 public building construction projects suffered cost overrun. The rate of cost overrun ranges from a minimum of 0% to the maximum of 126% of the contract amount for individual projects. In this research it was found that the rate of cost overrun decreases with the increase in contract amount. The respondents identified 39 causes of cost overrun for Ethiopian case. The most important causes of cost overrun were found to be inflation or increase in the cost of 26 construction materials, poor planning and coordination, change orders due to enhancement required by clients, excess quantity during construction.

2.2. Empirical Reviews

There are a number of researches about factors leading to cost overrun occurrence in construction projects in several countries (developed and developing countries), as follow. However, it should be performed more such studies in developing countries, in particular Egypt to face the critical problem of cost overrun in construction field. Past researchers studied the factors affecting construction costs from various perspectives. However, different countries have different cost factors for consideration. After the literature review, the researcher extracted the following facts:

Whereas Whereas, Ekab, (2009) mentioned that poor review of drawings and Changes in design is the most influencing factor in cost overrun of construction projects in Iraq then, poor contracts management and fluctuation in material prices.

According to Bageis and Fortune.(2009) and Alfouzan, (2013) that there are many factors lead to cost overrun in construction projects in KSA as Decision-making regarding tenders which depend on the size of contractor, contractor’s classification status and type of main client, corruption in selling lands and government’s poor role in monitoring materials prices.

Whereas, Zujo et al. (2010) the main only factor causes cost overrun in Bosnia and Herzegovina is the delay in projects handing over. In addition, Ameh et al. (2010) extracted that the junior factors cause cost overrun in Nigeria are the economic stability, shortage of materials, government policies (laws and regulations), domination of construction industry by foreign firms and aids, project location and absence of construction cost data.

Gajewska, and Ropel, (2011) stated that the delay in diction making, miscalculation, and not finding the right contractor are the most influencing factors of delay the construction projects which leading to cost overrun occurrence in Sweden. In addition, Memon et al, (2011), Toh et al, (2012) and Abd-Karim et al, (2013) mentioned that client requirements on quality, poor design and delays in design, unrealistic contract duration and requirements imposed lack of experience, late delivery of materials and equipment, relationship between management and labor, fluctuation of prices of materials, cash flow and financial difficulties faced by contractors and shortages of materials are the most influencing factors in cost overrun in Malaysia.

Whereas, Banaitiene and Banaitis, (2012) stated that lack of experience, design errors, scheduling errors and failure to comply with contractual quality requirements, and technology changes in Croitia. In addition, Apolot et al, (2012) stated that the most influencing factors of cost overrun in Uganda are lack of project management during execution: insufficient and ineffective working, delays, changes in scope of work and location.

Besides, Doloi, (2013) clarified that the planning and scheduling deficiencies, Methods/techniques of construction, effective monitoring and feedback process, complexity of design and construction, improper control over site resource allocations and contractor’s deficiencies in planning and scheduling at tender stage are the main causes of cost overrun of construction projects in Australia.

Shaqour, (2014); Khodeir and Hamdy, (2015) and Yakoub, (2016) mentioned that the junior factors cause cost overrun in Egypt are changes in project scope, material prices, Poor estimation of project cost, additional works at owner's request, donor policy in bidding to the lowest price, fluctuations in the cost of building materials, delay in project completion time, fraudulent practices, kickbacks, and economic instability/ political insecurity.

2.3. Research study gap.

Most of the empirical studies was focused on public sectors (which controlled by concerned government bodies), this implies that all construction material are provided by the government at certain fixed unit rate which makes it completely different from the private run projects and although, there is no recent research has been done on factors affecting project cost overrun on real estate construction projects in Addis Ababa city. Therefore this research was clearly discussed about the cause of project cost overrun, and their aggregate effects on different sectors, and resolution methods in construction projects.

2.4. Conceptual Framework

Conceptual framework can clearly shows the relationship between explanatory variables of the study and dependent variables. According to Kothari (2008), are structured from a set of broad ideas and theories that help a researcher to properly identify the problem they are looking at, frame their questions and find suitable literature. Most academic research uses a conceptual framework at the outset because it helps the researcher to clarify the research questions and aims. So this study was clearly assess or identify the cause of construction project cost overrun by focusing on factors related to contractor, Economic factors, Timeliness and financial factors, Consultant related factors and Owner related factors.

DEPENDENT VARIABLES

Cost over run

INDEPENDENT VARIABLES

Factors related to contractor

.

Economic factors

Timeliness and financial factors

Consultant related factors

Owner related factors

Fig1. Conceptual Frame Work Model (Developed by the researcher)

CHAPTER THREE

RESEARCH METHODOLOGY

3. Introduction

Under this Chapter, this study was discussed about background of the organization, Research design, approach, data sources and type, target population, sample size, sampling techniques, data collection tools data analysis, model specification and ethical consideration.

3.1 Description of study area

Addis Ababa (Finfine) is the capital and largest city of Ethiopia and Oromia. It also serves as the seat of the president of Oromia. The current metro area population of Addis Ababa in 2022 is 5,228,000. It lies on a plateau in the country’s geographic centre at an altitude of about 8,000 ft (2,450 m). It has become the national centre for higher education, banking and insurance, and trade. Several international organizations have their headquarters there, including the Organization of African Unity.

3.2 Background of the organization

Ethiopia has its own several ancient civilizations, from the 60s there is a great influence by the international style of architectural design. Because of these, every building is reduced to plain vertical and horizontal lines of concrete blocks, which is unimpressive and ugly, are a menace to the society and a cause of environmental degradation. They are also a cause of a complete break to traditional values and cultural patterns. Apart from that, because of the international style influence, the country cannot relate itself with tradition while we have not yet been to able satisfy the basic housing needs of our people even with modern solutions. But I think, it is very important to learn from mistakes done on built housing blocks that were implemented without a thorough study of function. And it is important to encourage the construction of buildings with local materials and of course with consideration of functional requirements and proper management. The legal definition of real estate or real property is land and the buildings on it. Real estate law governs who may own and use the land in real estate in Ethiopia along with the rest of the world. Real estate may be either residential or commercial. It can be owned by one person but can be used by another through rental arrangements. All land in Ethiopia belongs to the government. Land can be purchased or leased. And due to its high value, many local laws ensure real estate transactions are properly performed and recorded. Land may also pass between family members through estate planning or owned by more than one person.

State and local governments have rules concerning the purposes for which land may be used. For example, each plot of land must be used according to local zoning laws, and landowners may not damage the surrounding environment.

3.3 Research Design

In order to accomplish the objective of the study, the researcher may use both descriptive and an explanatory research design. The researcher select the explanatory research design since the explanatory research aims to answer the question why some variables have an effect on other variables or it seeks to test a theory which is a set of logically organized and interconnected principles, rules, assumptions, statements and propositions which are employed to explain, describe and predict the phenomenon, (Melkamu, 2020).

3.4 Research Approach

In light of this, the study were adopted a mixed research approach (both quantitative and qualitative). According to Creswell (2012), is used when the problem has been defined specifically, and where the researcher has certain issues to be examined through qualitative and quantitative approaches. This design would also help in conducting statistical analysis to reach at conclusive results about the phenomenon under the study. More specifically, the quantitative aspect employed survey method while the qualitative aspect utilized case analysis (through interview). Hence, the study employs concurrent triangulation to examine the Factor affecting projects cost overrun on Real Estate construction projects in Addis Ababa City.

3.5 Data Sources and Type

Kothari, (2004) notes that there are two major sources of data namely primary and secondary data sources that could be used in any study. Hence, the data sources for the research were both secured from primary and secondary sources. The primary data was collects from purposively selected constructors and other participants through survey instrument. In addition, primary data was also collected through key informant interview conducted with purposively selects clients and consultants. The data was also support by document analysis technique, which was applies through the review of reports. In utilizing secondary sources, published articles, research works, previous studies, books, reports, and other sources was reviewed. In addition to this, both quantitative and qualitative data were collected from various sources and were used for the research.

3.6 Target Population

Target population is a well-defined or specified set of people, group of things, households, firms, services, elements or events which are being investigated. Thus, the target population of the study was contractors, consultants, clients of the Real estate construction projects that are currently registered for the construction of real estate. The number of constructor registered for the construction of real estate is above 522 contractors, 26 consultants, and 9 clients in Addis Ababa. (Websites, Addis Ababa Constriction Bureau).

3.7 Sample Size

To determine the sample size for the study, Kothari (2004)’s statistical formula was used. In order to determine the sample size from the total population, the following formula, Kothari (2004) used:

zn=z2 .  p .  q .  Ne2N-1 + z2.  p .  q

| confidence level | 90% |
| --- | --- |
| Probability | 0.5 |
| Error | 0.05 |
| population size | 557 |
| alpha divided by 2 | 0.05 |
| z-score | 1.645 |

Where:

n - Sample size

N - Total households of the town

e - Precision level (standard error (0.05 for 90% confidence interval) = 5%

z=the statistical value for the confidence level used 1.645 for 90% confidence level.

P - Proportion of success (probability to be included in the sample) = 50% = 0.5 based on most conservative sample size.

q = proportion of fail = (1-p) = 0.5 = 50%

n = 1.6452(0.5)(0.5)(557)(0.05)2557-1 + 1.6452(0.5)(0.5)

n=376.813981252.06650625

n = 182.34 ≈ 182

Different researchers had been taken sample by determining the sample proportion success and not success based on the experience from previous survey research response rate, Corbetta (2003) the return or success rate 50% is “adequate”; 60% response rate is “good” and 70% rate or higher is “very good” .

3.8 Sampling Techniques

To have fair distribution between the constructors, consultants and clients, stratified sampling method was used. Thus, given the available resource and time at the disposal of the researcher, a total of 182 sample size will be uses, that is only 168  contractors (out of 522), 8 consultants (out of 26), and 6 clients (out of 9).

Table3.1 population and sample size

| Targeted parties | No. of population | Sample |
| --- | --- | --- |
| Constructors | 522 | 168 |
| Consultants | 26 | 8 |
| Clients | 9 | 6 |
| Total | 557 | 182 |

Source: (Websites, Real estate constriction).

The strata sampling technique is generally applied in order to obtain a representative sample. Under stratified sampling the population of the study is divided into three:  Constructors, Consultants and Clients that has a direct exposure to the construction activity.  In the study Constructors refers a person he/she who take the overall responsibility of a given project. Whereas, a Consultant is professional person that gives expert advice in the given project and lastly Client is the owner of the given project. The selection of the sample is limited to the Constructors, Consultants and Clients of the construction project because, the objective of the study is only examine the Factor Affecting Projects Cost Overrun on Real Estate Construction Projects in Addis Ababa City, due to some difficulties in getting complete data base of all Constructors, Consultants and Clients of the construction projects.

3.9 Data Collection Techniques

According to Creswell, (2003), there are many methods of data collection. The choice of a tool and instrument depends mainly on the attributes of the subjects, research topic, problem question, objectives, design, expected data and results. This is because each tool and instrument collects specific data. To this end, the study was use questionnaire, key informant interview and document analysis techniques to collect both primary and secondary data. Secondary data was secures through the review of relevant articles, research works, books, and journals, officially published documents government and, and other pertinent sources.

A. Questionnaire

Questionnaire as instrument to conduct the survey was prepared and distributed to illicit information from randomly selected constructors enhancing the validity of the instrument. The Questionnaire was prepared in Likert scale and respondents were asked to rate the issues under each headings. With this regards, the questionnaire had closed-ended questions. The researcher has administered the survey questionnaire to each member of the target respondent. The questionnaire was carefully designed and pilot test was conducted with a few members of the population for further improvements. This test was done in order to enhance its validity and accuracy of data to be collected for the study.

B. Key informant Interview

Key informant interview was conducted with the client’s and consultants at different sites. The selection of key informants is done using stratified sampling technique.

C. Document Analysis

Review and analysis of important documents related to the study were reviewed in order to get sufficient data that supports the findings of the study.

3.10 Method of Data Analysis

Data that collects from questioner was analyzed by using descriptive and inferential or econometrics analysis.

3.10.1 Descriptive Analysis

As stated by Duncan Cramer and Dennis Howitt (2004), descriptive data analysis emphasizes on maximizing the gain from the data by making clearer the process of describing and analyzing the data gathered. After proper editing, the data was coded and entered to the software then it will be ready to analysis. For the purpose of achieving the objectives of the study, the collected data was processed and analyzed with descriptive statistics using Statistical Package for Social Studies (SPSS) of 20th version. This technique was selected because it helps to summarize the sample, provides and allows describing the characteristics of the data collects and it helps to thoroughly analyze and interpret the questions one by one in order to reach meaningful results. Throughout the analyzing process, percentages, frequency and mean were employed. In doing so tables were used to present and made easily understandable the findings in order to arrive at certain conclusion. The qualitative types of data (interview) were analyzes by using narration and explaining the response of the participants. In the descriptive analysis of the study, tables, mean, standard deviation, minimum and maximum was used.

3.10.2 Model Specification

The Logistic Regression Analysis is one of the most commonly used tools in econometric works. It is concerned with describing and evaluating the relationship between the explained variable and one or more than one explanatory variables. In its dictionary definition, regression is backward movement, a retreat, a return to an earlier stage of development Maddala, (1992). In an econometric analysis, the Logistic regression   models was applied in order to identify the Factors affecting projects cost overrun on Real Estate construction projects in Addis Ababa City.

      - Logistic Regression Analysis

Binary logistic regression analysis is employed in analyzing the data. The binary or binomial logistic regression is the type of regression which is used when the response variable is dichotomous and the predictor variables are of any type. In binary logistic regression, a single outcome variable Yi (i=1, 2,…,n) follows a Bernoulli probability distribution that takes on the value 1 with probability pi and 0 with probability 1- pi. Then pi varies over the observations as an inverse logistic function of a vector Xi of predictors for the ith individual which includes a constant and k explanatory variables, that is,

Pi=eβo+β1x1i+β2x2i+…+βkxki1+eβo+β1x1i+β2x2i+…+βkxki

In logistic regression, the response variable is a logit, which is the natural log of the odds,

that is,

logodds=logit(pi=Inpi1-pi

A model parameter is interpreted as a change in the log odds for a one unit increase in Xi, holding all the other predictors constant, or after adjusting for the other predictors. In logistic regression, the odds of an event happening (e.g. the event that) is defined as the ratio of the probability that the event will occur by the probability that the event will not occur. That is, the odds of event E is given by

oddsE=pE1-pE

3.10.2.2 Basic assumption of Binary logistic regression Model

Reddy, Likassa & Asefa (2015) have made a list of the following basic assumptions:

- Logistic regression assumes meaningful coding of the variables. Logistic coefficients were difficult to interpret if not coded meaningfully. The convention for binomial logistic regression is to code the dependent class of interest as 1 and the other class as 0.

- Logistic regression does not assume a linear relationship between the dependent and independent variables.

- The dependent variable must be categorical.

- The independent variables need not be interval, no normally distributed, no linearly related and no equal variance within each group.

- The groups must be mutually exclusive and exhaustive; a case can only be in one group and every case must be a member of one of the groups.

- Larger samples are needed than for linear regression because maximum likelihood coefficients was large sample estimates.

- The logit regression equation should have a linear relationship with the logit form of the dependent variable.

- Absence of multicollinearity.

- It does not need a linear relationship between the dependent and independent variables.

- Logistic regression can handle all sorts of relationships; it applies a non linear log transformation to the predicted odds ratio.

- The error terms need to be binomially distributed.

- The assumption of homoscedesticity is not necessary in logistic regression. Logistic regression can handle ordinal and nominal data as independent variables.

- Logistic regression requires the dependent variable to be categorical (Mostly binary).

Logistic regression assumes linearity of independent variables and log odds. Otherwise, the logistic regression underestimates the strength of the relationship and reject the relationship easily, that is being not significant (not rejecting the null hypothesis) where it should be significant. Logistic regression requires quite large sample sizes (Reddy et al., 2015).

3.10.2.3 Estimation of parameters

In fitting a logistic regression model, the maximum likelihood and non-iterative weighted least squares are the two commonly used estimation methods (Green, 1993 and Hosmer and Lemeshow, 1989). In this study the maximum likelihood estimation technique is employed to estimate the parameters of the model.

Let pi be the probability of success, which is equivalent to the probability that the response variable Yi assumes the value one. Then:

pi=PYi=1|Xi =xi=11+e-x'iβ, i=1,2,……,n…………….3

Each observation (response) can be considered as an outcome of a Bernoulli trial. Thus, for the ith observation Yi, the Bernoulli distribution is:

PYi =yi|Xi= pyi1-p1-yi,=i=1,2…..n……………………………………...4

Then the likelihood function is the joint probability distribution of all n observations and is given by:

L=i=1npiyi1-pi.1-yi………………………………………….…………..5

Taking the natural logarithm of both sides gives:

InL=i=1nyi In11+e-x'iβ+i=1n1-yiIne-x'iβ1+e-x'iβ…………………………….6

Thus, by maximizing the log-likelihood function in equation (6) we can estimate the parameter vector β. Since the equation of the maximize log-likelihood function is nonlinear in β, the estimates do not have a closed form expression, we can obtain β ̂, the estimator of β using a numerical iterative method (Agresti,1996).

3.10.2.4 Variable selection and Model assessment

3.10.2.4.1 Variable selection

The goal of logistic regression is to correctly predict the category of outcome for individual cases using the most appropriate model. To accomplish this goal, a model that includes all predictor variables that are useful in predicting the response variable is considered. Several different options are available during model creation. Variables can be entered into the model in order specified by the researcher or logistic regression can test the fit of the model after each coefficient is added or deleted, called stepwise regression. The basic procedures involve (1) identifying an initial model, (2) iteratively “stepping” that is, repeatedly altering the model at the previous step by adding or removing a predictor variable in accordance with the “stepping criteria”, and (3) terminating the search when stepping is no longer possible given the stepping criteria, or when a specified maximum number of steps has been reached. The two major categories of stepwise regression techniques are: (1) the forward stepwise and forward entry and (2) the backward stepwise and backward removal.

3.10.2.4.2 Assessing goodness of fit

After developing the model for our data, it is necessary to investigate how effective the model is in describing the outcome variable. The Pearson’s chi-square, the likelihood ratio test (deviance), the Hosmer-Lemeshow test and the Wald test are the most commonly used measures of goodness of fit for categorical data. Among them, some are briefly discussed in the following section. See detailed discussion in Agresti (1996).

3.10.2.4.3 The Hosmer-Lemeshow Test

The Hosmer-Lemeshow test is one of the methods used in testing the hypothesis that the model fits the data. In this approach, data are divided into 10 groups. From each group, the observed and expected number of events will be computed and the test statistics is given by

∁=k=1gOk-Ek2Vk

Where  Ek = nPk, Vk = nPk(1-Pk), g is the number of group, Ok is observed number of events in the kth group, Ek is expected number of events in the kth group, and Vk is a variance correction factor for the kth group. If the difference between the observed number of events and what is expected by the model is large, then the statistic C ̂   becomes large and there will be evidence against the null hypothesis that the model is adequate to fit the data. This statistics has an approximate chi-square distribution with g-2 degrees of freedom (Hosmer and Lemeshow, 1989).

3.10.2.4.4 The Likelihood Ratio Test

The likelihood ratio statistic, G2, is the other commonly used approach which is based on the comparison of the fitted and the observed counts.

G2=-2LLR-LLF=-2InlikelihoodRlikelihoodF

where -2(log likelihood R) for a restricted (smaller) model and (-2log likelihood F) for a full (larger) model. G^2is distributed as X^2. The full or larger model has all the parameters of interest in it whereas the restricted is nested in the larger model. The restricted model has one or more of parameters in the full model restricted to some value (usually zero). The parameters in the nested model should be a proper subset of the parameters in the full model. Here the chi-square test is employed to see whether including a variable improves goodness-of-fit measure. If chi-square is significant, the variable is considered to be a significant predictor in the equation. A large value of G2 indicates lack of fit of the model. If the fit of the model is not good, residuals and other diagnostic measures describe the influence of individual observations on the model fit (Chatterjee and Hadi, 2006).

3.10.2.4.5 The Wald Test

Another measure of goodness of fit is what we call the Wald statistic which is commonly used to test the significance of individual logistic regression coefficients for each predictor variable. The Wald statistic also provides information whether the coefficient of an explanatory is significantly different from zero. It is analogous to the „t‟ test in multiple linear regressions. The Wald statistic is obtained by dividing the value of the coefficient of the factor of interest by its standard error. For the large sample the likelihood ratio and Wald squared give approximately the same value. In the case of small and moderate sized samples the two statistics may give different results. In that a case the likelihood ratio statistic is better than Wald statistic. For a dichotomous independent variable, the Wald statistic is given by

W=β2(s.e.β)2

When the sample size is large, the statistic has an approximate chi-square distribution with one degree of freedom (Stevenson, 2008).

3.11. Ethical Consideration

The study involves the use of human participants and ethical considerations were taken into account. Before the data gathering, task took place, negotiation will made by researcher and the organization to gain permission to conduct discussions and to gain ethically. The supported letter will be written by Ambo University Department of Accounting and Finance to Real Estate contractors in Addis Ababa will give. The purpose of the study was explained the study subjects and participation was being on voluntary basis. Study participants were clearly informed that they could withdraw from the study at any time if they need to do so. The right of each respondent to refuse or answer for few or all questions was respected. Names of study participants were not mentioned in the study report to ensure confidentiality. Moreover, the researcher was informing that a statement of confidentiality, need of conducting of this study, refraining from deceptive practices as well as reciprocity.

# CHAPTER FOUR

# DATA PRESENTATION AND ANALYSIS

This chapter presents the results and discussions of the responses gathered from the respondents through questionnaire.

## 4.1 Introduction

This chapter deals with the presentation of data, analysis and interpretation. To collect the data and extract findings, questionnaire and Interview was prepared and distributed to Owner of Project, Consultancies, Contractors, Project manager, Site Engineers and others selected from Real estate construction projects found in Addis Ababa. This chapter presents the findings of the research in accordance to the research objectives. The analyses and interpretation of the data collected from the respondents was presented. It began with a description of the demographic and general characteristics of the participating respondents. The results of Cronbach‘s coefficient alpha for reliability were examined. The study was discussed “factors affecting projects cost overrun on real estate construction projects using both descriptive and explanatory statistics. Based on the model specified in the above chapter the study was used inferential statistics or econometrics model to measure the cause and effect relationship among the explanatory and dependent variables.

The descriptive statistics utilized are based on frequency tables to provide information on the demographic variables. Through tables, summary statistics such as mean and standard deviations are computed to discuss the factor that affecting the determinants of projects cost overrun on real estate construction projects. This is followed by presentation of inferential statistics based on each research question for the study.

4.1 Response Rate

Data was collected by using structured closed questionnaires with some open ended questions, and analysis was done using SPSS version 20. Questionnaires were sent to all 182 selected Real estate construction project   employee and clients. Only 173 employees responded. This translated to 95.0 % response rate which is satisfactory.

Table 4.1 Rate of Respondent

| Description | Numbers |
| --- | --- |
| No. of questionnaire distributed | 182 |
| No. of questionnaire returned | 173 |
| Rate | 95.0% |

Source: survey data: 2022

## 4.2 General Information about the respondents

Table 4.2 Demographic characteristics of the respondents

| Demographic variables | Category | Frequency | Percentage |
| --- | --- | --- | --- |
| Sex | Male | 160 | 87.9 |
|  | Female | 22 | 12.1 |
|  | Total | 182 | 100.0 |
| Age | 21-30 years | 28 | 15.4 |
|  | 31-40 years | 99 | 544 |
|  | 41-50 years | 53 | 29.1 |
|  | above 50 years | 2 | 1.1 |
|  | Total | 182 | 100.0 |
|  | Diploma | 8 | 4.4 |
| Education level | BA/BSC | 108 | 59.3 |
|  | Master’s degree and above | 66 | 36.3 |
|  | Total | 182 | 100.0 |
| Current Position | Project manager | 3 | 1.6 |
|  | Contractors | 35 | 19.2 |
|  | Consultant | 5 | 2.7 |
|  | site engineers | 109 | 59.9 |
|  | Others | 30 | 16.5 |
|  | Total | 182 | 100.0 |
| Experience | 1-5 years | 31 | 17.0 |
|  | 6-10 years | 98 | 53.8 |
|  | 11-15 years | 43 | 23.6 |
|  | Above 15 years | 10 | 5.5 |
|  | Total | 182 | 100.0 |

Source: survey data: 2022

Sex of the respondents

As the above table 4.2 shows 160 (87.9%) of the respondents were males, while the remainder 22(12.1%) of them were females. From the result we can conclude that majority of the research participants in the study organizations, whereas male and female are underrepresented.

Age category of the respondents

Based on the above table 4.2 depicted respondents, most of the respondent’s age groups 99(54.4%) was found between 31-40 years. Followed from this 53(29.1%) of the respondent found in the age group of 41-50 years. while 28 (15.4%) and 2(1.1%) of the respondents found under the age range of 21-30 years and above 50 years respectively. Based on the age category of the respondent’s majority of the respondents are in the age category of 31-40 years. From the result shown above most of the employee or research participants were found in the middle age groups. Young and middle aged dominated the participants of this study and this has indeed contributed to the quality of work Kiros, (2018).

Education level of the respondents

In addition, table 4.2 presents education level of sample respondents’. And illustrate that most of the respondents 108 (59.3%) were bachelor’s degree holders while 66(36.3%) were second degree holder. This illustrate that majority of the respondents were in state of providing well response about their performance and their observation of the delay cause and its effects.

Current Position in the organizations

Table 4.2 illustrates that, majority of the respondent which are 109(59.9%) of the participants, were drawn from the site engineer position, followed 35 (19.2%) for contractors and 30(16.5%) of the respondents were from different other positions which was not listed in questionnaire. The other categories were 5(2.7%) for consultant and 3(1.6%) are project managers of the selected real estate construction projects.

Experience

Based on the data collected through questionnaire from the total respondents of employees, or participants of the study 98(53.8%) employees had worked for a 6-10 years, 43(23.6%) of employees had worked for a period of between 11 to 15 years, 31(17.0%) of employees had been working for 1-5 years. Lastly the study shows that 10(5.5%) of respondents were worked in the selected real estate for long period of time.

Pie chart 4.1 cost estimation techniques used

5.5%

34.1%	48%

12.1%

Pie chart 4.1 cost estimation techniques used

As the pie chart shows how the construction sector determines or measure its costs since the sector has varies cost based on the complexity of the projects. As it clearly shows majority of the respondents 88(48.4%) were answered as their company used budgetary estimate, following the result 62(34.1%) of the participants were used Rough order of magnitude and next the result 22(12.1%) of the participants were answered as their company used definitive estimation. From the pie chart result 10(5.5%) of them were answered as their company used other estimates.

Based on the result majority of the respondents were said that the organization or the most of the real estate projects has been using budgetary estimate. This technique was estimate preliminary itemized list of expenditures based on the major components of the projects. But the techniques accuracy is less since the plan is done within the actual planning stage of the projects, since the market is in state of dynamics. The finding was supported by National Institute of Building Sciences, 2014). “Cost estimating is employed as one of the main tools of successful cost management. Once an initial budget has been established, it is important to test its assumptions by employing a series of increasingly precise cost estimating techniques that coincide with further development of design and construction details” .the result shows that budgetary cost estimation system were employed to manage the overall cost of the construction sectors.

## 4.3 Discussion on Factor Affecting Projects Cost Overrun

Here below the study was discussed about the different factors which affect project timely completion.

4.3.1 Rank the project’s cost overrun

Table 4.3   Ranking the factor affecting on projects cost overrun

|  | Mean | Std. Deviation | Rank |
| --- | --- | --- | --- |
| Contractors related factors | 9.4 | 11.97 | 2 |
| Economic factors | 5.8 | 4.87 | 4 |
| Consultancies factor | 4.8 | 4.06 | 5 |
| Owner-related factors | 6.6 | 6.9 | 3 |
| Financial factor | 9.8 | 14.16 | 1 |

Source: survey data: 2022

The above Table 4.3 shows the ranking of the factors affecting on projects cost overrun depending on the value of the means. From the listed factors Financial factor                               (Mean 9.8 and SD 14.16) is the most critical factor which affects the overall projects cost overrun. Following that the second ranked factor was Contractors related factors (Mean 9.4 and Standard deviation 11.97) has also undeniable factors effects on the construction projects cost overrun,  the third ranked factor was Owner-related factors  (Mean 6.6 and SD 6.9 ) also has an effects on construction project cost overrun . Those variables have an impact on the project successful completion of the project.

Based on the mean value of the variables Economic factors (Mean 5.8 and SD 4.87) and Consultancies factor (Mean 4.8 and SD 4.06 ) were ranked fourth and fifth accordingly.

Based on the result shows above the study was concluded that majority of the construction projects are lead to cost overrun as a result of financial factor. Performance of the project highly affected by inflation or the overall price increment, change in material price and changes in exchange rates. Overall the project cost overrun problem was highly affected by poor construction management and late payment.

The finding was supported by Gary (2009) in Ghana construction industry also revealed problems in late payments by clients. It is, therefore, essential that clients should develop a responsive mechanism so as to speed up the payment process and issue the payments on time. In Afghanistan, bureaucracy in government agencies is also responsible for slowing down the payment process. Thus, it is recommended that the government should develop a transparent strategy to speed up the process.

4.3.2 Causes of project cost overrun using descriptive analysis

According to Pallant, (2005) Explain Descriptive statistics concern the development of certain indices from the raw data. These are mean scores, standard deviations and percentage for each subgroup. Interpreting the result of these values will also give us an indication of the impact of the independent variable.

| Scale | Interpretation |
| --- | --- |
| 1 to 1.40 | Represents (strongly disagree) |
| 1.41 until 2.20 | Represents (Disagree). |
| 2.21 until 3.00 | Represents (Neutral). |
| 3:10 until 4:40 | Represents (agree) |
| 4:41 until 5:00 | Represents (strongly agree) |

Source: survey data. (2022)

| Table 4.4 Causes of project cost overrun |  |  |  |
| --- | --- | --- | --- |
|  | N | Mean | Std. Deviation |
| The project is complex and large | 182 | 3.8352 | 1.22374 |
| New technology is involved not on the construction process | 182 | 3.4890 | 1.49304 |
| Risks were not planned for and improperly managed | 182 | 4.0385 | 1.15326 |
| Delay between design and procurement phases | 182 | 3.4011 | 1.40189 |
| Unclear, unstable and incomplete requirement statement and inappropriately assigned cost for it | 182 | 3.9505 | 1.16713 |
| Rework and additional work | 182 | 3.4066 | 1.42183 |
| Inadequate monitoring of funds | 182 | 3.9615 | 1.08920 |
| Pooled Mean | 3.73 |  |  |

Source: survey data: 2022

The result above shows the causes of project cost overrun in the construction sector. As the result shows the highest mean score is 4.0385 and standard deviation of 1.15326 on Risks were not planned for and improperly managed. Based on the mean value the second higher mean score is 3.9615 and of Inadequate monitoring of funds Unclear, unstable and incomplete requirement statement and inappropriately assigned cost for it. The third mean score is 3.9505 of Unclear, unstable and incomplete requirement statement and inappropriately assigned cost for it. Fourth and fifth result shown in the above table the mean scores 3.8352 and 3.4890 shows employee or respondents were agreed on the project is complex and large And New technology is involved not on the construction process as are the causes of project cost overrun in the construction project sector. The result coincides with the findings of previous research study by Le-Hoai et al. in the Vietnam construction industry. Difficulties in financing projects by contractors: This indicator is another major problem in contributing to cost overruns in Afghanistan construction industry.

Overall the grand mean (Pooled mean) 3.73 shows that the construction projects were cost overrun  as a result of different factors like using Risks were not planned  and improperly managed, Inadequate monitoring of funds Unclear, unstable and incomplete requirement statement and inappropriately assigned and Unclear, unstable and incomplete requirement statement and inappropriately assigned  are hinder the performance of the sectors.  But the company is working well in design and procurement phases and Rework and additional work. The finding of the was similar with Olatunji, (2010) the study found that A weak link in the process such as a lack of project management experience, could adversely affect timely execution/ timely completion of the projects and technology related factors was highly affect or the project cost overrun problem.

4.3.2.1 Factors related to contractor

Among all the construction parties, a contractor has the major responsibility to carry out most of the project activities. Similarly, if the project is not finished on time and within the allocated budget then the contractors is blamed. In reality, the contracting business is a challenging and demanding profession that contains many complex activities, and, to avoid project cost overrun, the main contractor often holds full responsibility for the work of sub-contractors as well as his own. Basically, how the contractor deals with particular situations depends on the nature of the work and the type of contract (Shi & Arditi, 2001).

Table 4.5 Factors related to contractor

| Scale | Measures | Frequency | Percent |
| --- | --- | --- | --- |
| Shortage of construction material and inflection problem has led to project cost overrun | Strongly disagree | 15 | 8.2 |
|  | Disagree | 20 | 11.0 |
|  | Neutral | 25 | 13.7 |
|  | Agree | 48 | 26.4 |
|  | Strongly agree | 74 | 40.7 |
|  |  | 182 | 100% |
| Project on the site have been led to cost overrun due to lack of adequate decision making by the contractors | Strongly disagree | 24 | 13.2 |
|  | Disagree | 32 | 17.6 |
|  | Neutral | 41 | 22.5 |
|  | Agree | 36 | 19.8 |
|  | Strongly agree | 49 | 26.9 |
|  |  | 182 | 100% |
| Contractor’s planning experience influences the cost of projects completion | Strongly disagree | 16 | 8.8 |
|  | Disagree | 26 | 14.3 |
|  | Neutral | 39 | 21.4 |
|  | Agree | 43 | 23.6 |
|  | Strongly agree | 58 | 31.9 |
|  |  | 182 | 100% |
| Evaluation steps held by the contractor influence projects completion at the initial (planed) costs | Strongly disagree | 25 | 13.7 |
|  | Disagree | 28 | 15.4 |
|  | Neutral | 31 | 17.0 |
|  | Agree | 45 | 24.7 |
|  | Strongly agree | 53 | 29.1 |
|  |  | 182 | 100% |
| Contractor is not use the update technology on the construction process | Strongly disagree | 29 | 15.9 |
|  | Disagree | 27 | 14.8 |
|  | Neutral | 17 | 9.3 |
|  | Agree | 44 | 24.2 |
|  | Strongly agree | 65 | 35.7 |
|  |  | 182 | 100% |

Source: survey data. (2022)

From the responses received, various factors attracted different degrees of responses on the liker scale a rating. On the factor that focused Shortage of construction material and inflection problem 74 respondents strongly agreed that it influenced the cost overrun of real estate construction projects in Addis Ababa. 15 respondents has opted for strongly disagree, 20 (11%) went for disagree, 25(13.7%) for neutral while 48 (26.4%) went for agree. Concerning with the lack of adequate   decision making by the contractors, 24(13.2%) went for strongly disagree, 32 (17.6%) went for disagree, 36(19.8%) went for agree, 41(22.5%) went for neutral, while 49(26.9%) went for strongly agree. Related to Contractor’s planning experience, 16 (8.8%) respondents went for strongly disagree, 26(14.3%) went for disagree, 39(21.4%) neutral, 43(23.6%) agreed and 58(31.9%) strongly agreed. Regarding the Evaluation steps held by the contractor influence projects completion at the initial (planed) costs, 53 (29.1%) respondents strongly agreed, 45(24.7%) respondents agreed, 31(17.0%) respondents neutral, 28(15.4%) respondents disagreed and 25(13.7%) respondents strongly disagreed. Lastly Contractor is not use the update technology on the construction process, 65(35.7%) strongly agreed, 44(24.2%) respondents agreed, 29(15.9%) respondents strongly disagreed, 27(14.8%) respondents disagreed, 17(9.3%) respondents neutral.

The findings of the study imply that majority of the respondents agreed that there is a problem Shortage of construction material and inflection and the Contractor also not use the update technology on the construction process.  Additionally interviewees have stated that there are lack of Contractor’s planning experience influences the cost of projects completion and the Evaluation steps held by the contractor influence projects completion or it may lead to the project cost overrun. They further bereaved that there were also lack of adequate   decision making by the contractors is leads to the problem of project cost overrun. These, according to the key informants, has affected the construction process and contributed to project cost overrun. The finding  was similar with Olatunji, (2010) the study found that A weak link in the process such as a lack of project management experience, could adversely affect timely execution/ timely completion and cost overrun of the projects and technology related factors was highly affect construction project completion.

4.3.2.2   Economic Factors

Chism and Armstrong (2010) confirm the fact that the political environment affects the construction of a project. Fortune and White (2014) in their review of sets of critical success factors in sixty-three publications listed political stability as one of the twenty-seven critical success factors. Wideman (1986) assert that changes in government actions are a major external risk factor militating against the success of projects. Economic environmental considerations refer to the level of general economic activity and resources available to carry out construction. In this context, the study has assessed the economic factors on real estate construction projects in Addis Ababa. The study has found out that majority of the respondent agreed and strongly agreed that economic factors had contributed to project cost overrun in the study area.

Table 4.6 Economic Factors

| Scale | Measures | Frequency | Percent |
| --- | --- | --- | --- |
| The project in the site have been led to project cost overrun due to lack of efficient quality control techniques | Strongly disagree | 14 | 7.7 |
|  | Disagree | 15 | 8.2 |
|  | Neutral | 29 | 15.9 |
|  | Agree | 60 | 33.0 |
|  | Strongly agree | 64 | 35.2 |
|  |  | 182 | 100% |
| The project in the site have been led to project cost overrun because of variation in market price | Strongly disagree | 18 | 9.9 |
|  | Disagree | 22 | 12.1 |
|  | Neutral | 33 | 18.1 |
|  | Agree | 52 | 28.6 |
|  | Strongly agree | 57 | 31.3 |
|  |  | 182 | 100% |
| The project in the site have been led to project cost overrun due to decline in purchasing power of birr compared to the dollar | Strongly disagree | 16 | 8.8 |
|  | Disagree | 15 | 8.2 |
|  | Neutral | 40 | 22.0 |
|  | Agree | 63 | 34.6 |
|  | Strongly agree | 48 | 26.4 |
|  |  | 182 | 100% |
| The project complicity and large in size have been led to project cost overrun | Strongly disagree | 12 | 6.6 |
|  | Disagree | 17 | 9.3 |
|  | Neutral | 30 | 16.5 |
|  | Agree | 53 | 29.1 |
|  | Strongly agree | 70 | 38.5 |
|  |  | 182 | 100% |

Source: survey data. (2022)

From the responses received, various factors attracted different degrees of responses on a rating. On the factor that focused project complicity and large in size 70(38.5) respondents strongly agreed that it influenced the cost overrun of real estate construction projects in Addis Ababa. 53(29.1) respondents has went for agree, 30(16.5) went for neutral, 17(9.3%) for disagree, while 12 (6.6%) went for strongly disagree. In connection lack of efficient quality control techniques, 14(7.7%) went for strongly disagree, 15 (8.2%) went for disagree, 29(15.9%) went for neutral, 60(33%) went for agree, while 64(35.2%) went for strongly agree. Related to variation in market price, 18(9.9%) respondents went for strongly disagree, 22(12.1%) went for disagree, 33(18.1%) neutral, 52(28.6%) agreed and 57(31.3%) strongly agreed. Regarding the decline in purchasing power of birr compared to the dollar 63(34.6%) respondents agreed, 48(26.4%) respondents strongly agreed, 40(22.0%) respondents neutral, 16(8.8%) respondents strongly disagreed and 15(8.2%) respondents disagreed.

The findings of the study imply that majority of the respondents agreed that there is a problem project complicity and large in size and lack of efficient quality control techniques on the real estate construction process.  Additionally interviewees have stated that there is the problem of variation in market price and decline in purchasing power of birr compared to the dollar are influences the cost of projects completion or lead project cost overrun problem. They further bereaved that there were also lack of adequate   decision making by the contractors is leads to the problem of project cost overrun. These, according to the key informants, has affected the construction process and contributed to project cost overrun. The finding was similar with Memo, Rahman and Azis (2012) investigated the variation and claims in construction projects in Dubai and Abu Dhabi in the United Arab Emirates using 124 claims related to can be little more specific the range of the projects or typical project.

### 4.3.2.3 Consultant-related factors

The client may consult with other professionals who can assist him in organizing the entire construction project. These professionals are called consultants. The main duties and responsibilities of a consultant may be to design the infrastructure of the project, which includes architectural, mechanical, structural, and electrical designs. Some other responsibilities may include the preparation of project related documents such as bills, drawings, specifications, and tender documents (Long et al, 2004). Furthermore, in some cases, consultants also conduct project planning, cost control and estimation, and quality control.

### Table 4.7 Consultant-related factors

| Scale | Measures | Frequency | Percent |
| --- | --- | --- | --- |
| Lack of experienced consultancy staff has led to the project cost overrun | Strongly disagree | 11 | 6.0 |
|  | Disagree | 14 | 7.7 |
|  | Neutral | 20 | 11.0 |
|  | Agree | 65 | 35.7 |
|  | Strongly agree | 72 | 39.6 |
|  |  | 182 | 100% |
| Projects in the site have been led to cost overrun problem due to lack adequate Preparation of project related documents | Strongly disagree | 16 | 8.8 |
|  | Disagree | 31 | 17.0 |
|  | Neutral | 37 | 20.3 |
|  | Agree | 45 | 24.7 |
|  | Strongly agree | 53 | 29.1 |
|  |  | 182 | 100% |
| Poor communication between members of the project team has led to project cost overrun | Strongly disagree | 25 | 13.7 |
|  | Disagree | 29 | 15.9 |
|  | Neutral | 33 | 18.1 |
|  | Agree | 36 | 19.8 |
|  | Strongly agree | 59 | 32.4 |
|  |  | 182 | 100% |
| The project cost estimation has not been achieved because of lack of proper planning | Strongly disagree | 7 | 3.8 |
|  | Disagree | 10 | 5.5 |
|  | Neutral | 39 | 21.4 |
|  | Agree | 53 | 29.1 |
|  | Strongly agree | 73 | 40.1 |
|  |  | 182 | 100% |

Source: survey data. (2022)

From the above table it is easy to determine that majority of the respondents 35.7% and 39.6% agreed and strongly agreed to the Lack of experienced consultancy staff in the study area. Less than 10% of the respondents have disagreed with the idea that there was Lack of experienced consultancy staff in the study area. Therefore this problem lead project cost overrun.  Besides, majority of the respondents 24.7% and 29.1% agreed and strongly agreed to that there was lack adequate Preparation of project related documents, and less than 18% of respondent have disagreed with the idea that there was lack adequate Preparation of project related documents. Therefore from the respondents feedback lack adequate Preparation of project related documents, have leads to project cost overrun problem. Related to, lack of Poor communication between members of the project team 19.8% and 32.4% of the respondents have agreed and strongly agreed respectively.  Few number of respondents stated that there was lack of Poor communication between members of the project team. Majority of the respondents agreed that lack of Poor communication between members of the project team have leads to project cost overrun. In last, it is confirmed by majority of the respondents 29.1% and 40.1% have agreed and strongly agreed respectively that lack of proper planning has led to project cost overrun while 5.5% and 3.8% of the respondents disagreed and strongly disagreed on the idea that there was no problem with the lack proper planning in the construction projects of the study area.

The findings of the study imply that majority of the respondents agreed that there is Lack of experienced consultancy staff and Poor communication between members of the project team in the real estate construction process.  Additionally respondents have stated that there is the problem of lack adequate Preparation of project related documents starting from the beginning of the projects in the real estate construction projects. Lastly the interviewees have stated that there is the problem of proper planning in the real estate construction projects. These, according to the key informants, has affected the construction process and contributed to project cost overrun. The finding was similar with Odeh & Battaineh (2002) believe that during the construction processes, the enquiries and inspections of the consultant may slow down the progress of the work.

4.3.2.4 Owner-related factors

One of the most crucial decisions that owners need to take at the beginning of the project is to determine the duration of the contract. Many owners prefer fast completion of work but thorough investigations should be conducted to decide the contract duration. Another major factor that delays the initialization of the project is the owner’s failure to hand over the site to the contractor. Therefore, the personal involvement and quick decision-making on various matters by the owner in the initial phases of the project may accelerate the project’s progress.

Table 4.8 Owner-related factors

| Scale | Measures | Frequency | Percent |
| --- | --- | --- | --- |
| Unrealistic contract duration imposed by owners have been led to project cost overrun | Strongly disagree | 54 | 29.7 |
|  | Disagree | 46 | 25.3 |
|  | Neutral | 35 | 19.2 |
|  | Agree | 24 | 13.2 |
|  | Strongly agree | 23 | 12.6 |
|  |  | 182 | 100% |
| Project on the site have been led to cost overrun due to lack of adequate decision making by the owner | Strongly disagree | 17 | 9.3 |
|  | Disagree | 24 | 13.2 |
|  | Neutral | 26 | 14.3 |
|  | Agree | 53 | 29.1 |
|  | Strongly agree | 62 | 34.1 |
|  |  | 182 | 100% |
| The absence of good contract management by the owner is led to the problem of project cost overrun | Strongly disagree | 19 | 10.4 |
|  | Disagree | 21 | 11.5 |
|  | Neutral | 31 | 17.0 |
|  | Agree | 43 | 23.6 |
|  | Strongly agree | 68 | 37.4 |
|  |  | 182 | 100% |
| Lack of the working relationship between an owner and a contractor have been led to project cost overrun problem | Strongly disagree | 12 | 6.6 |
|  | Disagree | 27 | 14.8 |
|  | Neutral | 29 | 15.9 |
|  | Agree | 48 | 26.4 |
|  | Strongly agree | 66 | 36.3 |
|  |  | 182 | 100% |

Source: survey data. (2022)

From the responses received, various factors attracted different degrees of responses on a rating. On the factor that focused Unrealistic contract duration imposed by owners 54(29.7%) respondents strongly disagreed that it not factor for the cost overrun of real estate construction projects in Addis Ababa. 46(25.3%) respondents has went for disagree, 35(19.2%) went for neutral, 24(13.2%) for agree, while 23 (12.6%) went for strongly agree. While related with lack of adequate decision making by the owner 17(9.3%) went for strongly disagree, 24 (13.2%) went for disagree, 26(14.3%) went for neutral, 53(29.1%) went for agree, while 62(34.1%) went for strongly agree. Regarding to the absence of good contract management by the owner 19(10.4%) respondents went for strongly disagree, 21(11.5%) went for disagree, 31(17.0%) neutral, 43(23.6%) agreed and 68(37.4%) strongly agreed. Related to Lack of the working relationship between an owner and a contractor 12(6.6%) respondents went for strongly disagree, 27(14.8%) went for disagree, 29(15.9%) neutral, 48(26.4%) agreed and 66(36.3%) strongly agreed.

The findings of the study imply that majority of the respondents agreed that there is a problem Lack of the working relationship between an owner and a contractor, lack of adequate decision making by the owner and absence of good contract management by the owner on the real estate construction process.  On the other hand interviewees have stated that there is no problem focused Unrealistic contract duration imposed by owners, therefore it’s not factor for project cost overrun. These, according to the key informants, has affected the construction process and contributed to project cost overrun. The finding was similar with Kwakye (1998) mentioned that the owner’s duties and responsibilities are onerous, and that he or she needs other knowledgeable parties to manage or organize the construction project. Another (Odeh & Battaineh, 2002) In a few cases, owners have in-house project management teams that participate in the construction process, but most of the time, owners hire a project manager and external parties to handle the project.

4.3.2.5 Timeliness of Payment and Financial Factors

A common issue in worldwide construction companies is to complete projects both on time and within the budget initially planned. The completion of projects in a timely manner is often a critical factor and measure of project success. In recent years, there has been an increasing interest in the use of projects as building blocks in the strategic management of organizations (Weiss & Potts, 2012).

Table 4.9 Timeliness of Payment and Financial Factors

| Scale | Measures | Frequency | Percent |
| --- | --- | --- | --- |
| Lack of payment in time and slow financial procedures has led to project cost overrun | Strongly disagree | 11 | 6.0 |
|  | Disagree | 17 | 9.3 |
|  | Neutral | 22 | 12.1 |
|  | Agree | 58 | 31.9 |
|  | Strongly agree | 74 | 40.7 |
|  |  | 182 | 100% |
| Limited authority among supervision of financial staff have overcome the problem of project cost overrun | Strongly disagree | 15 | 8.2 |
|  | Disagree | 22 | 12.1 |
|  | Neutral | 35 | 19.2 |
|  | Agree | 51 | 28.0 |
|  | Strongly agree | 59 | 34.4 |
|  |  | 182 | 100% |
| Absence risk allocation mainly on the contractor has led to the project cost overrun | Strongly disagree | 10 | 5.5 |
|  | Disagree | 13 | 7.1 |
|  | Neutral | 18 | 9.9 |
|  | Agree | 60 | 33.3 |
|  | Strongly agree | 81 | 44.5 |
|  |  | 182 | 100% |
| Inadequate monitoring of funds have been led to project cost overrun | Strongly disagree | 25 | 13.7 |
|  | Disagree | 29 | 15.9 |
|  | Neutral | 32 | 17.6 |
|  | Agree | 39 | 21.4 |
|  | Strongly agree | 57 | 31.3 |
|  |  | 182 | 100% |

Source: survey data. (2022)

From the above table it is easy to determine that majority of the respondents 31.9% and 40.7% agreed and strongly agreed to the Lack of payment in time and slow financial procedures in the study area. Less than 5% and 10% of the respondents have strongly disagreed and agreed respectively with the idea that there was Lack of payment in time and slow financial procedures in the study area. Therefore this problem was factor for project cost overrun problem in the study area.  On the other hand, majority of the respondents 28.0% and 34.4% agreed and strongly agreed to that there was Limited authority among supervision of financial staff, and less than 13% of respondent have disagreed with the idea that there was Limited authority among supervision of financial staff. Therefore from the respondents feedback Limited authority among supervision of financial staff, have leads to project cost overrun problem. Related to, Absence risk allocation 33.3% and 44.5% of the respondents have agreed and strongly agreed respectively.  Few number of respondents stated that there was risk allocation procedures in construction projects. Majority of the respondents agreed that Absence risk allocation have leads to project cost overrun. In last, it is confirmed by majority of the respondents 21.4% and 31.3% have agreed and strongly agreed respectively that Inadequate monitoring of funds has led to project cost overrun while 15.93% and 13.74% of the respondents disagreed and strongly disagreed that there was no problem related with monitoring of funds in the construction projects of the study area.

The findings of the study imply that majority of the respondents agreed that there is Lack of payment in time and slow financial procedures and Limited authority among supervision  of financial staff in the real estate construction process.  Additionally respondents have stated that there is the Absence risk allocation problem in the real estate construction projects. Lastly the interviewees have stated that there is the problem monitoring of funds in the real estate construction projects. These, according to the key informants, has affected the construction process and contributed to project cost overrun. The finding was related with Al-Tabtabai (2002) conducted a study on causes of delays in construction projects in Kuwait and found out that the major causes of delay were: Slow financial and payment procedures; Slow decision-making process; Limited authority among supervision staff; Risk allocation mainly on the contractor; and Lack of design drawings coordination.

## 4.4 Inferential Analysis

In this sub sections the study was discussed binary logistic regression methods analysis to identify the effects of independent variables (Contractors related factors, Economic factors, Consultancies factor, Owner-related factors and financial factors) on the dependent variables (cost overrun).

4.4.1 Logistic Regression Model Analysis

| Table 4.10 Case Processing Summary |  |  |  |
| --- | --- | --- | --- |
| Unweighted Casesa |  | N | Percent |
| Selected Cases | Included in Analysis | 182 | 100.0 |
|  | Missing Cases | 0 | .0 |
|  | Total | 182 | 100.0 |
| Unselected Cases |  | 0 | .0 |
| Total |  | 182 | 100.0 |
| - If weight is in effect, see classification table for the total number of cases. |  |  |  |

| Dependent Variable Table 4.11 Encoding |  |
| --- | --- |
| Original Value | Internal Value |
| No | 0 |
| Yes | 1 |

Block 0: Beginning Block

4.4.1.1 Classification

Table 4.12 classification table

| Table 4.12 Classification Tablea |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Observed |  |  | Predicted |  |  |
|  |  |  | cost overrun |  | Percentage Correct |
|  |  |  | No | Ye |  |
| Step 1 | cost overrun | No | 24 | 41 | 36.9 |
|  |  | Ye | 12 | 105 | 89.7 |
|  | Overall Percentage |  |  |  | 70.9 |
| - The cut value is .500 |  |  |  |  |  |

The beginning Block evaluates our model with only the constant in the equation (sometimes called the null model). The constant is analogous to the y-intercept in OLS regression.

Table 4.12 is an SPSS classification table for the response variable based on how well the model does with only a constant term included. The overall classification for the model is equal to 70.9%. What this means is that the model doesn't do a good job at classifying subjects, which actually is expected at this stage of the analysis since we only have the constant term included in the model. That is, we have yet to use more predictors to aid in classification and to sharpen our predictive power.

4.4.1.2 Omnibus Tests of Model Coefficients

| Table 4.13 Omnibus Tests of Model Coefficients |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Chi-square | Df | Sig. |
| Step 1 | Step | 23.385 | 5 | .000 |
|  | Block | 23.385 | 5 | .000 |
|  | Model | 23.385 | 5 | .000 |

Consider the model which includes all predictors. Omnibus Tests of Model Coefficients (Table 4.13) gives a Chi-Square of 23.385 which is significant at 0.01. This is a test of the null hypothesis that adding the predictors to the model has not significantly increased our ability to predict cost overrun. Since the omnibus test is significant we can conclude that adding predictors to the model has significantly increased our ability to predict cost overrun.

4.4.1.3 Model Summary

| 4.14 Model Summary |  |  |  |
| --- | --- | --- | --- |
| Step | -2 Log likelihood | Cox & Snell R Square | Nagelkerke R Square |
| 1 | 213.855a | .121 | .166 |
| a. Estimation terminated at iteration number 4 because parameter estimates changed by less than .001. |  |  |  |

The most common assessment of overall model fit in logistic regression is the likelihood ratio test, which is simply the chi-square difference between the null model (i.e., with constant only table 4.14) we see that –2Log Likelihood statistic is 213.855. This statistic measures how poorly the model predicts cost overrun, the smaller the statistic the better the model. SPSS does not give this statistic for the model that had only the intercept; we know it to be 237.24 (213.855 + 23.385). Adding the predictors reduced the -2Log Likelihood statistic by 237.24- 213.855 = 23.385, which is the X^2statistic for omnibus test.

4.4.1.4 Hosmer and Lem test

| Step | Chi-square | df | Sig. |
| --- | --- | --- | --- |
| 1 | 6.533 | 8 | .588 |

| Table 4.15 Hosmer and Lemeshow Test |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | cost overrun = no |  | cost overrun = yes |  | Total |
|  |  | Observed | Expected | Observed | Expected |  |
| Step 1 | 1 | 13 | 13.102 | 5 | 4.898 | 18 |
|  | 2 | 10 | 9.854 | 8 | 8.146 | 18 |
|  | 3 | 9 | 8.375 | 9 | 9.625 | 18 |
|  | 4 | 9 | 7.637 | 10 | 11.363 | 19 |
|  | 5 | 3 | 6.504 | 15 | 11.496 | 18 |
|  | 6 | 6 | 5.686 | 12 | 12.314 | 18 |
|  | 7 | 7 | 5.027 | 11 | 12.973 | 18 |
|  | 8 | 3 | 4.468 | 15 | 13.532 | 18 |
|  | 9 | 3 | 4.010 | 15 | 13.990 | 18 |
|  | 10 | 5 | 3.336 | 14 | 15.664 | 19 |

Another method of assessment for overall goodness of fit is by using the Hosmer- Lemeshow test. The Hosmer-Lemeshow test is performed by dividing the predicted probabilities into deciles (10 groups based on percentile ranks) and computing a Pearson chi-square that compares the predicted to the observed frequencies (in table). An insignificant chi-square indicates a good fit to the data and, therefore, good overall model fit. Since the p-value is 0.588 which is insignificant therefore our fitted logistic regression model is good fit or there is no difference between observed and model predicted values, implying that the model estimates are adequate to fit the data at an acceptable level. (Table 4.15).

4.4.1.5 Variables in the Equation

Table 4.16 Variables in the Equation

|  | B | SE | Wald | df | Sig. | EXP(B) |
| --- | --- | --- | --- | --- | --- | --- |
| Factors related to contractor | .274 | .131 | 4.378 | 1 | .036 | 1.315 |
| Economic factors | -.044 | .122 | 0.131 | 1 | .718 | 0.957 |
| Consultant-related factors | .168 | .139 | 1.458 | 1 | .227 | 1.183 |
| Owner-related factor | .436 | .159 | 7.515 | 1 | .006 | 1.547 |
| Timeliness of payment and financial factors | .423 | .139 | 9.324 | 1 | .002 | 1.527 |
| Constant | -4.422 | 1.256 | 12.3871 | 1 | .000 | .012 |

- Variable(s) entered on step 1: Factors related to contractor, Economic factors, Consultant-related factors, Owner-related factor, Timeliness of payment and financial factors.

One of the problems of simple binary logistic regression approach is the ignorance of the probability that a collection of variables each of which is weakly associated with the outcome can become an important predictor of the outcomes when taken together. There are many variable selection procedures; among those researcher use backward elimination procedure to select the best variables of the model. Backward elimination is the procedure of selecting variable starting from regressing all variables at a time and removes the variable which has minimum Wald test or maximum p-value as compared to the level of significance (Table 4.16).

Each additional unit increase in concentration of contractor on the project was associated with an increase of 1.315 (13.15%) in the odds ratio to overcome of the project cost overrun problem.

The unit increase in adequate decision making by Owner of the project on the project was associated with an increase of 1.547(15.47%) in the odds ratio to manage the project cost overrun problem.

Each additional unit increase in good management of financial sector on the real estate construction project was associated with an increase of 1.527 (15.27%) in the odds ratio to manage of the project cost overrun problem.

4.5 Presentation and Analysis of the Interview Data This section presents the replies found from the interview on project cost overrun. The interview was presented to the management, contractors, consultants, clients and others participant of the Real estate construction projects in Addis Ababa. 4.5.1 The way of cost of the project determined One of the study participants of interviews stated here view saying: We are always thinking the way how to determine the project cost and profits, mostly the cost of project is determined by capacity of projects financial sector, market price of construction material, the design of project and the time it take to complete the project. This study also investigated that the owner of the projects concentrate these factors in the processes of prepare the budget of the project. Therefore cost determination of the project has power of trapping and retaining the great development of our project and we give great concern for cost determination of project even before starting the construction work.

    - Projects resources distribution for construction

Other study participants of interviews stated his/her view about the project resources distribution for construction:

We are serious on resource allocation and mobilization for project construction.  Resource is efficient distribution between projects, since in the private projects it related with good management and capacity of owner of the projects. Generally majority of respondents argued that the efficient distribution of resource is not a problem, since it’s determined by the capacity of the owner of the project, Even though it is difficult to conclude the efficient distribution of resources is fair or not it is somewhat good. For the reason that still there is no complaint from the respondents towards the efficient resource distribution among the projects. Therefore, there is efficient resource distribution between projects.

    - Factors for project cost overrun?

Other participants of interviews also stated his/her view about the factor that affected cost overrun project:

Obviously the factor of project cost overrun we are classified under a serious condition which means external and internal factors. Among the external or internal factor around 70% was financial factors which is the most factor that affects the overall project cost overrun in different perspectives followed by and constructor related factor. Rest of respondents replied that consultant, owner of the project, economic, and political situation is the factors for the project cost overrun. Therefore, we can conclude from the respondent’s feedback financial and constructor is factors for the project cost overrun.

    - Projects cost incurred due to schedule delay

Most of the interviewees replied that the project incurred cost, due to schedule delay. Even though it is difficult to generalize the project incurred cost because of schedule delay we conclude that from large number of respondents view the project incur cost.

4.5.5 The relationship between size of the project and rate of cost overrun

For this question the interviewees have common view, all of interviewees said that the size of the projects and the rate of cost overrun is positive relationship. These means from their response the probability of project cost overrun is high in the large projects than small project. Therefore, we can conclude that the owner of the project give high concentrate on cost estimation of the project regarding to the size of project.

# CHAPTER FIVE:-

# SUMMARY, CONCLUSION AND RECOMMENDATIONS

## 5.1 Summary of Major Findings

Majority of the respondents were in state of providing well response about their performance and their observation of the cost overrun cause and its effects. The result we can conclude that the construction project in the study organizations was incurred cost overrun and the project has many consequences both in terms of cost and market competition.

Based on the result majority of the respondents were said that the project or the real estate construction project has been using budgetary estimate. Overall the grand mean (Pooled mean) 3.73 shows that the construction projects were cost overrun problem as a result of different factors like Risks were not planned for and not properly allocating, the money whenever it needed, Unclear, unstable and incomplete requirement statement and inappropriately assigned cost for it and the project is complexity and large that can hinder the performance of the sectors.  But the company is working well in managing the time between design and procurement phases.

The descriptive analysis result shown above the highest mean score 9.8 is given to financial factor. This shows respondents were agreed that financial factor is one of the factors which affect the competition of the project with planed budget.

As the mean score (9.4) shows contractor related factors has one of the factors affecting the competition of the project with planed budget. Since the construction project needs different inputs to accomplish within a planed budget.

The logistic regression result that the financial factor is a key determinant of project cost overrun. The result obtained in this study showed that the rate of the project which has good financial management is lover the problem of project cost overrun than the project which has not good financial management. As a result better financial management is lead to project completion with the initial planed budget than the project which has the problem of financial management.

The study was concluded that from the listed factors financial is the most critical factor which affects the overall project cost overrun in different perspectives the second factor was Owner-related factors undeniable effects on the construction project cost overrun problem, the third ranked factor was contractor related has an effects on construction project cost overrun. This shows the construction sector has been affected by many internal and external factors, this leads to lack construction completion with initial budget.

From the variable that has been incorporated in the regression models economic factor and consultant-related factor are statistically insignificant or it doesn’t have a cause and effect relationship with project cost overrun since the p value of both variables is greater  than 0.05.

## 5.2 Conclusions

The purpose of the study was the overall objectives of the study to assess factor affecting projects cost overrun on real estate construction projects in Addis Ababa city and to make the analysis the study was used both descriptive and inferential or econometrics statistic like mean, standard deviation, and logistic regression were used.

The study organization is using budgetary system to control the resource that has been used. This system is helpful to rank out the most important expenditures based on the major components of the projects. But the techniques accuracy is less since the plan is done within the actual planning stage of the projects, since the market is in state of dynamics. Since the construction sector has vulnerable to unpredictable and every changing market so determining the price of the product is one of the factors that can help to improve construction project performance.

The study was concluded that from the listed factors financial is the most critical factor which affects the overall project cost overrun in different perspectives the second factor was Owner-related factors undeniable effects on the construction project cost overrun problem, the third ranked factor was contractor related has an effects on construction project cost overrun. This shows the construction sector has been affected by many internal and external factors, this leads to poor construction completion with initial budget.

From the regression result financial factors, Owner-related factor and Factors related to contractor has statistically significant relationship with project cost overrun since the p value is 0.05 which is less than the cut point. The result shows the above explanatory variables has a cause and effects relationship with project cost overrun.

## 5.3 Recommendations

Based on the findings of the research, the following recommendations are proposed:

Related to financial resource, it is found that construction of real estate have limited financial access adding that even the available financial resource is not managed efficiently. Moreover, it’s found that there is the existence of project financial diversion. Thus, it is recommended to devise a strong auditing procedures and mechanisms of controlling financial diversion to make sure that the financial resource are put and used for the intended purpose i.e. for construction of the project.

Additionally financial factor like slow decision making and inadequate budget management are one of the determinants of project cost overrun so the organization should give more emphasis to improve the project financial sector and needs to prioritize the tasks based on its importance to project achievement in the planed budget.

As a result of Owner-related factor the problem of unity between members of the project team and the owner of project was forced to the problem of project cost overrun so the organization should keep the team work with the owner of projects informed of every additional cost and change of plans.

The organization should make the units affordable by designing adequate range and having the operational excellence that incorporates with resource utilization and costs minimization.

The organization should work closely with the concerned bodies to cope with every changing market of constructions sectors by Setting up factories to produce building construction materials by the organizations

Use project management tools and techniques systematically for efficient planning and controlling the project activities.

Ensure efficient time management through proper resource planning and good site management system for the different activities of the project.

Reference

Abd-Karim, A., Memon, A. and Abdul-Rahman, I. 2013: Relationship between Factors of Construction Resources Affecting Project Cost, modern applied science. vol 7 . no.1.

Abdul Rahman, “Significant factors causing cost overruns in large construction projects in Malaysia,” Journal of Applied Sciences, vol. 13, no. 2, pp. 286–293, 2013.

Ahady et al ( 2017),  A study of the causes of cost overrun in construction industry in Afghanistan, A number of factors are responsible for the poor cost performance and increases in the cost of the construction in Afghanistan.

Akintoye, A. (2000). Analysis of factors influencing project cost estimating practice, Construction Management Economics, 18: 77 – 89.

Alfouzan, A. 2013: Analyzing the factors that lead to housing and construction cost escalation: A case study focused on Riyadh, Saudia Arabia. M.Sc. thesis, Western Kentucky University, Bowling Green, Kentucky.

Alla- Momanii (1996], Researches on construction projects

Ammar, .2009: Risk Allocation and Response in the Egyptian Barrage Projects, Thirteenth International Conference on Structural and Geotechnical

Ameh O J. Significant factors causing cost overruns in Telecommunication projects in  Nigeria. Journal of  Construction in Developing Countries. 2010;15(2): 49–67p

Andric, (2019).The Cost Performance and Causes of Overruns in Infrastructure Developments inAsia, Journal of Civil Engineering and Management, 25 (3): 203 – 214. https://doi.org/10.3846/jcem.2019.8646.

Apolot, 2012:  An Investigation into the Causes of Delay and Cost Overrun in Uganda‟s Public Sector Construction Projects”, Second International Conference on Advances in Engineering and Technology.

Agresti, A. 1996.  An introduction to categorical data analysis second edition. John Wiley and

Son Inc, New York.

Azhar and Farouqi,  (2008) Factors Influencing   Cost Overruns on Construction Projects in the Gaza Strip: Master’s Thesis: The Islamic University of Gaza.

Azhar, Cost  overrun  factors in construction industry of Pakistan." In First International Conference on Construction In Developing Countries (ICCIDC–I), Advancing and Integrating Construction Education, Research & Practice, pp. 499-508. 2008.

Bageis, A. and Fortune. C. 2009: Factors Affecting the Bid/No bid Decision in the Saudi Arabian Construction Contractors, Construct Manage Econom 2009;27:53-71.

Banaitiene, N. and Banaitis, A. 2012: Risk management – current issues and challenges, chapter 19, InTech, Croatia.

Bari,. (2012). Factors influencing the construction cost of Industrialized Building System  (IBS) projects, Procedia – Social and Behavioral Sciences, 35: 689 – 696.

Chan Dissanayaka. W., Kumaraswamy MM. (2008) A comparative study of causes of time overruns in Hong Kong construction projects. International Journal project Management 1997;15(1):55-63.

Chan, S. L., & Park, M. (2005). Project cost estimation using principal component regression, Construction Management Economics, 23: 295 – 304.

Chatterjee, S. and Hadi, A.S 2006. Regression analysis by example. Fourth edition, John Wiley

and Sons, Inc., Hoboken, New Jersey.

Chileshe, N., and Berko, P. D. (2010).  "Causes of project cost overruns  within the Ghanaian road construction sector." Proc., Proceedings 5th Built Envi-ronment Conference, (ASOCSA) Association of Schools of Construction of Southern Africa, ed., Bellville (South Africa), 66–81

Chism, N., & Armstrong, G. (2010). Project delivery strategy: getting it right. KPMG International, pp.1-24.

Chitkara Ashok-Chitkara University of Management Chandigarh,2004

Construction Enterprise in Ethiopia’ IGNOU-SMU, School of Management studies.

Cook, R.D., 1998. Regression graphics: ideas for studying regression through graphics. Wiley

and Sons, New York.

Corbetta, P. (2003). Social research: theory, methods and techniques. SAGE

Creswell, J. W. (2012). Research Design (3rd ed.).SAGE Publications, Inc.

Datta, B. (2002). Management of infrastructure projects in urban local bodies: case study of Kanpur Development Authority, India Infrastructure Report, 207–211.

Dissanayaka, S. M., and Kumaraswamy, M. M. (1999).  “Evaluation of factors affecting time and cost performance in Hong Kong building projects." Eng, Const and Arch Man, 10.1108/eb021119, 287–298.

Doloi, "Cost overruns and failure in project management: Under-standing the roles of key stakeholders in construction projects." Journal of construction engineering and management 139, no. 3 (2012): 267

Duncan Cramer and Dennis Howitt (2004)  Gujarati, D. N. (2004). Basic Econometrics (Fourth Edition ed.)

Elhag, l. "Critical determinants of construction tendering costs: Quantity surveyors’ standpoint." International Journal of Project Management 23, no. 7 (2005): 538-545.

Elinwa, A. U., & Buba, S. A. (1993). Construction cost factors in Nigeria, ASCE Journal of Construction Engineering and Management, 119: 698 – 713.

Endut, Intan Rohan. "Framework for minimising time overruns of Malaysian construction projects." PhD diss., Glasgow  Caledonian University, 2008.

Engineering, 13th ICSGE 27-29, Cairo, Egypt.

Enshassi,. "Factors affecting the performance of construction projects in the Gaza strip." Journal of Civil engineering and Management 15, no. 3 (2009): 269-280.

FeteneNega,(2008). “ Causes and effects of cost overrun public building construction projects in Ethiopia”.  Thesis paper for Master of Science in civil Engineering at Addis Ababa University.

Flyvbjerg, . (2004). what causes cost overrun in transport infrastructure projects? Transport Reviews, 24(1): 3-18.

Frimpong, Causes of delay and cost overruns in construction of groundwater projects in a developing countries; Ghana as a case study, International Journal of Project Management 21(2003): 321-326.

Gajewska, E. and Ropel, M. 2011: Risk Management Practices in a Construction Project, M.Sc. thesis, Chalmers University of technology, Goteborg, Sweden.

Hammad, . (2008).  "Prediction Model for Construction Cost and Duration in Jordan." Jordan Journal of Civil Engineering, 2(3), 250–266.

Hosmew W, Lemeshow S (2000) Applied logistic regression. (2nd) John Wiley and Sons, New Work, USA, pp: 1-369

Ikechukwu, A. C., & Akiohnbare, W. (2017). Factors affecting cost of construction in Nigeria, International Journal of Advancement In Engineering Technology, Management and Applied Science (IJAETMAS), 4 (6): 48 – 61.

Kaming,. “Factors influencing construction time and cost overruns on high-rise projects in Indonesia."  Construction Management & Economics 15, no. 1 (1997): 83-94.

Kirchberger, M. (2018). The Role of Construction Sector, WIDER, Working Paper No. 146.

Kothari, C. R. (2004). Research Methodology: Methods and Techniques (Second Revised Edition ed.). Jaipur, India: New Age International (P) Limited, Publishers.

Koushki, (2004). Delays and cost increases in the construction of private residential projects in Kuwait. Construction Management and Economics.

Maddala, G. S. (1992). Introductions to Econometrics (Second Edion ed.).

Mansfield, (1994).Causes of delay and cost overruns in Nigerian construction projects, International Journal of Project Management, 12(4): 254–260.

Memon, A. and Abdul-Rahman,I. 2013: Relationship between Factors of  Construction Resources Affecting Project Cost, applied science. vol 7 . no.1.

Mehamid, et al. (2013), Project Management Institute (2013), A guide to the Project Management Body of Knowledge (PMBOK guide), fifth edition

Memon, A., Rahman, I. and Abdullah, M. 2010: Factors Affecting Construction Cost in Mara Large Construction Project, International Journal of Sustainable Construction Engineering & Technology.

Merid Taye (2016) ‘Assessments of Time and Cost Overruns in construction projects: in case study at Defense

NAP. Completing the Big dig; managing the final stages of Boston’s Central Artery/Tunnel Project. Washington DC, The National Academies Press 2003. [cited Dec 05, 2011]. Available from Internet: http://www.darwin.nap.edu/books/0309088879/html>.

Odeh, A.M. & Battaineh, H.T. (2002), Causes of Construction Delay: Traditional Contracts, pp.67–

Olawale YA, Sun M. Cost and time control of construction projects: Inhabiting factors and mitigating measures in practice. Construction management and Economics. 2010; 28(5): 509–526p.

Olatunji, A. A. (2010). Influences on construction project delivery time.(PhD. thesis). Nelson Mandela Metropolitan University, Eastern Cape, South Africa.

Odeh, A.M. & Battaineh, H.T. (2002), Causes of Construction Delay: Traditional Contracts, pp.67

Pallant, J. (2011). SPSS Survival Manual: A Step by Step Guide to Data Analysis using SPSS (4th ed.). Set in 11/13.5 pt Minion by Midland Typesetters, Australia Printed in China at Everbest Printing.

Prasad, K., (2019). Critical Causes of Time Overrun in Indian Construction Projects and Mitigation Measures, International Journal of Construction Education and Research, 15 (3): 216 – 238.https://doi.org/10.1080/15578771.2018.1499569

Ramabodu, M. S., and Verster, J. J. (2010). "Factors Contributing to Cost Over-runs of Construction Projects." Proc., Proceedings 5th Built Environment Conference,(ASOCSA) Association of Schools of Construction of Southern Africa, ed., Bellville (South Africa), 131–143.

Razali, N. M., and Wah, Y. B. (2011). Power Comparisons of Shapiro-Wilk, Kolmogorov Smirnov, Lilliefors and Anderson-Darling tests. Journal of Statistical Modeling and Analytics, 2(1), 21 – 33

Reddy, O.C., Likassa, H.T., & Asefa, L. (2015). Binary Logistic Regression Analysis in Assessing and Identifying Factors that Influence the Use of Family Planning: The Case of Ambo Town, Ethiopia. International Journal of Modern Chemistry and Applied Science, 2(2), 108-120.

Roachanakanan, K. (2005). A case study of cost overruns in a Thai condominium project,PhD thesis, Texas: Texas A&M University.

Schexnayder, C., Fiori, C. and Weber, S. (2003). Project cost estimating; a synthesis of highway practice, Arizona. Available from Internet: <http://www4.trb.org/trb/crp.nsf/All+Projects/NCHRP+20-7>.

Shaqour, E. 2014: An approach to Control Cost overrun in Construction Projects of Egypt, Doctor Dissertation in Architecture Engineering, faculty of Engineering, Cairo University, Egypt.

Stevenson, M 2008. An introduction to logistic regression. Epicenter, Massey University,

Newzeland. Page 1-28.

Stoy, C., & Schalcher, H.R. (2007). Residential building projects: building cost estimators and drivers, ASCE Construction Engineering and Management, 133: 139 – 145.

Stoy, C.,(2008). Drivers for cost estimating in early design: case study of residential construction, ASCE Construction Engineering and Management, 134: 32 – 39.

Tyler, E. J. (2004).  National Electrical Estimator, Craftsman Book Company, California.

Umar Isma'il, (2013). "Prioritizing Cost Overrun causes in the Nigerian Road construction." IJCRB,

Widerman  Glossary of Project Management Terms.

### Weiss EL, et al. (2000) Effects of urban land expansion on the regional meteorology and air quality of eastern China.

Wooldridge, J. M. (2013). Introductory Econometrics: A Modern Approach (fifth edition ).

Xiao, H., & Proverbs, D. (2002). The performance of contractors in Japan, the UK and USA: A comparative evaluation of construction cost, Construction Management and Economics, 22: 425 – 435.

Yang and Ye, 2010); General definition of Residential real estate

Zujo 2010: Contracted Price Overrun as Contracted Construction Time Overrun Function, Technical Gazette, Vol.17 No.1.

# Appendixes

AMBO UNIVERSITY

COLLEGE OF BUSINESS AND ECONOMICS

DEPARTEMENT ACCOUNTING AND FINANCE

Questioners and Interview for Respondents

Dear respondents: This questionnaire is prepared for research purpose entitled “factor that affecting the determinants of projects cost overrun on real estate construction projects: the case of Addis Ababa city: The expected respondents of this questionnaire will be Professional Staff of the company who are working in the selected project.

The questionnaire will not take more than 15 minutes of your time. I do not foresee that you will experience any negative consequences by completing this questionnaire. The researcher will keep any individual information provided herein confidential, not to let it out of his possession, and to analyze the feedback received only at a group level. It will be a great contribution if you may complete all the items covered in the questionnaire since your opinion is of utmost importance for this study. I thank you in advance for sharing your valuable experience and time in completing the questionnaire.

General instruction

1. Please do not write your name in the questionnaires

2. Your participation is voluntary .i.e., there is no penalty if you do not participate.

3. Please simply circle on the appropriate choices, tick (√) on the space given in the table   to the closed ended questions and give an explanation to the open-ended question.

Name of student: Abdisa Angasa

Address: email, abdisaangasa@gmail.com

Tel: 0911336238

Part one: Demographic Characteristics of the respondents

- Gender:

- Male                                                          B. Female

- Age

- 21-30                                                         C. 41-50

- 31-40                                                         D. Above 50

3. What is your educational qualification?

A.  Diploma                                                                        B. BA/ BSC

C. Master’s Degree and Above

4.  What is your current position in the organization?

A.  Project manager                                       C. Consultant

B.  Contractors                                               D. Site Engineers

E. other-----------------------------------------

5. How long have you been working for your current organization?

A. 1-5 years                                                    C. 11-15 years

B. 6-10 years                                                  D. Above 15 years

6. Delay time

A. Less than 5 month                                     C. 13-25 month

B. 6-12 Month                                               D. above 25 Month

7. Which of the cost estimation technique was used?

A. Budgetary Estimate                                 C. Rough order of magnitude

B. Definitive Estimates                                 D. Other----------------------------

Part two: Factor that affecting the determinants of projects cost overrun

Don’t forget to put tick if it is a factor determining for construction project cost overrun. Each scale represents the following rating:

Please tick and fill in the blanks if you select others. Each scale represents the following rating:

1 = strongly disagree 2 = Disagree 3 = Neutral 4 = Agree 5 = strongly agree

| No | Items | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | The project is complex and large |  |  |  |  |  |
| 2 | New technology is not involved on the construction process |  |  |  |  |  |
| 3 | Risks were not planned for and improperly managed |  |  |  |  |  |
| 4 | Delay between design and procurement phases |  |  |  |  |  |
| 5 | Unclear, unstable and incomplete requirement statement and inappropriately assigned cost for it |  |  |  |  |  |
| 6 | Rework and additional work |  |  |  |  |  |
| 7 | Inadequate monitoring of funds |  |  |  |  |  |

1 = strongly disagree 2 = Disagree 3 = Neutral 4 = Agree 5 = strongly agree

1.  Factors related to contractor

| No | Factors related to contractor | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Shortage of construction material and inflection problem has led to project cost overrun |  |  |  |  |  |
| 2 | Project on the site have been led to cost overrun due to lack of adequate decision making by the contractors |  |  |  |  |  |
| 3 | Contractor’s planning experience influences the cost of projects completion |  |  |  |  |  |
| 4 | Evaluation steps held by the contractor influence projects completion at the initial (planed) costs |  |  |  |  |  |
| 5 | Contractor is not use the update technology on the construction process |  |  |  |  |  |

- Economic Factors

| No | Economic factors | 1 | 2 | 3 | 4 | 5 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | The project in the site have been led to project cost overrun due to lack of efficient quality control techniques |  |  |  |  |  |  |
| 2 | The project in the site have been led to project cost overrun because of variation in market price |  |  |  |  |  |  |
| 3 | The project in the site have been led to project cost overrun due to decline in purchasing power of birr compared to the dollar |  |  |  |  |  |  |
| 4 | The project complicity and large size have been led to project cost overrun |  |  |  |  |  |  |

- Consultant-related factors

| NO | Consultant-related factors | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Lack of experienced consultancy staff has led to the project cost overrun |  |  |  |  |  |
| 2 | Projects in the site have been led to cost overrun problem due to lack adequate Preparation of project related documents |  |  |  |  |  |
| 3 | Poor communication between members of the project team has led to project cost overrun |  |  |  |  |  |
| 4 | The project cost estimation has not been achieved because of lack of proper planning |  |  |  |  |  |
| 5 | Unclear, unstable and incomplete requirement statement and inappropriately assigned cost for the project |  |  |  |  |  |

- Owner-related factors

| No | - Owner-related factors | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Unrealistic contract duration imposed by owners have been led to project cost overrun |  |  |  |  |  |
| 2 | Project on the site have been led to cost overrun due to lack of adequate decision making by the owner |  |  |  |  |  |
| 3 | The absence of good contract management by the owner is led to the problem of project cost overrun |  |  |  |  |  |
| 4 | Lack of the working relationship between an owner and a contractor have been led to project cost overrun problem |  |  |  |  |  |

- Timeliness of  Payment and Financial Factors

| No | - Timeliness of Payment and Financial Factors | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Lack of payment in time and slow financial procedures has led to project cost overrun |  |  |  |  |  |
| 2 | Limited authority among supervision of financial staff have overcome the problem of project cost overrun |  |  |  |  |  |
| 3 | Absence risk allocation mainly on the contractor has led to the project cost overrun |  |  |  |  |  |
| 4 | Inadequate monitoring of funds have been led to project cost overrun |  |  |  |  |  |

Part three: Questions to answer specific objectives (factor that affecting the determinants of projects cost overrun)

Rank the items presented in the table from 1st to 5th based on their effects in projects cost overrun. You may leave item/s unranked that you believe have no contribution for project cost overrun.

| No | Factors | Rank |
| --- | --- | --- |
| 1 | Contractors related factors |  |
| 2 | Economic factors |  |
| 3 | Consultancies factor |  |
| 4 | Owner-related factors |  |
| 5 | Financial factor |  |

Part four: Interview Questions

- How was the cost of the project determined? Can you explain the process please?

---------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------

- How efficiently was resources (manpower, money, material…) distributed for the project?

------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------

- What are the factors for project cost overrun?

------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------

- How much does your organization incurred cost due to schedule delay in the projects?

-------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------

- Compare the size of the project and rate of cost overrun?

-----------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------